## 2021 STEP Appendix 1
2021 STEP Appendix 1 - Project Status Definitions
CLOSED OUT |  |  |  | Upgrade is operation, all project activities are complete, & all close-out requirements fulfilled
COMPLETE |  |  |  | Upgrade is operation and all project activities are complete
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project; asterisk (*) indicates interim mitigation plan provided by SPP
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
RE-EVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
SUSPENDED |  |  |  | NTC/GIA suspended
NTC_ID | PID | UID | Project Owner | State(s) | Project Name | Upgrade Name | Project Type | STEP Upgrade Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200397 | 242 | 10308 | WFEC | OK | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-03-01 | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3576353.7636 | 3240000 | 4171494.22 | Delay - Mitigation | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
200229 | 772 | 11017 | SPS | TX | Line - Carlisle - Wolfforth 230 kV | Carlisle Interchange - Wolfforth Interchange 230 kV Ckt 1 | Regional Reliability | ITP | 2018-03-27 | 2017-06-01 | 2013-09-10 | 2013 ITPNT | 32429240 | 2013 | 36690708.3801 | 29936635 |  | In Service | 526525 | Wolfforth Interchange 230 kV | 526161 | Carlisle Interchange 230 kV | Build new 16.8-mile 230 kV line from Carlisle to Wolfforth South and install necessary terminal equipment. | 230 | 16.8
200397 | 844 | 11113 | WFEC | OK | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-12-31 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5088308.1795 | 4725000 | 643783.96 | On Schedule < 4 | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10
200256 | 856 | 11127 | SPS | TX | Multi - Centre St. - Hereford NE 115 kV Ckt 1 and Centre St. and Hereford 115 kV Load Conversion | Centre St. - Hereford NE 115 kV Ckt 1 | Regional Reliability | ITP | 2018-04-06 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 9247136 | 2014 | 10207107.9124 | 9543280 | 9509428.03 | In Service | 524567 | Northeast Hereford Interchange 115 kV | 524555 | Hereford Centre Street Sub | Build new 5.1-mile 115 kV line from Centre St. to Hereford NE. Convert distribution transformer high side at Centre St. from 69 kV to 115 kV. Install any necessary terminal equipment at Hereford NE. | 115 | 7.8
20097 | 938 | 11239 | TSMO | MO | Multi - Nebraska City - Mullin Creek - Sibley 345 kV (GMO) | Nebraska City - Mullin Creek 345 kV (GMO) | High Priority | HP | 2016-12-15 | 2017-06-01 | 2010-07-23 | Priority Projects | 81407015 | 2015 | 83442190.375 | 76578565 |  | Complete | 645458 | Sub 3458 (Neb Cty) | 541197 | Maryville 345 kV | Build a new 345 kV substation at Mullin Creek (formerly Maryville) with a ring bus and necessary terminal equipment. Build a new 65 mile 345 kV line with at least 3000 A capacity from the new Mullin Creek substation to the Missouri/Nebraska state border towards OPPD's Nebraska City substation. | 345 | 65
20104 | 947 | 11261 | AEP | OK | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | TS | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6379395 | 6072000 |  | Complete | 509806 | ONETA 138KV | 509786 | BROKEN ARROW NORTH - SOUTH TAP | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33
20130 | 1036 | 11372 | SPS | TX | Line - Soncy convert load to 115 kV | Soncy Tap 115 kV - New Soncy 115 kV | Regional Reliability | ITP | 2018-12-31 | 2015-06-01 | 2011-02-14 | 2010 STEP | 929500 | 2014 | 1025994.0813 | 6411523 | 4088429.32 | Complete | 524252 | Soncy Tap 115 kV | 524254 | New Soncy 115 kV | Convert 1.04 miles of Z33 to 115 kV service by tapping the 115 kV line from Sunset Substation to Coulter Interchange at I-40 & Soncy Street. At Soncy Sub split the converted Z33 line off the 69 kV bus and terminate to a new 115/13.2 kV transformer to serve the Soncy distribution load. Install new 115/13.2 kV distribution transformer. Leave 69 kV underground cable to Lawrence Park to be fed by Y72 out of Coulter Interchange. | 115 |  |  | 1.04
200297 | 1139 | 11501 | SPS | TX | Line - Allen Sub - Lubbock South Interchange 115 kV Ckt 1 | Allen Substation - Lubbock South Interchange 115 kV Ckt 1 | Regional Reliability | TS | 2019-04-26 | 2019-06-01 | 2015-05-05 | SPP-2012-AG3-AFS-9 | 1164782 | 2015 | 1285701.3856 | 183738 |  | Complete | 526268 | Lubbock South Interchange 115 kV | 526213 | Allen Sub 115 kV | Rebuild 6-mile 115 kV line from Lubbock South Interchange to Allen substation. | 115
200369 | 1142 | 11506 | SPS | TX | Line - Canyon East - Randall 115 kV Ckt 1 Rebuild | Canyon East Sub - Randall County Interchange 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2020-03-20 | 2014-02-01 | 2016-02-12 | SPP-2011-AG3-AFS-11 | 12806065 | 2016 | 14135499.6172 | 6657686 | 5534931.21 | Complete | 524364 | Randall County Interchange 115 kV | 524523 | Canyon East Sub 115 kV | Rebuild 13.5-mile 4/0 segment of 115 kV line from Canyon East Sub to Randall County Interchange. | 115 | 18.5
20080 | 30201 | 50208 | NPPD | NE | Device - Clarks 115 kV | CLARKS 115KV | Regional Reliability | ITP | 2018-06-01 | 2012-11-01 | 2010-02-08 | 2009 STEP | 700000 | 2014 | 772669.023 | 700000 |  | Delay - Mitigation | 640436 | Clarks |  |  | Add a 18 Mvar capacitor bank at Clarks substation 115 kV bus. | 115
20080 | 30203 | 50210 | NPPD | NE | Device - Oneill 115 kV | ONEILL 115KV | Regional Reliability | ITP | 2018-07-01 | 2012-11-01 | 2010-02-08 | 2009 STEP | 700000 | 2014 | 772669.023 | 1739903 | 1739903 | Complete | 640305 | O'Neill |  |  | Add a second 18 Mvar capacitor bank at Oneill 115 kV substation for a total of 36 Mvar at this location. | 115
200253 | 30374 | 50441 | NPPD | NE | Multi - Hoskins - Neligh 345 kV | Neligh 345/115 kV Substation | Regional Reliability | ITP | 2018-06-08 | 2016-06-01 | 2014-02-19 | 2014 ITPNT | 10082325 | 2017 | 10334383.125 | 10281412 | 10381296 | Complete | 750013 | Neligh 345 kV | 640293 | Neligh 115 kV | Build new substation at Neligh. Install a new 345/115 kV transformer and all necessary 345 kV equipment at Neligh. | 345/115
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | ITP | 2024-04-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 204236579 | 204236579 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | ITP | 2024-04-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 13692681 | 13692681 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | ITP | 2024-04-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 232903698 | 232903698 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
200220 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | ITP | 2022-01-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 12543756 | 2020 | 12543756 | 12543756 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Build new Holt County 345 kV substation tap on the Grand Island - Fort Thompson 345 kV line owned by WAPA. Install necessary terminal equipment at new substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200395 | 31068 | 50447 | SPS | TX | Multi - Tuco - Yoakum 345/230 kV Ckt 1 | Tuco - Yoakum 345 kV Ckt 1 | Regional Reliability | ITP | 2020-06-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 128473352 | 2016 | 141810541.9591 | 122614354 |  | Delay - Mitigation | 525832 | TUCO Interchange 345 kV | 526462 |  | Construct new 107-mile 345 kV line from Tuco to Yoakum. Install any necessary 345 kV terminal equipment at Yoakum associated with new 345/230 kV transformer. | 345 | 107
210484 | 31068 | 50451 | SPS | TX | Multi - Tuco - Yoakum 345/230 kV Ckt 1 | Yoakum 345/230 kV Ckt 1 Transformer | Regional Reliability | HP | 2019-05-31 | 2017-06-01 | 2018-04-27 | HPILS | 5047344 | 2016 | 5435437.4095 | 10202591 |  | Complete | 526462 |  | 526460 | Amoco Switching Station 230 kV (Amoco Slaughter) | Install new 345/230 kV 640 MVA transformer at Yoakum substation. Install any necessary 230 kV terminal equipment. | 345/230
210484 | 30376 | 50452 | SPS | NM | Multi - Hobbs - Yoakum 345/230 kV Ckt 1 | Hobbs 345/230 kV Ckt 1 Transformer | High Priority | HP | 2018-03-30 | 2018-06-01 | 2018-04-27 | HPILS | 16204449 | 2014 | 17886679.6815 | 14238847 | 14113711.09 | Complete | 527896 | Hobbs Interchange 345 kV | 527894 | Hobbs Interchange 230 kV | Expand existing Hobbs substation to accommodate 345 kV terminals. Install 345/230 kV 638 MVA transformer at Hobbs. | 345/230
200309 | 30376 | 50457 | SPS | NM/TX | Multi - Hobbs - Yoakum 345/230 kV Ckt 1 | Hobbs - Yoakum 345 kV Ckt 1 | High Priority | HP | 2019-05-30 | 2020-06-01 | 2014-12-03 | HPILS | 90628750 | 2014 | 102538111.812 | 80628969 |  | Complete | 526462 |  | 527896 | Hobbs Interchange 345 kV | Construct new 52-mile 345 kV line from Hobbs to Yoakum. | 345 | 52
| 30401 | 50492 | TBD | NE | Cass Co. - S.W. Omaha (aka S3454) 345 kV | Cass Co. - S.W. Omaha (aka S3454) 345 kV Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 33126800 |  | Identified | 645740 | Sub 3740 | 645454 | Sub 3454 | Build new 28 miles 345 kV Cass Co. - S.W. Omaha (aka S3454) and associated terminal equipment | 345
200384 | 30444 | 50539 | SPS | TX | Device - Cochran 115 kV Cap Bank | Cochran 115 kV Cap Bank | Regional Reliability | TS | 2018-12-31 | 2016-06-01 | 2016-04-20 | DPA-2013-JUN-342 | 1808805 | 2016 | 1900375.7531 | 2669998 |  | Complete | 526361 | Cochran Interchange 115 kV |  |  | Install 28.8-MVAR capacitor bank at Cochran 115 kV (two 14.4-MVAR stages). | 115
200214 | 30451 | 50546 | SPS | NM | Line - Atoka - Eagle Creek 115 kV Ckt 1 | Atoka - Eagle Creek 115 kV Ckt 1 | Regional Reliability | ITP | 2018-12-31 | 2015-06-01 | 2013-02-20 | 2013 ITPNT | 20808304 | 2013 | 23542685.9818 | 23034125 | 24272585.75 | Complete | 527786 | Atoka Interchange 115 kV | 527711 | Eagle Creek 115 kV | Build new 12-mile 115 kV line from Atoka to Eagle Creek and install necessary terminal equipment. | 115 | 22.1
200229 | 30469 | 50564 | SPS | NM | Multi - Kilgore Switch - South Portales - Market St. - Portales 115 kV | Market St. - South Portales 115 kV Ckt 1 | Regional Reliability | ITP | 2018-07-13 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 6498682 | 2013 | 7352662.169 | 5145241.5 | 4850346.19 | Complete | 524949 | S Portales 115 kV | 524950 | Market ST 115 kV | Build new 6-mile 115 kV line from South Portales to Market St. and install necessary terminal equipment. | 115 | 6
200229 | 30469 | 50565 | SPS | NM | Multi - Kilgore Switch - South Portales - Market St. - Portales 115 kV | Market St. - Portales 115 kV Ckt 1 | Regional Reliability | ITP | 2018-02-07 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 15394429 | 2013 | 17417383.3589 | 14897010.5 | 15189905.47 | Complete | 524950 | Market ST 115 kV | 524924 | Portales Interchange 115 kV | Build new 10.4-mile 115 kV line from Market St. to Portales and install necessary terminal equipment. | 115 | 10.4
200200 | 30491 | 50600 | WFEC | OK | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | TS | 2017-03-01 | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  | Complete | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69
200400 | 30496 | 50609 | NPPD | NE | Multi - Bobcat Canyon 345/115 kV and Bobcat Canyon - Scottsbluff 115 kV | Bobcat Canyon - Scottsbluff 115 kV Ckt 1 | Regional Reliability | ITP | 2017-10-26 | 2014-06-01 | 2016-08-17 | 2014 ITPNT | 26027015 | 2016 | 26677690.375 | 21204480 | 21201741 | Complete | 640530 | Stegall 115 kV | 640338 | Scottsbluff | Install new 22-mile 115 kV line from Bobcat Canyon to Scottsbluff and install any necessary terminal equipment. | 115 | 23
200234 | 30503 | 50628 | WFEC | OK | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | TS | 2017-03-01 | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  | Complete | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69
200262 | 30510 | 50637 | SPS | TX | Line - Mustang - Shell CO2 115 kV Ckt 1 | Mustang - Shell CO2 115 kV Ckt 1 | Transmission Service | TS | 2019-04-29 | 2015-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 15473119 | 2014 | 17506413.8709 | 19315807 | 18699620.79 | Complete | 527146 | Mustang Interchange North Bus 115 kV | 527062 | Shell Co2 Gas Sub 115 kV | Construct new 7.7-mile 115 kV line from Mustang to Shell CO2. | 115 | 7.71
200296 | 30560 | 50698 | WR | KS | Line - Sumner County - Viola 138 kV Ckt 1 | Sumner County - Viola 138 kV Ckt 1 | Zonal Reliability | ITP | 2020-05-11 | 2019-06-01 | 2014-09-02 | 2014 ITPNT | 34432188 | 2019 | 35292992.7 | 34432188 |  | In Service | 532984 | SUMNER COUNTY 138 kV | 533075 | Viola 138kV | Build new 28-mile 138 kV line from Viola to Sumner County. | 138 | 28
200245 | 30563 | 50702 | WFEC | OK | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | ITP | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  | Complete | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138
200246 | 30573 | 50718 | AEP | LA | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695985.9 | 2014 | 7210844.4074 | 6695985.9 |  | Complete | 507716 | BROADMOOR | 507730 | FORT HUMBUG 69KV | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7
200256 | 30577 | 50723 | SPS | NM | Line - Chavis - Price - CV Pines - Capitan 115 kV Ckt 1 | CV Pines - Price 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-30 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 4158668 | 2014 | 4590391.3436 | 0 |  | Complete | 527543 | PRICE 3 115 kV | 527542 | CV-PINES 3 115 kV | Rebuild 3-mile 69 kV line from CV Pines to Price converting to 115 kV. | 115 |  |  | 3
200256 | 30577 | 50724 | SPS | NM | Line - Chavis - Price - CV Pines - Capitan 115 kV Ckt 1 | Capitan - CV Pines 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-30 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 5415053 | 2014 | 5977205.3014 | 4343227 | 1727131.44 | Complete | 527542 | CV-PINES 3 115 kV | 527541 | Capitan 115 kV | Rebuild 5-mile 69 kV line from Capitan to CV Pines converting to 115 kV. | 115 | 5 |  | 5
200242 | 30584 | 50740 | WR | KS | Line - Montgomery - Sedan 69 kV Ckt 1 | Elk Junction - Sedan 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-09-11 | 2018-06-01 | 2014-02-19 | 2014 ITPNT | 19015228 | 2016 | 20477320.6704 | 17965350 |  | Complete | 533690 | ELK JUNCTION 69 KV | 533544 | CANEY VALLEY NO. 5 SEDAN 69 KV | Rebuild 18.8-mile 69 kV line from Elk Junction to Sedan to achieve new emergency rating of 72 MVA. | 69 |  | 19
200294 | 30596 | 50757 | NPPD | NE | Multi - Broken Bow Wind - Ord 115 kV Ckt 1 | Broken Bow Wind - Ord 115 kV Ckt 1 | Regional Reliability | ITP | 2018-03-01 | 2014-06-01 | 2014-08-26 | 2014 ITPNT | 28018664 | 2018 | 28018664 | 23583074 | 29418126 | Complete | 640445 | Broken Bow Wind | 640308 | Ord | Build a new 35-mile 115 kV line from Ord to Broken Bow Wind and install necessary terminal equipment. | 115 | 42
200294 | 30596 | 50760 | NPPD | NE | Multi - Broken Bow Wind - Ord 115 kV Ckt 1 | North Loup - Ord 115 kV Ckt 1 | Regional Reliability | ITP | 2018-06-01 | 2014-06-01 | 2014-08-26 | 2014 ITPNT | 516009 | 2018 | 516009 | 548029 | 516009 | Complete | 640284 | North Loup | 640308 | Ord | Increase line clearance on 115 kV line from North Loup to Ord to 100 degree C. Upgrade disconnect switches, CTs, and jumpers at North Loup. | 115
| 30599 | 50769 | AEP | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | South Fayetteville 345/161 kV Transformer Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified |  |  |  |  | Install new 345/161 kV Transformer at South Fayetteville. | 345/161
| 30599 | 50770 | TBD | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | Chamber Springs - South Fayetteville 345 kV Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 21295800 |  | Identified |  |  |  |  | Build new 345 kV line from Chamber Springs to South Fayetteville and associated terminal equipment. | 345 | 18
| 30600 | 50771 | GMO | MO | XFR - Maryville 345/161 kV | Maryville 345/161 kV Transformer Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 541197 | Maryville 345 kV | 300097 | Maryville | Install new 345/161 transformer at Maryville. | 345/161
| 30601 | 50772 | KCPL | KS | XFR - Nashua 345/161 kV | Nashua 345/161 kV Transformer Upgrade Ckt11 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified |  |  |  |  | Increase rating of Nashua transformer to 650/715 MVA. | 345/161
| 30602 | 50773 | TBD | NE | Line - Keystone - Red Willow 345 kV | Keystone - Red Willow 345 kV Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 130141000 |  | Identified | 640252 | Keystone | 640325 | Red Willow | Build new 110 mile 345 kV line from Keystone to Red Willow and associated terminal equipment. | 345 | 110
| 30603 | 50774 | TBD | TX | Line - Tolk - Tuco 345 kV | Tolk - Tuco 345 kV Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 75718400 |  | Identified | 525549 | Tolk Station 345 kV | 525832 | TUCO Interchange 345 kV | Build new 64 mile 345 kV line from Tolk to Tuco and associated terminal equipment. | 345 | 64
| 30604 | 50775 | SEPC | KS | XFR - 2nd Holcomb 345/115 kV | Holcomb 345/115 kV Transformer Ckt2 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 531449 | HOLCOMB | 531448 | HOLCOMB | Install 2nd 345/115 kV transformer at Holcomb. | 345/115
| 30605 | 50776 | TBD | KS | Line - Neosho - Wolf Creek 345 kV | Neosho - Wolf Creek 345 kV Ckt1 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 117126900 |  | Identified | 532797 | WOLF CREEK 345 KV | 532793 | NEOSHO 345 KV | Build a new 86.4 mile 345kV line from Neosho to Wolf Creek rated at 1792 MVA | 345 | 86.4
| 30606 | 50777 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | Clinton - Truman 161 kV Ckt1 Reconductor | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 15701325 |  | Identified | 300071 | Clinton | 505502 | Truman | Rebuild 29 mile 161 kV line from Clinton to Truman. | 161 |  | 29
| 30606 | 50778 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | North Warsaw - Truman 161 kV Ckt1 Reconductor | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 1082850 |  | Identified | 505502 | Truman | 541314 | North Warsaw 161 | Rebuild 2 miles of 161 kV line from North Warsaw to Truman. | 161 |  | 2
| 30608 | 50779 | WR | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn 345/115 kV Transformer Ckt2 | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified |  |  |  |  | Install new 345/115 kV transformer at Auburn. | 345/115
| 30608 | 50780 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Swissvale 345 kV Ckt1 Voltage Conversion | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 20112700 |  | Identified |  |  |  |  | Convert 17 mile Auburn - Swissvale 230 kV line to a 345 kV line. | 345 |  |  | 17
| 30608 | 50781 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Jeffrey EC 345 kV Ckt1 Voltage Conversion | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 35493000 |  | Identified |  |  |  |  | Convert the 30 mile Auburn - Jeffrey EC 230 kV to 345 kV. | 345 |  |  | 30
| 30607 | 50782 | OGE | OK | Sub - Muskogee/Pecan Creek 345 kV | Muskogee/Pecan Creek 345 kV Terminal Upgrades | ITP20 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 34605675 |  | Identified | 515224 | MUSKOGEE 345 | 515235 | PECAN CREEK 345 | Upgrade terminal equipment at Muskogee and Pecan Creek substations to increase Muskogee - Pecan Creek 345 kV Ckts 1 & 2 ratings to 1195/1195 MVA.
200309 | 30638 | 50820 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | Kiowa - North Loving 345 kV Ckt 1 | High Priority | HP | 2018-06-01 | 2018-06-01 | 2014-12-03 | HPILS | 25716516 | 2014 | 28386221.8467 | 24115491 | 25905391.02 | Complete | 528185 |  | 527965 |  | Construct new 20.4-mile 345 kV line from new Kiowa substation to North Loving. | 345 | 20.4
200282 | 30675 | 50869 | SPS | NM | Multi - China Draw - Yeso Hills 115 kV | China Draw - Yeso Hills 115 kV Ckt 1 | High Priority | HP | 2019-05-03 | 2018-06-01 | 2014-05-19 | HPILS | 14583586 | 2014 | 16499988.9316 | 4463698 |  | Complete | 528222 | China Draw 115 kV | 528246 |  | Construct new 18.4-mile 115 kV line from China Draw to new Yeso Hills substation. | 115 | 18.4
200309 | 30639 | 50871 | SPS | NM | Multi - Potash Junction - Road Runner 345 kV Conv. and Transformers at Kiowa and Road Runner | Kiowa - Potash Junction 345/115 kV Ckt 1 | High Priority | HP | 2018-04-30 | 2018-06-01 | 2014-12-03 | HPILS | 2176451 | 2014 | 2402394.6683 | 3012621.85 | 5136294.52 | Complete | 527965 |  | 528027 | Road Runner 345 kV | Construct 1-mile of double circuit structures from the new Kiowa substation to Potash Junction. Construct Circuit 1 with 345 kV conductor and Circuit 2 with 115 kV conductor. | 345 | 2
200282 | 30672 | 50874 | SPS | NM | Multi - Dollarhide - Toboso Flats 115 kV | Dollarhide - Toboso Flats 115 kV Ckt 1 | High Priority | HP | 2018-06-01 | 2018-06-01 | 2014-05-19 | HPILS | 5062341 | 2014 | 5587877.2494 | 0 |  | In Service | 528561 | Dollarhide Sub 115 kV | 528566 |  | Construct new 7.4-mile 115 kV line from new Toboso Flats substation to Dollarhide. | 115 | 7.4
200282 | 30694 | 50877 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa 115 kV Substation | High Priority | HP | 2017-06-01 | 2018-06-01 | 2014-05-19 | HPILS | 996485 | 2014 | 1073105.3495 | 1082345 |  | Complete | 528240 |  |  |  | Construct new 115 kV Ponderosa substation. Install any necessary 115 kV terminal equipment. | 115
200474 | 30694 | 50879 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa Tap 115 kV Substation | High Priority | HP | 2017-06-01 | 2018-06-01 | 2018-02-27 | HPILS | 4174446 | 2014 | 4495421.7411 | 616860 |  | Complete | 528239 |  |  |  | Tap the existing 115 kV line from Ochoa to Whitten to construct new 115 kV Ponderosa Tap substation. Install any necessary 115 kV terminal equipment. | 115 | 0.2
200309 | 30717 | 50883 | SPS | NM | Line - Hopi Sub - North Loving - China Draw 115 kV Ckt 1 | China Draw - North Loving 115 kV Ckt 1 | High Priority | HP | 2015-05-25 | 2015-06-01 | 2014-12-03 | HPILS | 13283227 | 2014 | 13615307.675 | 11260834 | 11070902 | Complete | 528182 | North Loving 115 kV | 528222 | China Draw 115 kV | Construct new 19.7-mile 115 kV line from North Loving to China Draw. | 115 | 19.7
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | HP | 2024-04-01 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 10792106.9665 | 9797157 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
200395 | 30692 | 50920 | SPS | TX | XFR - Seminole 230/115 kV #1 and #2 | Seminole 230/115 kV #1 Transformer | Regional Reliability | ITP | 2018-12-28 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3621405 | 2016 | 3804738.6281 | 3312055 |  | Complete | 527276 | Seminole Interchange 230 kV | 527275 | Seminole Interchange 115 kV | Replace first existing 230/115 transformer at Seminole. | 230/115
200395 | 30692 | 50921 | SPS | TX | XFR - Seminole 230/115 kV #1 and #2 | Seminole 230/115 kV #2 Transformer | Regional Reliability | ITP | 2019-04-30 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3621405 | 2016 | 3899857.0757 | 2519547 |  | Complete | 527276 | Seminole Interchange 230 kV | 527275 | Seminole Interchange 115 kV | Replace second existing 230/115 transformer at Seminole. | 230/115
200421 | 30693 | 50922 | SPS | TX | XFR - Wolfforth 230/115 kV Ckt 1 Transformer | Wolfforth 230/115 kV Ckt 1 Transformer | Regional Reliability | TS | 2021-04-15 | 2021-06-01 | 2017-01-12 | SPP-2015-AG2-AFS-3 | 3510969 | 2017 | 3780929.5832 | 3400766 |  | On Schedule < 4 | 526525 | Wolfforth Interchange 230 kV | 526524 | Wolfforth Interchange 115 kV | Replace 230/115 kV transformer at Wolfforth substation. | 230/115
200411 | 30694 | 50923 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa - Ponderosa Tap 115 kV Ckt 1 | High Priority | HP | 2017-06-01 | 2018-06-01 | 2016-08-17 | HPILS | 8030702 | 2016 | 8231469.55 | 9170509 |  | Complete | 528239 |  | 528240 |  | Construct new 9.3-mile 115 kV line from new Ponderosa substation to new Ponderosa Tap substation. | 115 | 9.3
200420 | 30699 | 50943 | SPS | TX | Line - Northwest - Rolling Hills 115 kV Ckt 1 | Northwest - Rolling Hills 115 kV Rebuild Ckt 1 | Regional Reliability | TS | 2021-05-15 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 4514434 | 2017 | 4861551.6292 | 5081459 |  | On Schedule < 4 | 524007 |  | 524106 | Northwest Interchange 115 kV | Rebuild 8.3-mile 115 kV line from Northwest to Rolling Hills. | 115 |  | 7.2
200360 | 30914 | 50952 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | IMC #1 Tap - Livingston Ridge 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-03-22 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 5700000 | 2018 | 5842500 | 4706858 | 4354881.13 | Complete | 528035 | I. M. C. #1 Sub Tap 115 kV (International Mineral Co) | 527953 |  | Rebuild 9.5-mile 115 kV line from Livingston Ridge to IMC #1 Tap. | 115 |  | 9.5 | 9.3
200360 | 30914 | 50955 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Ponderosa Tap - Whitten 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-26 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 2280000 | 2018 | 2280000 | 2251591 | 1987893.3 | Complete | 528239 |  | 528540 | Whitten Sub 115 kV | Reconductor 5.9-mile 115 kV line from Ponderosa Tap to Whitten. | 115 |  | 3.92
200360 | 30914 | 50957 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Intrepid West - Potash Junction 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-03-22 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 2455000 | 2018 | 2516375 | 2355090 | 2332086.68 | Complete | 527999 |  | 527962 | Potash Junction Interchange 115 kV | Rebuild 1.5-mile 115 kV line from Intrepid West Tap to Potash Junction. | 115 |  | 1.5
200360 | 30914 | 50958 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | IMC #1 Tap - Intrepid West 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-03-22 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 3121473 | 2018 | 3199509.825 | 2664610 |  | Complete | 527999 |  | 528035 | I. M. C. #1 Sub Tap 115 kV (International Mineral Co) | Rebuild 3.9-mile 115 kV line from Intrepid West Tap to IMC #2. | 115 |  | 3.9
200282 | 30756 | 50968 | SPS | NM | Multi - Battle Axe - Road Runner 115 kV | Battle Axe 115 kV Substation | High Priority | HP | 2015-12-04 | 2018-06-01 | 2014-05-19 | HPILS | 2964499 | 2014 | 3038611.475 | 2624228 |  | Complete | 528040 |  |  |  | Construct new 115 kV Battle Axe substation. Install any necessary 115 kV terminal equipment. | 115
200282 | 30675 | 50988 | SPS | NM | Multi - China Draw - Yeso Hills 115 kV | Yeso Hills 115 kV Substation | High Priority | HP | 2019-05-03 | 2018-06-01 | 2014-05-19 | HPILS | 1046485 | 2014 | 1184001.7206 | 378378 |  | Complete | 528246 |  |  |  | Construct new 115 kV Yeso Hills substation. Install any necessary 115 kV terminal equipment. | 115
200455 | 30755 | 50992 | SPS | TX | XFR - Tuco 230/115 kV Ckt 1 | Tuco 230/115 kV Ckt 1 Transformer | Transmission Service | ITP | 2019-06-15 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 3800415 | 2015 | 4194947.0643 | 99119 |  | Complete | 525830 | TUCO Interchange 230 kV | 525828 | TUCO Interchange 115 kV | Upgrade 230/115 kV transformer at Tuco to 273 MVA. | 230/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | HP | 2024-04-01 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1079442.6353 | 913714 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
200262 | 30766 | 51039 | SPS | TX | XFR - Yoakum County Interchange 230/115 kV Ckts 1 and 2 | Yoakum County Interchange 230/115 kV Ckt 1 Transformer | Transmission Service | TS | 2019-03-15 | 2019-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 3632101 | 2014 | 4109388.8909 | 2300353 |  | Complete | 526935 | Yoakum County Interchange 230 kV | 526934 | Yoakum County Interchange 115 kV | Upgrade Yoakum County Interchange Ckt 1 230/115 kV transformer to 250 MVA. | 230/115
200262 | 30766 | 51050 | SPS | TX | XFR - Yoakum County Interchange 230/115 kV Ckts 1 and 2 | Yoakum County Interchange 230/115 kV Ckt 2 Transformer | Regional Reliability | TS | 2019-05-07 | 2019-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 3432506 | 2014 | 3883565.4693 | 3131117 |  | Complete | 526935 | Yoakum County Interchange 230 kV | 526934 | Yoakum County Interchange 115 kV | Upgrade Yoakum County Interchange Ckt 2 230/115 kV transformer to 250 MVA. | 230/115
| 30786 | 51069 | NPPD | NE | Sub - Dixon County 230kV | Dixon County 230kV Substation | Generator Interconnection | GI | 2018-10-01 |  |  | GI STUDIES |  |  | 0 | 6404189 |  | In Service |  |  |  |  | 230kV Line Terminal including four (4) breaker substation addition | 230
| 30787 | 51070 | NPPD | NE | Line - Twin Church - Dixon County 230kV Ckt 1 | Twin Church - Dixon County 230kV Line Upgrade | Generator Interconnection | GI | 2018-11-01 |  |  | GI STUDIES |  |  | 0 | 61774 |  | In Service |  |  |  |  | Increase clearances to accommodate 320MVA facility rating | 230
200382 | 30809 | 51096 | AEP | OK | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | TS | 2020-06-11 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4767920.8822 | 6445009 |  | Complete | 505610 | Keystone Dam | 509757 | WEKIWA 138KV | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2
200395 | 30844 | 51140 | SPS | TX | Sub - Amoco - Sundown 230 kV Terminal Upgrades | Amoco - Sundown 230 kV Terminal Upgrades | Regional Reliability | ITP | 2019-02-20 | 2019-01-01 | 2016-05-17 | 2016 ITPNT | 1771222 | 2016 | 1907412.3577 | 717573 |  | Complete | 526435 | Sundown Interchange 230 kV | 526460 | Amoco Switching Station 230 kV (Amoco Slaughter) | Upgrade switches and wave traps at Sundown and Amoco and increase the line clearance to increase the rating of the 230 kV line from Amoco to Sundown. | 230
200326 | 30866 | 51170 | SPS | TX | Sub - Amarillo South 230 kV Terminal Upgrades | Amarillo South 230 kV Terminal Upgrades | Regional Reliability | ITP |  | 2020-04-01 | 2015-02-18 | 2015 ITPNT | 31198 | 2015 | 35297.6733 | 0 |  | On Schedule < 4 | 524415 | Amarillo South Interchange 230 kV | 525213 | Swisher County Interchange 230 kV | Replace wave trap at Amarillo South to increase the rating of the 230 kV line from Amarillo South to Swisher County. | 230
200318 | 30883 | 51200 | NPPD | NE | Multi - Bassett 115 kV | Bassett 115 kV Substation | Regional Reliability | ITP | 2018-06-01 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 5163000 | 2015 | 5559986.2711 | 127220 | 192099 | Complete | 640580 |  |  |  | Tap the existing 115 kV line from Ainsworth to Stuart to construct the new Bassett substation. | 115 | 0.1
200326 | 30888 | 51206 | SPS | TX | XFR - Lynn County 115/69 kV Ckt 1 Transformer | Lynn County 115/69 kV Ckt 1 Transformer | Regional Reliability | ITP | 2019-05-15 | 2019-06-01 | 2015-02-18 | 2015 ITPNT | 1699629 | 2015 | 1876072.3984 | 2303946 |  | Complete | 526656 | Lynn County Interchange 115 kV | 526655 | Lynn County Interchange 69 kV | Replace 115/69 kV transformer at Lynn County substation. | 115/69
200343 | 30912 | 51235 | SPS | KS | Multi - Walkemeyer Tap - Walkemeyer 345/115 kV | Stevens Co. 345 kV Substation | Regional Reliability | ITP | 2018-06-01 | 2015-06-01 | 2015-08-13 | 2015 ITPNT | 13831957 | 2015 | 14895504.7495 | 13341462 | 13433258 | Complete | 531512 | Walkemeyer Tap 345 kV |  |  | Tap the existing 345 kV line from Finney to Hitchland to construct the new Stevens Co. substation. Install any necessary 345 kV terminal equipment. | 345 | 0.1
200360 | 30914 | 51250 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | National Enrichment Plant - Targa 115 kV Ckt 1 | Regional Reliability | ITP | 2019-03-20 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 1874116 | 2018 | 1920968.9 | 1340580 | 1095980.93 | Complete | 528603 | National Enrichment Plant Sub 115 kV | 528540 | Whitten Sub 115 kV | Rebuild 4.3-mile 115 kV line from National Enrichment Plant to Targa. | 115 | 3
200326 | 30888 | 51270 | SPS | TX | XFR - Lynn County 115/69 kV Ckt 1 Transformer | Lynn County 115 kV Terminal Upgrades | Regional Reliability | ITP | 2019-05-15 | 2019-06-01 | 2015-02-18 | 2015 ITPNT | 19425 | 2015 | 21441.5654 | 291632 |  | Complete | 526656 | Lynn County Interchange 115 kV |  |  | Install 115 kV terminal equipment at Lynn County substation necessary to replace 115/69 kV transformer. | 115
200318 | 30883 | 51277 | NPPD | NE | Multi - Bassett 115 kV | Bassett 115 kV Cap Bank | Regional Reliability | ITP | 2018-06-01 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 902000 | 2015 | 971355.3392 | 3831068 | 5563439 | Complete |  |  |  |  | Install one(1) 9-MVAR capacitor bank at the new Bassett 115 kV substation. | 115
| 30934 | 51292 | NPPD | NE | Line - Hoskins - Dixon County 230kV Ckt 1 | Hoskins - Dixon County 230kV Line Upgrade | Generator Interconnection | GI | 2018-11-01 |  |  | GI STUDIES |  |  | 0 | 308869 |  | In Service |  |  |  |  | Increase clearances on Hoskins - Dixon County 230kV line to accommodate 320MVA facility rating to address loading issues | 230
| 30946 | 51318 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule - Witten 230 kV Ckt 1 | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration | 31500000 | 2014 | 34770106.035 | 31500000 |  | Re-evaluation | 659312 | Lower Brule | 659310 | Witten | Construct new 65-mile 230 kV line from Lower Brule to Witten. | 230
| 30946 | 51319 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule 230 kV Substation | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration | 4500000 | 2014 | 4967158.005 | 4500000 |  | Re-evaluation | 659312 | Lower Brule |  |  | Install any necessary terminal upgrades at Lower Brule 230 kV to accommodate new 230 kV line from Witten. | 230
| 30946 | 51320 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule - Witten 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration | 2000000 | 2014 | 2207625.78 | 2000000 |  | Re-evaluation | 659312 | Lower Brule | 659310 | Witten | Install communication facilities associated with the new 230 kV line from Lower Brule to Witten. | 230
200376 | 30953 | 51333 | SEPC | KS | Device - Lane Scott 115 kV Cap Bank | Lane Scott 115 kV Cap Bank | Regional Reliability | TS | 2019-09-19 | 2017-06-01 | 2016-07-12 | DPA-2015-MARCH-494 | 3852342 | 2016 | 4148550.9648 | 4008888 | 4008888 | Closed Out |  |  |  |  | Install 12-MVAR capacitor bank at Lane Scott 115 kV. | 115
| 30959 | 51338 | WR | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 NU) | Generator Interconnection | GI | 2021-05-01 |  |  | GI STUDIES |  |  | 0 | 3115802 |  | On Schedule < 4 |  |  |  |  | Install three (3) 345 kV breakers, six (6) 345 kV 3000 Amp switches, two (2) 345 kV 3000 Amp motor-operated switches, six (6) 345 kV CCVTs, four (4) 345 kV wave traps, new redundant primary relaying, two (2) 345 kV full tension dead-end structures, and all associated site, yard, cable, grounding and conduit work into a new Transmission Owner GEN-2014-001 Point of Interconnection substation.; Site for Transmission Owner Substation: Site parcel to be approved by Transmission Owner, such approval to not be unreasonably withheld.; Allowance for Funds Used During Construction (AFUDC) and Contingency; Emporia Substation – Relay change-out work; Wichita Substation – Relay change-out work; New Transmission Owner Substation – Inspection costs during Construction for Option to Build (assumes using Transmission Owner preferred contractors); Wichita – Emporia Energy Center 345 kV Ckt 1: Install two (2) three-pole steel dead-end and turning structures plus associated foundations, equipment, and labor to tap and loop the Wichita – Emporia Energy Center 345 kV Ckt 1 into new Transmission Owner 345kV substation. The estimated facilities and associated costs assume that the interconnection substation is adjacent to the existing 345kV line easement.; Allowance for Funds Used During Construction (AFUDC) and Contingency
| 30956 | 51339 | NPPD | NE | Multi - GEN-2013-032 Interconnection Work | Antelope 115kV - Add terminal for GEN-2013-032 | Generator Interconnection | GI | 2017-05-01 |  |  | GI STUDIES |  |  | 0 | 2868775 |  | In Service |  |  |  |  | Install two (2) 115 kV circuit breakers and associated switches, structures, and associated equipment. Add one (1) 115 kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities; Replace one (1) 115 kV circuit breaker due to short circuit over-duty.
| 30960 | 51341 | OGE | OK | SUB - Beaver County 345kV - Add 345kV terminal for GEN-2013-030 | Beaver County Substation - Add 345kV terminal for GEN-2013-030 | Generator Interconnection | GI | 2019-10-28 |  |  | GI STUDIES |  |  | 0 | 4842217.34 |  | Complete |  |  |  |  | Beaver County 345 kV: Convert from ring bus to breaker–and-a-half configuration by installing additional rung to the existing bus layout and install five (5) 345 kV, 3000 Amp breakers, line relaying, disconnect switches, and associated equipment.
200384 | 30971 | 51358 | SPS | TX | Line - Cochran - Whiteface Tap 69 kV Ckt 1 Rebuild | Cochran - Whiteface Tap 69 kV Ckt 1 Rebuild | Regional Reliability | TS | 2018-11-28 | 2016-06-01 | 2016-04-20 | DPA-2013-JUN-342 | 2254282 | 2016 | 2368405.0263 | 2452087 |  | Complete |  |  |  |  | Rebuild 4.5-mile 69 kV line from Cochran to Whiteface Tap to 115 kV standards (operated at 69 kV). | 69
| 30959 | 51360 | WR | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generator Interconnection | GI | 2021-05-01 |  |  | GI STUDIES |  |  | 0 | 1106149 |  | On Schedule < 4 |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
200365 | 30987 | 51406 | SPS | NM | Line - Cunningham - Monument Tap 115 kV Ckt 1 Rebuild | Cunningham - Monument Tap 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2019-12-20 | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 5129356 | 2016 | 5523755.363 | 5318981 |  | Complete | 527864 | Cunningham Station 115 kV | 528568 | Monument Tap 115 kV | Rebuild 6.5-mile 115 kV line from Cunningham to Monument Tap. | 115
200366 | 30988 | 51408 | SPS | NM | Sub - Eddy Co. 230 kV Bus Tie | Eddy Co. 230 kV Bus Tie | Transmission Service | TS | 2019-12-20 | 2017-10-01 | 2016-01-12 | SPP-2013-AG3-AFS-6 | 19732223 | 2020 | 19732223 | 19315864 |  | Complete | 527800 | Eddy County Interchange 230 kV |  |  | Reconfigure 230 kV bus tie at Eddy Co. substation to convert to a double bus and breaker scheme. | 230 | 0.2
200365 | 30989 | 51409 | SPS | NM | Sub - Potash Junction 230 kV Terminal Upgrade | Potash Junction 230 kV Terminal Upgrade | Regional Reliability | TS | 2018-06-01 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 63251 | 2016 | 66453.0819 | 0 |  | Complete | 527963 | Potash Junction Interchange 230 kV |  |  | Replace wavetrap at Potash Junction 230 kV substation. | 230
200365 | 30991 | 51411 | SPS | NM | Line - National Enrichment Plant - Teague 115 kV Ckt 1 Rebuild | National Enrichment Plant - Teague 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2018-12-14 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 4915370 | 2016 | 5164210.6063 | 215414 |  | Complete | 528596 | National Enrichment Plant Tap 115 kV | 528526 | Teague Sub 115 kV | Rebuild 6.8-mile 115 kV line from National Enrichment Plant to Teague. | 115
200397 | 30995 | 51430 | WFEC | OK | Device - Harrisburg 69 kV Cap Bank | Harrisburg 69 kV Cap Bank | Regional Reliability | ITP | 2017-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 450000 | 2016 | 461250 | 450000 |  | Re-evaluation | 520933 | HARRISBURG |  |  | Install new 15-MVAR cap bank at Harrisburg 69 kV. | 69
200395 | 30999 | 51436 | SPS | TX | Sub - Potter Co. - Harrington 230 kV Terminal Upgrades | Potter Co. - Harrington 230 kV Terminal Upgrades | Regional Reliability | ITP | 2019-05-16 | 2019-06-01 | 2016-05-17 | 2016 ITPNT | 914347 | 2016 | 984651.7077 | 1191684 |  | Complete | 523959 | Potter County Interchange 230 kV | 523979 | Harrington Station East Bus 230 kV | Upgrade terminal equipment at both Potter Co. and Harrington 230 kV substations. | 230
200395 | 31001 | 51438 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Agave Red Hills - Road Runner 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2017-03-20 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 443866.42 | 2016 | 454963.0805 | 443866.42 |  | Complete | 528230 |  | 528025 | Road Runner 115 kV | Construct new 115 kV line from Agave Red Hills to Road Runner. | 115 | 0.8
200395 | 31001 | 51440 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Custer Mountain - Road Runner 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2017-04-28 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 759610.22 | 2016 | 778600.4755 | 759610.22 | 204462.1 | Complete | 528239 |  | 528025 | Road Runner 115 kV | Add new 1-mile segment to existing 115 kV line from Custer Mountain to Ochoa, re-terminating at Road Runner. | 115 | 11
200392 | 31002 | 51444 | OGE | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (OGE) | Regional Reliability | ITP | 2020-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 750000 | 2016 | 827859.6675 | 700000 |  | Complete | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 138 kV line from Lincoln to Meeker. The total estimated length of the Lincoln to Meeker line is 12 miles.OGE and Western Farmers Electric Cooperative shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138
200397 | 31002 | 51445 | WFEC | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | ITP | 2020-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6622877.34 | 6000000 |  | Complete | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
200386 | 31003 | 51446 | AEP | OK | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | ITP | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011.16 | 2016 | 518011.16 | 518011.16 |  | Complete | 510396 | NORTHEAST STATION 138KV |  |  | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138
210496 | 31007 | 51450 | SPS | TX | XFR - Sundown 230/115 kV Transformer | Sundown 230/115 kV Transformer | Regional Reliability | ITP | 2020-12-15 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 4264796 |  | 0 | 8813819 |  | Delay - Mitigation | 526435 | Sundown Interchange 230 kV | 526434 | Sundown Interchange 115 kV | Upgrade the existing 230/115 kV transformer at Sundown and replace any terminal equipment required to meet the full rating of the new transformer. | 230/115
200395 | 31008 | 51452 | SPS | NM | Multi - Artesia County 115 kV | Artesia Country Club Tap 115 kV Line Tap | Regional Reliability | ITP | 2018-12-17 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 336134 | 2016 | 353150.7838 | 378619 |  | Complete | 527711 | Eagle Creek 115 kV | 527786 | Atoka Interchange 115 kV | Tap the 115 kV line from Atoka to Eagle Creek and install 3-way switch at tap point. | 115
| 31014 | 51467 | NPPD | NE | Sub - Friend 115kV Substation - GEN-2014-039 Addition | Friend 115kV Substation - GEN-2014-039 Addition (TOIF) | Generator Interconnection | GI | 2017-10-15 |  |  | GI STUDIES |  |  | 0 | 875000 |  | On Schedule < 4 |  |  |  |  | Install 115kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, and associated and miscellaneous material.; One (1) 115 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Friend 115 kV substation.
| 31014 | 51468 | NPPD | NE | Sub - Friend 115kV Substation - GEN-2014-039 Addition | Friend 115kV Substation - GEN-2014-039 Addition | Generator Interconnection | GI | 2017-10-15 |  |  | GI STUDIES |  |  | 0 | 4300000 |  | On Schedule < 4 |  |  |  |  | Expand the substation to a ring bus configuration. Work to include the installation of three (3) 115kV circuit breakers, disconnect switches, associated bus, supports, relay panels, and all associated and miscellaneous equipment.
200407 | 31021 | 51478 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Mustang - Seminole 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2020-12-15 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 15007492 | 2016 | 16565463.1162 | 13009461 |  | Delay - Mitigation | 527146 | Mustang Interchange North Bus 115 kV | 527275 | Seminole Interchange 115 kV | Construct new 115 kV line from Mustang to Seminole. | 115 | 19.7
200407 | 31021 | 51479 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Mustang 115 kV Terminal Upgrades | Regional Reliability | ITP | 2020-12-15 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 2712194 | 2016 | 2993754.6974 | 2468876 |  | Delay - Mitigation | 527146 | Mustang Interchange North Bus 115 kV |  |  | Install terminal upgrades at Mustang 115 kV substation needed to accommodate termination of new line from Seminole. | 115 | 19.7
200407 | 31021 | 51480 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Seminole 115 kV Terminal Upgrades | Regional Reliability | ITP | 2020-12-15 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 2016340 | 2016 | 2225662.0826 | 2149144 |  | Delay - Mitigation | 527275 | Seminole Interchange 115 kV |  |  | Install terminal upgrades at Seminole 115 kV substation needed to accommodate termination of new line from Mustang. | 115 | 19.7
200395 | 31022 | 51481 | SPS | TX | Line - Canyon East Tap - Randall 115 kV Ckt 1 Rebuild | Canyon East Tap - Randall 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-05-16 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4804292 | 2016 | 5173696.9905 | 4373777 |  | Complete | 524523 | Canyon East Sub 115 kV | 524364 | Randall County Interchange 115 kV | Rebuild 3-mile segment of 115 kV line from Canyon East Tap to Randall. | 115
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | ITP | 2023-05-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4415251.56 | 4000000 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability | ITP |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2501240.0087 | 2266000 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | ITP | 2022-04-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 607097.0895 | 600000 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | ITP | 2022-04-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3311438.67 | 3600000 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
200419 | 31042 | 51531 | WFEC | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | ITP | 2024-12-01 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1507646.868 | 5700000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
200395 | 31051 | 51549 | SPS | TX | Sub - Terry Co. - Wolfforth 115 kV Terminal Upgrades | Terry Co. - Wolfforth 115 kV Terminal Upgrades | Regional Reliability | ITP | 2018-06-01 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 1461643 | 2016 | 1535638.6769 | 598187 |  | Complete | 526736 | Terry County Interchange 115 kV | 526524 | Wolfforth Interchange 115 kV | Upgrade terminal equipment at Terry Co. and Wolfforth to increase the rating of the 115 kV line from Terry Co. to Wolfforth. | 115
200386 | 31057 | 51558 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-18 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512896.75 | 2016 | 14551911.7591 | 11805970.48 |  | Complete | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69
200386 | 31057 | 51559 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146463.7 | 2016 | 16718861.87 | 15595092.29 |  | Delay - Mitigation | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 23918059.8437 | 21981547.8 |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
200420 | 31061 | 51565 | SPS | NM | Line - Livingston Ridge - Wipp 115 kV Ckt 1 Rebuild | Livingston Ridge - Wipp 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2021-04-15 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 264157 | 2017 | 284468.1955 | 296645 |  | On Schedule < 4 | 527952 | Livingston Ridge Sub 69 kV | 528009 | WIPP Sub 115 kV | Rebuild 2.8-mile 115 kV line from Livingston Ridge to Wipp. | 115
200420 | 31063 | 51567 | SPS | NM | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 826348.7866 | 890000 |  | On Schedule < 4 | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
200418 | 31042 | 51569 | OGE | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (OGE) | Regional Reliability | ITP | 2019-04-17 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 7723383 | 2017 | 8114379.2644 | 4562494.75 |  | Complete | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. OGE and Western Farmers Electric Cooperative shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138
| 30786 | 51577 | NPPD | NE | Sub - Dixon County 230kV | Dixon County 230kV Substation (TOIF) | Generator Interconnection | GI | 2018-11-01 |  |  | GI STUDIES |  |  | 0 | 501197 |  | In Service |  |  |  |  | Dixon County 230kV Substation Addition: Build 230kV Substation addition on the Twin Church – Hoskins 230kV to accommodate new 230kV interconnection. Includes: 230kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities to the new Transmission Owner substation. | 230
| 30937 | 51602 | SPS |  | SUB - TUCO 230kV Switching Station GEN-2012-020 Addition | TUCO 230kV Switching Station GEN-2012-020 Addition (TOIF) | Generator Interconnection | GI | 2018-12-14 |  |  | GI STUDIES |  |  | 0 | 260000 |  | On Schedule < 4 |  |  |  |  | TUCO 230kV Switching Station: Communications; Revenue Metering; 230kV Line arrestors.
| 30960 | 51609 | OGE | OK | SUB - Beaver County 345kV - Add 345kV terminal for GEN-2013-030 | Beaver County Substation - Add 345kV terminal for GEN-2013-030 (TOIF) | Generator Interconnection | GI | 2019-10-28 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | Complete |  |  |  |  | Beaver County 345 kV: Add one (1) 345 kV line terminal including dead-end structure, substation steel, substation bus, interconnection metering, line switch and associated equipment. No additional Right-of-Way is included in this cost.
| 30956 | 51610 | NPPD | NE | Multi - GEN-2013-032 Interconnection Work | Antelope 115kV - Add terminal for GEN-2013-032 (TOIF) | Generator Interconnection | GI | 2018-10-03 |  |  | GI STUDIES |  |  | 0 | 873106 |  | In Service |  |  |  |  | Add one (1) 115 kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities to the new Transmission Owner substation.
200444 | 31079 | 51623 | SPS | TX | Sub - Tuco - Stanton 115 kV Terminal Upgrades | Tuco - Stanton 115 kV Terminal Upgrades | Economic | ITP | 2018-12-31 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 283963 | 2017 | 291062.075 | 0 |  | In Service | 525828 | TUCO Interchange 115 kV | 526076 | Stanton Sub 115 kV | Upgrade any necessary terminal equipment at Stanton and/or Tuco to increase the rating of the 115 kV line between the two substations. | 115
200444 | 31081 | 51625 | SPS | TX | Sub - Indiana - SP-Erskine 115 kV Terminal Upgrades | Indiana - SP-Erskine 115 kV Terminal Upgrades | Economic | ITP | 2020-02-28 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 1133153 | 2017 | 1220281.8367 | 0 |  | Delay - Mitigation | 526146 | Indiana Sub 115 kV | 526109 | South Plains REC-Erskine 115 kV | Upgrade any necessary terminal equipment at Indiana and/or SP-Erskine to increase the rating of the 115 kV line between the two substations. | 115
200428 | 31085 | 51630 | KCPL | MO | Device - Northeast - Charlotte - Crosstown 161 kV Reactor | Northeast - Charlotte - Crosstown 161 kV Reactor | Economic | ITP | 2018-03-01 | 2018-01-01 | 2017-02-22 | 2017 ITP10 | 500000 | 2017 | 512500 | 204681 | 204681 | Complete | 542985 | NORTHEAST 161 KV | 542990 | CROSSTOWN 161 KV | Install new 2-ohm line reactor at Northeast substation on the 161 kV line from Northeast to Charlotte to Crosstown. | 161
200458 | 31086 | 51631 | WR | KS | Line - DePaul - Girard Jct - Franklin - Frontenac 69 kV | DePaul - Girard Jct 69 kV | Regional Reliability | TS | 2018-11-15 | 2018-12-31 | 2017-06-23 | DPA-2016-March-596 | 2908572 | 2017 | 2981286.3 | 5699405 | 5699405 | Complete |  |  |  |  | 1.71 miles of the existing DePaul-Girard Jct. 69 kV line will be rebuilt with single 1192.5 Bunting ACSR. | 69 | 1.71
200433 | 31144 | 51764 | WFEC | OK | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | ITP | 2021-12-31 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 107689.062 | 410000 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
200457 | 31175 | 51818 | SPS | TX | Line - Cox Interchange - Hale Co Interchange 115 kV Rebuild | Cox Interchange - Hale Co Interchange 115 kV Ckt 1 | Regional Reliability | TS | 2021-04-15 | 2021-06-01 | 2017-05-15 | SPP-2016-AG1-AFS-3 | 13355250 | 2017 | 14382143.4528 | 11819914 |  | On Schedule < 4 |  |  |  |  | Rebuild 19.88 miles of 115 kV transmission line from Cox Interchange to Hale Co Interchange. | 115 |  | 19.7
200457 | 31176 | 51819 | SPS | TX | Sub - Hockley County Interchange 115 kV Terminal Upgrades | Hockley County Interchange 115 kV Terminal Upgrades | Regional Reliability | TS | 2019-11-15 | 2021-06-01 | 2017-05-15 | SPP-2016-AG1-AFS-3 | 228066 | 2017 | 239611.8412 | 197304 |  | Complete |  |  |  |  | Replace wave trap at Hockley County Interchange to increase the line capacity for Hockley County Interchange - Lamb County Interchange 115 kV Ckt 1. | 115
200444 | 41189 | 61836 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Martin - Pantex North 115 kV Terminal Upgrades | Economic | ITP | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 332501.8 | 0 |  | Complete | 523928 | Martin Sub 115 kV | 523938 | Pantex North Sub 115 kV | Upgrade any necessary terminal equipment at Martin and/or Pantex North to increase the rating of the 115 kV line between the two substations. | 115
200444 | 41189 | 61837 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Pantex South - Highland Tap 115 kV Terminal Upgrades | Economic | ITP | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 332501.8 | 0 |  | Complete | 523945 | Pantex South Sub 115 kV | 523931 | Highland Park Tap 115 kV | Upgrade any necessary terminal equipment at Pantex South and/or Highland Tap to increase the rating of the 115 kV line between the two substations. | 115
200455 | 41192 | 61840 | SPS | TX | Sub - Coulter 115 kV | Coulter 115 kV Terminal Upgrades | Regional Reliability | ITP | 2020-05-15 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 286869 | 2017 | 308926.5353 | 276046 |  | Delay - Mitigation | 524306 | Coulter Interchange 115 kV |  |  | Install terminal upgrades on the 115 kV circuit W71 (Coulter - Puckett) at Coulter Substation. | 115
200455 | 41194 | 61844 | SPS | TX | Sub - Plant X - Sundown 230 kV | Plant X 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 217734 | 2017 | 223177.35 | 0 |  | Delay - Mitigation | 525481 | Plant X Station 230 kV |  |  | Install terminal upgradeson the 230 kV circuit K46 (Plant X - Sundown) at Plant X. | 230
200455 | 41194 | 61845 | SPS | TX | Sub - Plant X - Sundown 230 kV | Sundown 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 360540 | 2017 | 369553.5 | 360540 |  | Delay - Mitigation | 526435 | Sundown Interchange 230 kV |  |  | Install terminal upgrades on the 230 kV circuit K46 (Plant X - Sundown) at Sundown. | 230
210496 | 41197 | 61850 | SPS | TX | Terry County - LG Clauene 115 kV Terminal Upgrades | Terry County - LG Clauene 115 kV Terminal Upgrades | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 888216 | 2018 | 910421.4 | 366704 |  | Complete | 526491 | Lyntegar REC-Clauene 115 kV |  |  | Replace terminal equipment on the Clauene-Terry (circuit V55) line and address any line clearance concerns to meet or exceed the line's conductor rating. | 115
200455 | 41198 | 61852 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 98639 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
200455 | 41198 | 61853 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 108430 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
200476 | 41200 | 61856 | WAPA | ND | Sub - Williston 115 kV | Williston 115 kV Terminal Upgrades | Regional Reliability | ITP | 2017-11-20 | 2018-06-01 | 2018-02-21 | 2017 ITPNT | 5000 | 2017 | 5000 | 5000 | 403.24 | Complete | 652421 | WILISTON |  |  | Install 115 kV terminal upgrades needed at Williston to increase the rating of the Williston - Judson line. | 115
200446 | 41202 | 61858 | AEP | OK | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | ITP | 2019-12-20 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381.13 | 2017 | 6318859.1747 | 7238795 |  | Complete | 509811 | TULSA SOUTHEAST 138KV | 509831 | EAST 61st STREET | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8
200448 | 41209 | 61869 | EDE | MO | Line - Line – Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Nichols – Republic North 69 kV Reconductor | Regional Reliability | ITP | 2018-04-13 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 4050000 | 2017 | 4151250 | 4050000 | 5263657.23 | Complete | 547542 | SUB 170 - NICHOLS ST. | 547576 | SUB 345 - REPUBLIC NORTHEAST | Reconductor 9.7-mile 69 line from Nichols to Republic North. | 69 |  | 10
200448 | 41209 | 61870 | EDE | MO | Line - Line – Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Republic Hines Street - Republic North 69 kV Reconductor | Regional Reliability | ITP | 2018-04-13 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 1450000 | 2017 | 1486250 | 1450000 | 3868242.24 | Complete | 547443 | SUB 451 - REPUBLIC HINES STREET | 547576 | SUB 345 - REPUBLIC NORTHEAST | Reconductor 3.9-mile 69 kV line from Republic Hines Street to Republic North. | 69 |  | 3.5
200448 | 41209 | 61871 | EDE | MO | Line - Line – Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Republic East - Republic Hines Street 69 kV Reconductor | Regional Reliability | ITP | 2018-04-13 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 800000 | 2017 | 820000 | 800000 | 3278100.02 | Complete | 547443 | SUB 451 - REPUBLIC HINES STREET | 547580 | SUB 359 - REPUBLIC EAST | Reconductor 1.3-mile 69 kV line from Republic East to Republic Hines Street. | 69 |  | 1.6
200452 | 51236 | 71926 | WAPA | SD | Multi - Roberts County - Sisseton 69kV | Roberts County 115 kV Substation | Regional Reliability | ITP | 2019-01-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 4300000 | 2017 | 4517687.5 | 3957000 |  | Complete | 655454 |  |  |  | Build new 115 kV substation at Roberts County between the Forman and Summit substations. | 115
200452 | 51236 | 71927 | WAPA | SD | Multi - Roberts County - Sisseton 69kV | XFR - Roberts County 115/69 kV Transformer | Regional Reliability | ITP | 2019-09-30 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 1200000 | 2017 | 1260750 | 1200000 |  | Complete | 655361 |  | 655454 |  | New 115/69 kV transformer at Roberts County. Install necessary 69 kV terminal equipment at Roberts County substation. | 115
| 51239 | 71933 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 4700000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
| 51239 | 71934 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generator Interconnection | GI | 2020-11-01 |  |  | GI STUDIES |  |  | 0 | 5900000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
| 51241 | 71939 | SEPC | KS | Sub - Johnson Corner 115kV - GEN-2015-021 Addition | Johnson Corner 115kV - GEN-2015-021 Addition (TOIF) | Generator Interconnection | GI | 2020-04-07 |  |  | GI STUDIES |  |  | 0 | 894061 |  | Complete | 531424 | JOHNSON CORNER 115 |  |  | 115 kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, one (1) 2000A circuit breaker, communications, control panel replacement, disconnect switches, revenue metering, and line arrestor, substation bus, and associated equipment. |  | 0.05
| 30781 | 71940 | NPPD | NE | Sub - Rosemont 115kV Substation GEN-2008-123N Addition | Rosemont 115kV Substation GEN-2008-123N Addition (TOIF) | Generator Interconnection | GI | 2017-11-01 |  |  | GI STUDIES |  |  | 0 | 1880000 |  | On Schedule < 4 |  |  |  |  | Rosemont 115 kV substation addition on the Pauline – Guide Rock 115 kV line to accommodate new 115 kV interconnection - Add 115kV dead-end tower, arresters, line equipment, metering, and associated equipment to terminate the 115kV line to the generating facility.; One (1) 115 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's new 115 kV Rosemont Substation.
| 51242 | 71941 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (TOIF) | Generator Interconnection | GI | 2020-09-15 |  |  | GI STUDIES |  |  | 0 | 216180 | 227363 | Complete |  |  |  |  | Add a single 115kV line termination, dead end structure, one (1) 115kV disconnect switch with ground blades, and line relaying. No additional Right-of-Way is included in this cost.
| 51242 | 71942 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (SANU) | Generator Interconnection | GI | 2020-09-15 |  |  | GI STUDIES |  |  | 0 | 7109676 |  | Complete |  |  |  |  | Construct new 115 kV switchyard in a three breaker ring bus configuration. Construction to include the addition of three (3) 115 kV power circuit breakers, four (4) 115 kV disconnect switches, two (2) 115 kV disconnect switches with ground blades, instrument transformers, associated control and protection equipment, control building, high voltage bus, transmission line take-off structures, and conductor.
| 51242 | 71943 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (NU) | Generator Interconnection | GI | 2020-11-16 |  |  | GI STUDIES |  |  | 0 | 8529876 |  | Complete |  |  |  |  | Maurine-Newell-Elk Creek-Rapid City 115 kV Transmission Lines - Replace thirty-five (35) 115 kV transmission structures.; Newell Substation - Replacement of the 115 kV strain bus, circuit switchers, and jumpers.; Elk Creek Substation - Replacement of the 115 kV strain bus, jumpers. Reset relays.; Rapid City Substation - Replacement of the main and transfer 115 kV buses, transfer bay, and transmission line bay (to Dry Creek).
200455 | 51246 | 71949 | SPS | TX | Sub - Nichols - 230 kV | Nichols 230 kV Terminal Upgrades | Regional Reliability | ITP | 2020-05-15 | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 490000 | 2017 | 527676.4038 | 90827 |  | Delay - Mitigation Window | 524044 | Nichols Station 230 kV | 524415 | Amarillo South Interchange 230 kV | Install terminal upgrades on the Nichols - Amarillo 230 kV circuit at Nichols. | 230
| 51247 | 71951 | OGE | OK | Sub - Cleo Corner 138kV GEN-2015-048 Addition | Cleo Corner 138kV GEN-2015-048 Addition (TOIF) | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 410000 |  | Re-evaluation |  |  |  |  | Transmission Owner’s Cleo Corner 138kV Substation: Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51247 | 71952 | OGE | OK | Sub - Cleo Corner 138kV GEN-2015-048 Addition | Cleo Corner 138kV GEN-2015-048 Addition (NU) | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 2558000 |  | Re-evaluation |  |  |  |  | Transmission Owner’s Cleo Corner 138kV Substation: Construct four (4) 2000 continuous ampacity breakers, control panel replacement, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Reroute transmission line to the south to open up the north terminal.
| 51248 | 71953 | OGE | OK | Line - Cleo Corner – Cleo Plant Tap 138kV Ckt 1 | Cleo Corner - Cleo Plant Tap 138kV Ckt 1 | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 61890 |  | Re-evaluation |  |  |  |  | Cleo Corner – Cleo Plant Tap 138kV Circuit #1: Change current transformers tap setting and testing.
200479 | 51249 | 71954 | KPP | KS | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | TS | 2020-12-30 | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5293123 |  | On Schedule < 4 |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
200466 | 51249 | 71955 | WR | KS | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8433590.2775 | 5742060 |  | On Schedule < 4 |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1
200466 | 51252 | 71958 | WR | KS | XFR - Creswell 138/69/13.2 kV Transformers | Creswell (CRSW TX-1) 138/69/13.2 kV Transformer Ckt 1 | Regional Reliability | TS | 2020-12-31 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 3486230 | 2017 | 3754288.3862 | 2752325 |  | On Schedule < 4 |  |  |  |  | Upgrade Creswell (CRSW TX-1) 138/69/13.2 kV transformer to 150/165 MVA. | 138/69
200466 | 51252 | 71959 | WR | KS | XFR - Creswell 138/69/13.2 kV Transformers | Creswell (CRSW TX-2) 138/69/13.2 kV Transformer Ckt 2 | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 3621491 | 2017 | 3899949.6883 | 2735801 |  | On Schedule < 4 |  |  |  |  | Upgrade Creswell (CRSW TX-2) 138/69/13.2 kV transformer to 150/165 MVA. | 138/69
210536 | 41199 | 71960 | SPS | TX | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | ITP | 2021-12-15 | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9732832.9652 | 1177301 |  | Delay - Mitigation | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 13335465.455 | 12692888 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5441877.1356 | 5179657 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5441877.1356 | 5179657 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
200477 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 11841839.1706 | 11271233 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
200477 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1337977.2412 | 1273506 |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 3890743.8413 | 3703266 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
200470 | 51260 | 71976 | CBPC | IA | Device - Prestage Family 69 kV Cap Bank | Prestage Family 69 kV Cap Bank | Regional Reliability | TS | 2018-09-01 | 2018-08-01 | 2018-01-19 | DPA-2017-March-735 | 1017500 | 2018 | 1017500 | 1017500 | 1091821.22 | Complete |  |  |  |  | Add two new 9.6 MVAR capacitor banks (19.2 MVAR total) at the new Prestage Family 69 kV station | 69 | 1.5
| 51261 | 71982 | NPPD | NE | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generator Interconnection | GI | 2019-11-01 |  |  | GI STUDIES |  |  | 0 | 1700000 |  | Re-evaluation |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115
| 51261 | 71983 | NPPD | NE | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generator Interconnection | GI | 2019-11-01 |  |  | GI STUDIES |  |  | 0 | 900000 |  | Re-evaluation | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115
| 51262 | 71984 | NPPD | NE | Sub - Tobias 345kV Substation GEN-2015-088 Addition | Tobias 345kV Substation GEN-2015-088 Addition (TOIF) | Generator Interconnection | GI | 2019-01-01 |  |  | GI STUDIES |  |  | 0 | 700000 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s Tobias 345kV Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, protection, controls, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; 345kV Transmission Line: One (1) approximately two-and-a-half (2.5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Tobias 345 kV substation. | 345/345
| 51262 | 71985 | NPPD | NE | Sub - Tobias 345kV Substation GEN-2015-088 Addition | Tobias 345kV Substation GEN-2015-088 Addition (NU) | Generator Interconnection | GI | 2019-01-01 |  |  | GI STUDIES |  |  | 0 | 11700000 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s Tobias 345kV Substation: Construct new substation and three (3) line terminals, five (5) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 345/345
200483 | 51277 | 72004 | OPPD | NE | Line - S1255 - S1260 161 kV | S1255 - S1260 161 kV Ckt 1 New Line | Regional Reliability | TS | 2020-01-27 | 2020-01-01 | 2018-02-27 | DPA-2017-May-746 | 14770262 | 2018 | 15518006.5137 | 9435262 |  | Complete | 646255 | Sub 1255 | 646260 |  | Build new 5.3-mile 161 kV line from S1255 to S1260. | 161 | 5.9
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | SP | 2023-01-31 | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 94556.25 | 90000 |  | On Schedule < 4 | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
200482 | 51280 | 72011 | WFEC | OK | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | TS | 2023-09-01 | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 525312.5 | 500000 |  | Delay - Mitigation | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
200482 | 51281 | 72012 | WFEC | OK | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | TS | 2023-08-01 | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1050625 | 1000000 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
210483 | 51282 | 72013 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | TS | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2000000 | 2000000 |  | Complete |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
210483 | 51282 | 72014 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | TS | 2019-07-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | Delay - Mitigation | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
210483 | 51282 | 72015 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-05-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8352468.75 | 7950000 |  | Delay - Mitigation | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
210483 | 51282 | 72016 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-08-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 6750000 | 2018 | 7091718.75 | 7520000 |  | Delay - Mitigation | 521016 | OKEENE | 521090 | WATONGA SW | Convert 13.5 mile 69 kV line from Okeene - Watonga SW to 138 kV. | 138 |  | 13.5 | 13.5
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2022-08-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 8825250 | 8400000 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2022-09-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1313281.25 | 1250000 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2023-12-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 4780343.75 | 4550000 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | TS | 2022-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4202500 | 4000000 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2023-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 5936031.25 | 5650000 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2022-06-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4202500 | 3500000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2022-05-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4202500 | 11750000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
210483 | 51282 | 72025 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2022-05-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11189156.25 | 1162000 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
210483 | 51282 | 72026 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-12-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1103156.25 | 5000000 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2024-01-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5253125 | 5300000 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
210483 | 51282 | 72029 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW - Park Community 138 kV Ckt 1 New Line | Regional Reliability | TS | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4500000 | 2018 | 4500000 | 4500000 | 5762250.69 | Complete |  |  |  |  | Construct new 9.0 mile 138 kV line from Kingfisher SW - Park Community. | 138 | 9
210483 | 51282 | 72030 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | TS | 2022-06-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4202500 | 4000000 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | TS | 2022-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4465156.25 | 4250000 |  | Delay - Mitigation Window | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 51283 | 72032 | WR | KS | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generator Interconnection | GI | 2021-12-01 |  |  | GI STUDIES |  |  | 0 | 841431 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51283 | 72033 | WR | KS | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generator Interconnection | GI | 2021-12-01 |  |  | GI STUDIES |  |  | 0 | 13362472 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
| 51283 | 72034 | OGE | OK | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generator Interconnection | GI | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 20000 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
210493 | 51285 | 72037 | CUS | MO | Multi - Brookline 345kV | Brookline 345kV Reactor | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3471864 | 2018 | 3558660.6 | 3471864 |  | Complete | 549984 | Brookline 345 |  |  | Install new 50 MVAR reactor at Brookline 345kV. | 345
210493 | 51285 | 72038 | CUS | MO | Multi - Brookline 345kV | Brookline 345kV Substation Expansion | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 794411 | 2018 | 814271.275 | 794411 |  | Complete | 549984 | Brookline 345 |  |  | Brookline 345kV Substation expansion to accommodate new 50MVAR reactor. | 345
210492 | 51295 | 72050 | BEPC | MT | Line - Lewis - Richland 115kV Ckt 1 | Lewis - Richland 115kV Ckt 1 (BEPC) | Regional Reliability | ITP | 2019-06-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 5000 | 2018 | 5125 | 19107.25 |  | Delay - Mitigation Window | 652451 | RICHLAND | 661056 | Lewis & Clark | Adjust CT taps on Lewis to Richland to 1200/5. | 115
210497 | 51295 | 72052 | WAPA | MT | Line - Lewis - Richland 115kV Ckt 1 | Lewis - Richland 115kV Ckt 1 (WAPA) | Regional Reliability | ITP | 2020-11-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 100000 | 2019 | 102500 | 136000 |  | Delay - Mitigation Window | 652451 | RICHLAND | 661056 | Lewis & Clark | Reconductor 0.1 miles of 115 kV line from Lewis to Richland and replace structures as needed. | 115 |  | 0.1
210491 | 51300 | 72066 | AEP | AR | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | ITP | 2019-04-11 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3357600 | 2018 | 3441540 | 3357600 |  | Complete | 504185 | Figure Five | 504032 | VBI NORTH | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI. | 69
210498 | 51305 | 72076 | WR | KS | XFR - Lawrence Hill 230/115kV | Lawrence Hill 230/115kV Transformer | Regional Reliability | ITP | 2020-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 5781164 | 2018 | 6073835.4275 | 5781164 |  | Delay - Mitigation | 532853 | LAWRENCE HILL 230 KV | 533250 | LAWRENCE HILL 115 KV | Replace the 230/115 kV transformer at Lawrence Hill. | 230
210496 | 51316 | 72095 | SPS | TX | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | ITP | 2022-03-11 | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 244745.195 | 674000 |  | On Schedule < 4 | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2024-03-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 10506250 | 10000000 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2024-02-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7249312.5 | 6900000 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
210489 | 51327 | 82113 | WFEC | OK | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-08-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 7984750 | 7600000 |  | Delay - Mitigation |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
210489 | 51327 | 82114 | WFEC | OK | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-04-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 315187.5 | 300000 |  | Delay - Mitigation | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2024-02-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6618937.5 | 6300000 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 51328 | 82116 | WR | KS | Sub - Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection | Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection (TOIF) | Generator Interconnection | GI | 2019-11-05 |  |  | GI STUDIES |  |  | 0 | 1208638 | 1208638 | Complete | 532768 | EMPORIA ENERGY CENTER |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; Allowance for Funds Used During Construction (AFUDC)
| 51328 | 82117 | WR | KS | Sub - Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection | Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection (NU) | Generator Interconnection | GI | 2019-11-05 |  |  | GI STUDIES |  |  | 0 | 1105091 | 1105091 | Complete | 532768 | EMPORIA ENERGY CENTER |  |  | Construct One (1) 345 kV 3000 continuous ampacity breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. The following are included in this cost estimate: Allowance for Funds Used During Construction (AFUDC)
210499 | 51331 | 82125 | GHP | MO | Line - Nixa Downtown - Nixa Espy | Nixa Downtown - Nixa Espy 69 kV Ckt1 | Regional Reliability | ITP | 2019-11-22 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 1402000 | 2018 | 1437050 | 3373306 |  | Complete |  |  |  |  | Reconductor 1.25 miles of 69 kV line from Nixa Downtown - Nixa Espy | 69
| 51332 | 82126 | OGE | OK | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generator Interconnection | GI | 2021-05-15 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51332 | 82127 | OGE | OK | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generator Interconnection | GI | 2021-05-15 |  |  | GI STUDIES |  |  | 0 | 1025042 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
| 51333 | 82128 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generator Interconnection | GI | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51333 | 82129 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generator Interconnection | GI | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 9213042 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 51335 | 82132 | NPPD | NE | Sub - Belden 115 kV Substation GEN-2015-076 Interconnection | Belden 115 kV Substation GEN-2015-076 Interconnection (TOIF) | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 300000 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s Belden Substation: Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51335 | 82133 | NPPD | NE | Sub - Belden 115 kV Substation GEN-2015-076 Interconnection | Belden 115 kV Substation GEN-2015-076 Interconnection (NU) | Generator Interconnection | GI | 2020-10-01 |  |  | GI STUDIES |  |  | 0 | 2900000 |  | On Schedule < 4 |  |  |  |  | Transmission Owner’s Belden 115 kV Substation: Construct two (2) 2000 continuous ampacity breakers, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 51338 | 82134 | WAPA |  | Line - Gavins Point - Yankton Junction 115 kV | Gavins Point - Yankton Junction 115 kV | Generator Interconnection | GI | 2021-01-01 |  |  | GI STUDIES |  |  | 0 | 1401596 |  | On Schedule < 4 |  |  |  |  | Western Area Power Administration (“WAPA”)/NorthWestern Energy Gavins Point – Yankton Junction 115 kV1: Rebuild approximately four (4) miles of 115 kV and replace associated terminal equipment.
| 51337 | 82137 | AEP |  | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generator Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  | 0 | 700000 |  | Complete |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
| 51337 | 82138 | AEP |  | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generator Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  | 0 | 8700000 |  | Complete |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
210512 | 51339 | 82139 | OGE | OK | Line - Kildare - White Eagle 138 kV | Kildare - White Eagle 138 kV Ckt 1 Rebuild | Sponsored Upgrade | SP | 2019-10-29 | 2019-06-01 | 2019-04-03 | SUS-004 | 7200000 | 2019 | 7200000 | 7200000 |  | Complete | 514760 | KILDARE4 138 | 514761 | WHITE EAGLE 138 | Rebuild 11.2 mile 138 kV line from Kildare - White Eagle and upgrade terminal equipment. | 138 |  | 11.22
210496 | 61346 | 92151 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | ITP | 2022-04-16 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 9069324 | 2018 | 9528458.5275 | 13626695 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
210496 | 61346 | 92152 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | ITP | 2022-04-16 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 5226730 | 2018 | 5491333.2062 | 6531679 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
210507 | 61347 | 92153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | TS | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 30675951.95 | 28009136 |  | Delay - Mitigation |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
210507 | 61347 | 92154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | TS | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 31259400.4 | 30000956 |  | On Schedule < 4 |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
210507 | 61347 | 102153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | TS | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6360140.375 | 7010444 |  | Delay - Mitigation |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | TS | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6275094.075 | 7072858 |  | On Schedule < 4 |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
210507 | 71347 | 102156 | SPS | NM | Line - Eddy County - Kiowa 345 kV New Line | Eddy County - Kiowa 345 kV Ckt 1 New Line | Regional Reliability | TS | 2020-11-03 | 2024-06-01 | 2018-12-11 | DPA-2017-November-808 | 63730259 | 2019 | 65323515.475 | 60461535 |  | Complete | 527802 | Eddy County Interchange 345 kV | 527965 |  | Build new 34 mile 345 kV line from Eddy County to Kiowa. | 345 | 34
210507 | 61347 | 102157 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | TS | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5282413.35 | 3398975 |  | Delay - Mitigation |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
210507 | 61347 | 102158 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | TS | 2020-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 14996159 |  | Delay - Mitigation |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
210548 | 71348 | 102159 | OPPD | NE | Multi - S1361 | S3761 345 kV Substation | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 4610067 | 2018 | 4843451.6419 | 4610067 |  | On Schedule < 4 |  |  |  |  | Build a new 345 kV Substation at S3761 | 345/161
210548 | 71348 | 102160 | OPPD | NE | Multi - S1361 | S3761 - S3455 345 kV New Line | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 17036209 | 2019 | 17462114.225 | 17036209 |  | On Schedule < 4 |  |  | 645455 | Sub 3455 | Build a new 4.5 mile S3761 - S3455 345 kV Line | 345 | 5.6
210548 | 71348 | 102161 | OPPD | NE | Multi - S1361 | S1361 161 kV Substation and 345/161 kV Transformer | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 9707827 | 2019 | 9950522.675 | 9707827 |  | On Schedule < 4 |  |  |  |  | Build a new S1361 161 kV Substation with new 345/161 kV transformer | 161
210548 | 71348 | 102162 | OPPD | NE | Multi - S1361 | S1260 161/69 kV Transformer (161 kV) | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 1105064 | 2019 | 1132690.6 | 1105064 |  | On Schedule < 4 | 646260 |  |  |  | 161 kV bus work associated with new S1260 161/69 kV Transformer | 161/69
210548 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3738657.775 | 3647471 |  | On Schedule < 4 | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
210548 | 71348 | 102165 | OPPD | NE | Multi - S1361 | S1259 - S1260 161 kV Rebuild | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 2107486 | 2019 | 2160173.15 | 2107486 |  | On Schedule < 4 | 646260 |  | 646259 | Sub 1259 | Rebuild 2.6 miles of S1259 - S1260 161 kV | 161 | 2.56
210548 | 71348 | 102166 | OPPD | NE | Multi - S1361 | S1255 161 kV Terminal Upgrades (new breakers) | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 654180 | 2019 | 670534.5 | 654180 |  | On Schedule < 4 | 646255 | Sub 1255 |  |  | Upgrade breakers at S1255 | 161
| 71350 | 102168 | OGE | OK | SUB - Ranch Road 345kV Substation GEN-2015-034 Addition | Ranch Road 345kV Substation GEN-2015-034 Addition (TOIF) | Generator Interconnection | GI | 2020-06-16 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | Complete |  |  |  |  | Transmission Owner’s Ranch Road 345kV Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 71350 | 102169 | OGE | OK | SUB - Ranch Road 345kV Substation GEN-2015-034 Addition | Ranch Road 345kV Substation GEN-2015-034 Addition (NU) | Generator Interconnection | GI | 2020-06-16 |  |  | GI STUDIES |  |  | 0 | 925042 |  | Complete |  |  |  |  | Transmission Owner’s Ranch Road 345kV Substation: Construct one (1) 3000 continuous ampacity breakers, control panel replacement, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 71351 | 102170 | OGE | OK | SUB - Johnston County 345kV Substation GEN-2015-036 Addition | Johnston County 345kV Substation GEN-2015-036 Addition (TOIF) | Generator Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  | 0 | 892334 |  | Complete |  |  |  |  | Transmission Owner’s Johnston County Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 71351 | 102171 | OGE | OK | SUB - Johnston County 345kV Substation GEN-2015-036 Addition | Johnston County 345kV Substation GEN-2015-036 Addition (NU) | Generator Interconnection | GI | 2020-09-30 |  |  | GI STUDIES |  |  | 0 | 1132666 |  | Complete |  |  |  |  | Transmission Owner’s Johnston County Interconnection Substation: Construct one (1) 345 kV 3000 continuous ampacity breaker, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210505 | 71352 | 102172 | WFEC | OK | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | TS | 2020-12-01 | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 735139.225 | 717209 |  | Delay - Mitigation Window |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
210525 | 81357 | 112180 | OPPD | NE | GEN-2016-115 Interconnection Costs | GEN-2016-115 Interconnection Costs (NU) (OPPD) | Generator Interconnection | GI |  | 2020-06-26 | 2019-11-01 | DISIS-2016-002 |  |  | 0 | 7553 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and costs estimates needed to interconnect the following Interconnection Customer facility, GEN-2016-115 (300.0 MW/Wind), into the Point of Interconnection (POI) at Holt 345kV.
210556 | 81362 | 112187 | OGE | OK | Sub - Henessey 138 kV Ckt 1 | Henessey 138 kV Ckt 1 Terminal Upgrades | Generator Interconnection | GI | 2021-06-01 | 2020-12-31 | 2020-03-17 | DISIS-2016-002 | 142965 | 2020 | 142965 | 142965 |  | On Schedule < 4 | 520882 | DOVER SW | 514774 | HENESSEY 138 | All elements and conductor must have at least an emergency rating of 202 MVA (846 Amps).
210511 | 81423 | 112253 | WFEC | OK | GEN-2016-020 Interconnection Costs | GEN-2016-020 Interconnection Costs (WFEC) | Generator Interconnection | GI | 2019-11-01 |  | 2019-04-03 | DISIS-2016-001 | 10000 | 2019 | 10000 | 10000 |  | On Schedule < 4 |  |  |  |  | GEN-2016-020 Interconnection Costs
| 81467 | 112300 | SEPC | KS | Mingo 345 kV Substation | Mingo 115kV Substation GEN-2015-064 (TOIF) | Generator Interconnection | GI | 2020-01-20 |  |  | GI STUDIES |  |  | 0 | 911033 |  | Complete |  |  |  |  | Transmission Owner’s Mingo 115kV Substation: Construct one (1) 115kV line terminal, line switches, dead end structure, line relaying,communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81467 | 112301 | SEPC | KS | Mingo 345 kV Substation | Mingo 115kV Substation GEN-2015-064 (NU) | Generator Interconnection | GI | 2020-01-20 |  |  | GI STUDIES |  |  | 0 | 4517777 |  | Complete |  |  |  |  | Transmission Owner’s Mingo 345kV Substation: Construct four (4) 115 kV 3000 continuous ampacity breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210548 | 71348 | 112357 | OPPD | NE | Multi - S1361 | S1260 161/69 kV Transformer (69 kV) | Regional Reliability | TS |  | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 1799221 | 2019 | 1844201.525 | 1799221 |  | Complete | 646260 |  |  |  | Add new S1260 161/69 kV Transformer and associated 69 kV bus work | 161/69
210540 | 81498 | 112358 | OGE | OK | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | ITP | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 271289 | 271289 |  | On Schedule < 4 | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
210540 | 81499 | 112359 | OGE | OK | Sub - Santa Fe 138 kV | Santa Fe 138 kV Breakers | Regional Reliability | ITP | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 406935 |  | On Schedule < 4 | 514926 | SANTA FE 138 |  |  | Replace 3 breakers at Santa Fe 138 kV with 40 kA breakers | 138
210544 | 81500 | 112360 | AEP | OK | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | ITP | 2023-05-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 16288000 | 2020 | 16288000 | 33619929 |  | Re-evaluation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 21 breakers at Riverside Station 138 kV with 80 kA breakers | 138 | 1.56
210544 | 81501 | 112361 | AEP | OK | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | ITP | 2023-12-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4421345 | 4194065 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138
210541 | 81502 | 112362 | SPS | NM | Sub - Carlsbad Interchange 115 kV | Carlsbad Interchange 115 kV Breaker | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP | 552668 | 2019 | 566484.7 | 552668 |  | On Schedule < 4 | 528160 | Carlsbad Interchange 115 kV |  |  | Replace 1 breaker at Carlsbad Interchange 115 kV with 40 kA breakers | 115
210541 | 81503 | 112363 | SPS | TX | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability | ITP | 2020-12-18 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1699454.1 | 1658004 |  | On Schedule < 4 | 525454 | Hale Co Interchange 115 kV |  |  | Replace 3 breakers at Hale County Interchange 115 kV with 40 kA breakers | 115
210541 | 81504 | 112364 | SPS | TX | Sub - Denver City Interchange 115 kV North | Denver City Interchange North 115 kV Breaker | Regional Reliability | ITP | 2021-03-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 496400 | 2020 | 496400 | 3316008 |  | On Schedule < 4 | 527130 | Denver City Interchange N. 115 kV |  |  | Replace 1 breaker at Denver City Interchange North 115 kV with 40 kA breaker | 115
210541 | 81586 | 112365 | SPS | TX | Sub - Denver City Interchange South 115 kV | Denver City Interchange South 115 kV Breakers | Regional Reliability | ITP | 2021-03-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 415519 | 2020 | 415519 | 2210672 |  | On Schedule < 4 | 527136 | Denver City Interchange S. 115 kV |  |  | Replace 2 breakers at Denver City Interchange South 115 kV with 40 kA breakers | 115
210538 | 81505 | 112366 | NPPD | NE | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | ITP | 2020-02-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 |  | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115
210538 | 81506 | 112367 | NPPD | NE | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | ITP | 2021-01-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 550000 | 506813 |  | On Schedule < 4 | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115
210538 | 81507 | 112368 | NPPD | NE | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | ITP | 2021-05-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 510000 | 679553 |  | On Schedule < 4 | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
210539 | 81508 | 112369 | KCPL | KS | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | ITP | 2021-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 319185 | 291361 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161
210539 | 81509 | 112370 | KCPL | MO | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | ITP | 2020-09-24 | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 502440 |  | In Service | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161
210539 | 81510 | 112371 | KCPL | MO | Sub - Midtown 161 kV | Midtown 161 kV Breakers | Regional Reliability | ITP | 2019-09-11 | 2021-06-01 | 2019-11-18 | 2019 ITP | 502440 |  | 0 | 363913.81 | 363913.81 | Complete | 542996 | MIDTOWN 161 KV |  |  | Replace 2 breakers at Midtown 161 kV with 40 kA breakers | 161
210539 | 81511 | 112372 | KCPL | MO | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | ITP | 2021-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 921065 | 1004980 |  | Delay - Mitigation | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | ITP | 2027-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 828359 | 838500 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
210545 | 81514 | 112378 | WFEC | OK | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | ITP | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 52400 | 52400 |  | On Schedule < 4 | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
210545 | 81515 | 112379 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | ITP | 2022-05-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 822500 | 2160000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
210545 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | ITP | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 128300 | 204000 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
210542 | 81516 | 112381 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | ITP | 2022-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3067168.2 | 3067168.2 |  | Delay - Mitigation Window | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | Rebuild 4 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 4
210542 | 81516 | 112382 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - Smittyville 115kV Ckt 1 | Regional Reliability | ITP | 2022-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 7327261.5 | 2020 | 7327261.5 | 7327261.5 |  | Delay - Mitigation Window | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Rebuild 7.99 miles of 115 kV line from Baileyville to Smittyville and upgrade any necessary terminal equipment at Baileyville and/or Smittyville to increase the summer emergency rating to 239 MVA | 115 | 8
210542 | 81516 | 112383 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Marshall County - Smittyville 115kV Ckt 1 | Regional Reliability | ITP | 2022-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 2528867.81 | 2020 | 2528867.81 | 2528867.81 |  | Delay - Mitigation Window | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Rebuild 2.17 miles of 115 kV line from Marshall County to Smittyville and upgrade any necessary terminal equipment at Marshall County and/or Smittyville to increase the summer emergency rating to 239 MVA | 115 | 2.2
210544 | 81520 | 112389 | AEP | OK | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 6724236.77 | 6724237 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2
210544 | 81523 | 112393 | AEP | OK | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | ITP | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1307802 | 1307802 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5
210545 | 81525 | 112395 | WFEC | OK | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | ITP | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 400000 | 400000 |  | On Schedule < 4 | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
210540 | 81532 | 112402 | OGE | OK | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP | 2021-12-31 | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 16602 | 16602 |  | On Schedule < 4 | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69/69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | ITP | 2023-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 608900 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115/115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | ITP | 2023-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3600000 | 2991100 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115/115
210541 | 81542 | 112425 | SPS | TX | Sub - Amoco - Sundown 115 kV | Amoco - Sundown 115kV Terminal Upgrades | Economic | ITP | 2020-06-01 | 2023-01-01 | 2019-11-18 | 2019 ITP | 408507 | 2020 | 408507 | 408507 |  | On Schedule < 4 | 526434 | Sundown Interchange 115 kV | 526445 | Amoco Tap 115 kV | Upgrade any necessary terminal equipment at Sundown and/or Amoco Tap to increase the summer emergency rating to 175 MVA | 115/115
210542 | 81545 | 112428 | WR | KS | Sub - Lawrence Energy Center - Midland 115 kV | Lawrence Energy Center - Midland 115 kV Terminal Upgrades | Economic | ITP | 2020-05-22 | 2021-01-01 | 2019-11-18 | 2019 ITP | 30939 | 2020 | 30939 | 30938.59 |  | In Service | 533248 | LAWRENCE ENERGY CENTER UNIT 3 115 KV |  |  | Upgrade any necessary terminal equipment at Lawrence Energy Center and/or Midland to increase the summer emergency rating to 138 MVA | 115/115
210541 | 81548 | 112433 | SPS | TX | Line - Hansford - Spearman 115kV | Hansford - Spearman 115 kV Rebuild | Economic | ITP | 2021-04-15 | 2021-01-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 828359 | 828359 |  | On Schedule < 4 | 523186 | Spearman Interchange 115 kV | 523195 | Hansford County Switch Station 115 kV (POI: JD Wind #4 80MW) | Rebuild 1.2 miles of 115 kV line from Spearman to Hansford and replace structures at Hansford and/or Spearman as needed to increase the summer emergency rating to 233 MVA | 115/115
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | ITP | 2021-01-01 | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1000000 | 1000000 |  | On Schedule < 4 |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138/138
210586 | 81553 | 112443 | WFEC | OK | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 9959290.81 |  | NTC - Commitment Window | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138/138
210540 | 81556 | 112449 | OGE | OK | Multi - Cimarron - Northwest - Mathewson 345kV | Cimarron - Northwest 345kV Ckt 1 Terminal Upgrades | Economic | ITP | 2020-06-17 | 2021-01-01 | 2019-11-18 | 2019 ITP | 166504 | 2020 | 166504 | 166504 |  | Complete | 514880 | NORTHWEST 345 | 514901 | CIMARRON 345 | Upgrade any necessary terminal equipment at Northwest and/or Cimarron to increase the summer emergency rating to 1426 MVA | 345/345
210540 | 81556 | 112450 | OGE | OK | Multi - Cimarron - Northwest - Mathewson 345kV | Northwest - Mathewson 345 kV Terminal Upgrades | Economic | ITP | 2020-06-01 | 2021-01-01 | 2019-11-18 | 2019 ITP | 369869 | 2020 | 369869 | 0 |  | Complete | 514880 | NORTHWEST 345 | 515497 | MATHEWSON 345 | Upgrade any necessary terminal equipment at Northwest and/or Mathewson to increase the summer emergency rating to 1792 MVA | 345/345
210543 | 81557 | 112451 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 462000 |  | NTC - Commitment Window | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115/115
210543 | 81557 | 112452 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 1633500 |  | NTC - Commitment Window | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115/115
210543 | 81557 | 112453 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 1556500 |  | NTC - Commitment Window | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115/115
210570 | 81559 | 112456 | EDE | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | TS |  | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 43153324 | 2020 | 43153324 | 43153324 |  | NTC - Commitment Window | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
210569 | 81559 | 112457 | WR | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (WR) | Transmission Service | TS | 2023-06-01 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 3972869 | 2020 | 3972869 | 3972868.87 |  | NTC - Commitment Window | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 | 2.7
210568 | 81561 | 112458 | TSMO | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | ITP |  | 2026-01-01 | 2020-11-12 | 2019 ITP | 97111851 | 2020 | 97111851 | 97111851 |  | NTC - Commitment Window | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345/345 | 66.2
210544 | 81561 | 112460 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | ITP | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 733520 | 733520 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138/138
210544 | 81571 | 112488 | AEP | OK | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | ITP | 2021-11-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9155167 | 9155167 |  | Delay - Mitigation | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115
210577 | 81497 | 112500 | EREC |  | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (EREC) | Regional Reliability | ITP | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 3277500 |  | NTC - Commitment Window | 660000 | ABERDEEN JCT |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA | 115 | 13.5
210544 | 81561 | 112502 | AEP | NM | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | ITP | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3244826.1 | 5383105 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06
210515 | 81581 | 112510 | SPS | ND | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | TS | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3244826.1 | 0 |  | On Schedule < 4 | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line |  | 3.5
210515 | 81581 | 122510 | SPS | ND | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability | TS | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 3842954.6 | 2850232 |  | On Schedule < 4 | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
210577 | 81497 | 122511 | EREC |  | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 115/69 kV Transformer | Regional Reliability | ITP | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 2022000 |  | NTC - Commitment Window |  |  |  |  | Install new 115/69 kV transformer at Richmond to achieve a summer emergency rating of 63 MVA
210577 | 81497 | 122512 | EREC |  | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 69 kV Capacitor Bank | Regional Reliability | ITP | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 222000 |  | NTC - Commitment Window |  |  |  |  | Install a new 8 MVAR capacitor bank at Richmond 69 kV | 69
210560 | 81614 | 122570 | BEPC | ND | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | TS | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33023153 | 2020 | 33023153 | 33155575 |  | Delay - Mitigation | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
210559 | 81614 | 122571 | MWE | ND | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | TS | 2021-09-05 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19235485 | 19235485 |  | Delay - Mitigation |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
210560 | 81614 | 122572 | BEPC | SD | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability | TS | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 5920939 | 2020 | 5920939 | 3176320 |  | Delay - Mitigation |  |  |  |  | Build new 230/115 kV Transformer at North Shore substation | 230/115
210560 | 81614 | 122575 | BEPC | OK | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability | TS | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 20938350 | 20938350 |  | Delay - Mitigation |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch
210522 | 81616 | 122576 | NWE | SD | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen City - Aberdeen Industrial Park 115 kV Ckt 1 New Line | Sponsored Upgrade | SP | 2019-12-31 | 2019-12-31 | 2019-09-06 | SUS-006 | 3200009 | 2019 | 3200009 | 3200009 |  | On Schedule < 4 |  |  |  |  | Build new 3.29 mile, 115 kV line from Aberdeen City - Aberdeen Industrial Park | 115
210586 | 81617 | 122577 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | ITP | 2021-01-01 | 2021-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2850000 | 2850000 |  | NTC - Commitment Window | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138 kV line from Anadarko to Gracemont as a double circuit and install/upgrade any necessary terminal equipment to increase the summer emergency rating to 353 MVA for each circuit | 138
210527 | 81626 | 122593 | EREC | OK | Multi - Wentworth 69 kV | Wentworth 69 kV Substation | Regional Reliability | TS | 2019-06-01 | 2019-08-01 | 2019-10-17 | DPA-2018-January-821 | 2073095 | 2020 | 2073095 | 2073095 |  | Complete |  |  |  |  | Expand Wentworth 69 kV Substation to accommodate new capacitor bank | 69
210527 | 81626 | 122594 | EREC | SD | Multi - Wentworth 69 kV | Wentworth 69 kV Capacitor Bank | Regional Reliability | TS | 2019-07-01 | 2019-08-01 | 2019-10-17 | DPA-2018-January-821 | 600675 | 2020 | 600675 | 600675 |  | Complete |  |  |  |  | Install new 7.2 MVAR capacitor bank at the Wentworth 69 kV Substation | 69
210545 | 81627 | 122597 | WFEC | KS | SUB - Marietta - Rocky Point 69 kV | Marietta 69 kV | Regional Reliability | ITP | 2021-12-01 | 2021-12-01 | 2019-11-18 | 2019 ITP | 100000 | 2020 | 100000 | 100000 |  | On Schedule < 4 |  |  |  |  | Install any necessary protection equipment at Marietta to change the operational status from normally open to normally closed | 69
| 81547 | 122598 | TBD |  | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | ITP |  | 2026-01-01 |  | 2019 ITP |  |  |  | 142601178 |  | NTC - Commitment Window |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA
210522 | 81616 | 122599 | NWE | KS | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | SP | 2021-12-31 | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 566484.7 | 552668 |  | On Schedule < 4 |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115
210564 | 81489 | 122600 | OGE | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generator Interconnection | GI | 2020-12-31 | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10000 | 10000 |  | NTC - Commitment Window |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-091 (303.6 MW/Wind) into the POI at Gracemont - Lawton East Side 345 kV
210565 | 81481 | 122622 | WR | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generator Interconnection | GI |  |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 139825 | 139824.59 |  | On Schedule < 4 |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
| 81481 | 122623 | WR | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generator Interconnection | GI |  |  |  | GI STUDIES | 10000 | 2020 | 10000 | 10000 |  | On Schedule < 4 |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
210553 | 81367 | 122631 | WAPA |  | Multi - Fort Randall - Spencer 115 kV, Martin - Vetal 115 kV, Eagle Creek 115 kV | Fort Randall - Spencer 115kV Ckt 1 Re-conductor | Regional Reliability | TS |  | 2022-06-01 | 2020-12-09 | DPNS-2019-May-1037 |  |  | 0 | 2650000 |  | NTC - Commitment Window |  |  |  |  | Re-conductor a portion of the of 115 kV line from Fort Randall to Spencer to increase the emergency rating to 240 MVA | 115
210553 | 81367 | 122632 | WAPA |  | Multi - Fort Randall - Spencer 115 kV, Martin - Vetal 115 kV, Eagle Creek 115 kV | Martin - Vetal Tap 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2022-06-01 | 2020-12-09 | DPNS-2019-May-1037 |  |  | 0 | 3800000 |  | NTC - Commitment Window |  |  |  |  | Re-conductor a portion of the 115 kV line from Martin to Vetal Tap to increase the emergency rating to 100 MVA | 115
210554 | 81638 | 122639 | OGE | OK | SUB - Forest Hill 69 kV Terminal Upgrades | Forest Hill 69 kV Terminal Upgrade | Regional Reliability | TS | 2021-01-01 | 2021-01-01 | 2020-03-17 | DPA-2019-January-974 | 43867 | 2020 | 43867 | 25000 |  | On Schedule < 4 | 515074 | FOREST HILL 69 |  |  | Upgrade the current transformer at the Forest Hill 69 kV substation to 1200 amps to increase the rating of the Forest Hill - Tecumseh 69 kV line to 143 MVA.
210551 | 81648 | 122650 | WR | KS | Sub - Neosho 345 kV | Caney River - Neosho 345 kV Terminal Upgrades | Sponsored Upgrade | SP | 2020-06-25 | 2020-10-01 | 2019-12-31 | SUS-013 | 419116 | 2020 | 419116 | 511342.85 |  | Complete | 532793 | NEOSHO 345 KV | 532780 | Caney River | Upgrade terminal equipment, disconnect switches, and line switch to increase the summer normal and emergency ratings to at least 1159 MVA.
210557 | 81652 | 122657 | CBPC | IA | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability | TS |  | 2020-06-01 | 2020-04-08 | DPNS-2019-March-1011 |  |  | 0 | 1227000 |  | NTC - Commitment Window |  |  |  |  | Construct a new switching station at Flint Hills connecting the MEC Clarksville line and Corn Belt's Parkersburg and Plainfield line
210563 | 81656 | 122664 | NPPD | NE | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | SP | 2022-12-01 | 2022-12-01 | 2020-07-14 | SUS-014 |  |  | 0 | 6000000 |  | On Schedule < 4 | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each.
| 81661 | 122675 | WR | KS | GEN-2016-162 and GEN-2016-163 Interconnection Costs | GEN-2016-162 and 163 Interconnection (TOIF) (WERE) | Generator Interconnection | GI |  |  |  | GI STUDIES |  |  | 0 | 1198282 |  | On Schedule < 4 |  |  |  |  | Construct one (1) new 345 kV dead-end, one (1) new 345 kV disconnect switch, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel.
210558 | 81673 | 122713 | AEP | OK | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | TS | 2022-06-01 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 |  |  | 0 | 3160967 |  | Delay - Mitigation | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49
210578 | 81675 | 122717 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 282000 |  | NTC - Commitment Window | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 0/0
210578 | 81675 | 122718 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 423000 |  | NTC - Commitment Window | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
210586 | 81679 | 122722 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | ITP | 2025-12-31 | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1010000 |  | NTC - Commitment Window | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
210574 | 81682 | 122725 | SPS |  | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4732267 |  | NTC - Commitment Window | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
210580 | 81683 | 122726 | WR | KS | Line - Meadowlark - Tower 33 115kV | Meadowlark - Tower 33 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2023-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1342588 |  | NTC - Commitment Window | 533441 | MEADOWLARK 115 KV | 533455 | TOWER 33 115 KV | Rebuild 0.92 miles of 115 kV line from Meadowlark to Tower 33 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 0.94
210574 | 81684 | 122727 | SPS |  | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 6817226 |  | NTC - Commitment Window | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
210575 | 81687 | 122730 | AEP |  | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | ITP |  | 2024-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 23622577 |  | NTC-C Project Estimate Window | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2
210581 | 81768 | 122745 | BEPC |  | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 3389739 |  | NTC - Commitment Window |  |  |  |  | Upgrade an necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 1 to achieve a summer emergency rating of 250 MVA | 230/115
210581 | 81768 | 122746 | BEPC |  | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 173041 |  | NTC - Commitment Window |  |  |  |  | Replace the 230/115 kV transformer Ckt 2 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
210586 | 81617 | 122753 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic | ITP | 2026-09-01 | 2023-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4636432 |  | NTC - Commitment Window | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont as double circuit and add/upgrade any necessary equipment to increase the achieve a summer emergency rating of 353 MVA for each circuit
210589 | 81617 | 122755 | OGE | OK | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic | ITP |  | 2023-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 405535 |  | NTC - Commitment Window | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Install terminal equipment at Gracemont 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA
210586 | 81617 | 122756 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko 138 kV Ckt 2 Terminal Equipment | Economic | ITP |  | 2023-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 405535 |  | NTC - Commitment Window | 520814 | ANADARKO |  |  | Install terminal equipment at Anadarko 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA
210575 | 81717 | 122796 | AEP |  | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 11999273.11 |  | NTC-C Project Estimate Window | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support an in and out tap of the existing Woodward to Border 345 kV line to achieve a summer emergency of 1792 MVA |  | 0.2
210578 | 81675 | 122801 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 282000 |  | NTC - Commitment Window | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA
210578 | 81675 | 122802 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 423000 |  | NTC - Commitment Window | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 345/161
210582 | 81719 | 122803 | SEPC | KS | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-23 | 2020 ITP |  |  | 0 | 2841951 |  | NTC - Commitment Window | 539701 | Russell 115 KV |  |  | Add new 24 MVAR capacitor bank at Russell 115 kV
210583 | 81720 | 122804 | KCPL | KS | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 887479 |  | NTC - Commitment Window |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
210583 | 81721 | 122805 | KCPL | KS | Sub - Stilwell 161 kV | Stilwell 161 kV Breaker | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 566485 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace 1 breaker at the Stilwell 161 kV station with a 63 kA breaker
210583 | 81722 | 122806 | KCPL | KS | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 566485 |  | NTC - Commitment Window | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker
210583 | 81723 | 122807 | KCPL | KS | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 566485 |  | NTC - Commitment Window | 543031 | SHAWNEE MISSION 161 KV |  |  | Replace 1 breaker at the Shawnee Mission 161 kV station with a 40 kA breaker
210583 | 81724 | 122808 | KCPL | KS | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  |  | #N/A |  | NTC - Commitment Window |  |  |  |  | Replace 1 breaker at the Southtown 161 kV station with a 40 kA breaker
210583 | 81725 | 122809 | KCPL | KS | Sub - Lake Road 161 kV | Lake Road 161 kV Breakers | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1132969.56 |  | NTC - Commitment Window | 541255 | Lake Road 161 KV |  |  | Replace 2 breakers at the Lake Road 161 kV station with a 30 kA breakers
210583 | 81726 | 122810 | KCPL | KS | Sub - Craig 161 kV #2 | Craig 161 kV Breakers | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1132970 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Replace 2 breakers at the Craig 161 kV station with a 63 kA breakers
210580 | 81728 | 122812 | WR | KS | Line - Circleville - Goff 115 kV | Circleville - Goff 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2025-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 12114772 |  | NTC - Commitment Window | 533152 | CIRCLEVILLE 115 KV | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | Rebuild 14.56 miles of 115 kV line from Circleville to Goff and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  |  | 14.5
210580 | 81730 | 122814 | WR | KS | Line - Kelly - Goff 115 kV | Goff - Kelly 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2025-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 7108395.3 |  | NTC - Commitment Window | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | 533217 | KELLY 115 KV | Rebuild 10.0 miles of 115 kV line from Goff to Kelly and upgrade any necessary terminal equipment to achieve a summer emergency rating 239 MVA
210589 | 81733 | 122818 | OGE | OK | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2023-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4281150 |  | NTC - Commitment Window | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 4.71
210589 | 81733 | 122819 | OGE | OK | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2023-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1081649 |  | NTC - Commitment Window | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 1.19
210587 | 81717 | 122823 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 11500000 |  | NTC-C Project Estimate Window |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
210587 | 81717 | 122824 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward Border 345 kV Ckt 1 (OGE) | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1259660 |  | NTC-C Project Estimate Window |  |  | 511553 | Elk City 345 kV | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA |  | 0.84
210587 | 81741 | 122848 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  |  | #N/A |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA
210587 | 81741 | 122849 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345 kV Substation | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 25500000 |  | NTC-C Project Estimate Window |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. | 345/138
210587 | 81741 | 122850 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4225000 |  | NTC-C Project Estimate Window |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210587 | 81741 | 122851 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4225000 |  | NTC-C Project Estimate Window |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210587 | 81741 | 122858 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 2288668 |  | NTC-C Project Estimate Window | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
210587 | 81741 | 122863 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 65000 |  | NTC-C Project Estimate Window | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
210586 | 81751 | 122864 | WFEC | OK | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability | ITP |  | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 850000 |  | NTC - Commitment Window | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
210586 | 81679 | 122865 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | ITP | 2022-01-01 | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 202500 |  | NTC - Commitment Window | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
210586 | 81679 | 122866 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | ITP | 2022-01-01 | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 405000 |  | NTC - Commitment Window | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
210574 | 81755 | 122869 | SPS |  | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | ITP | 2022-04-15 | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 923938.47 |  | NTC - Commitment Window | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA. |  | 33
210574 | 81756 | 122870 | SPS |  | Sub - Newhart - Potter 230 kV | Newhart - Potter 230 kV Terminal Upgrades | Regional Reliability | ITP | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 731282.27 |  | NTC - Commitment Window | 525461 | Newhart Interchange 230 kV | 523959 | Potter County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Newhart and/or Potter 230 kV to achieve a summer emergency rating of 540 MVA. |  | 67
210574 | 81757 | 122871 | SPS |  | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | ITP | 2022-04-01 | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 12626190.2 |  | NTC - Commitment Window | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
210574 | 81758 | 122872 | SPS |  | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4746175 |  | NTC - Commitment Window | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
210574 | 81760 | 122876 | SPS |  | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-04-01 | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 6660556.1 |  | NTC - Commitment Window | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
210574 | 81763 | 122883 | SPS |  | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | ITP | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 872390.98 |  | NTC - Commitment Window | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | : Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
210584 | 81497 | 132893 | NWE |  | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | ITP | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1060000 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA
210577 | 81497 | 132894 | EREC |  | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 69 kV Substation | Regional Reliability | ITP | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 4812500 |  | NTC - Commitment Window |  |  |  |  | Expand the existing 69 kV substation to accommodate a new 115/69 kV transformer | 115/69
| 81741 | 133085 | TBD | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic | ITP |  | 2025-01-01 |  | 2020 ITP |  |  | 0 | 57512100 |  | Identified |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating.
| 81741 | 133106 | TBD | Ok | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic | ITP |  | 2025-01-01 |  | 2020 ITP |  |  | 0 | 23400139 |  | Identified |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA
210576 | 91875 | 143156 | AEP |  | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Regional Reliability | ITP |  | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 688788.07 |  | NTC - Commitment Window |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV
210579 | 91876 | 143157 | WAPA |  | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-23 | 2020 ITP |  |  | 0 | 2380700 |  | NTC - Commitment Window |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
210585 | 91878 | 143159 | MRES |  | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1515440 |  | NTC - Commitment Window |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
210579 | 91880 | 143161 | WAPA |  | Device - Devil's Lake 115 kV | Devil's Lake 115 kV Reactor | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-23 | 2020 ITP |  |  |  | 1190000 |  | NTC - Commitment Window |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
210591 | 91881 | 143162 | CPEC |  | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-23 | 2020 ITP |  |  |  | #N/A |  | NTC - Commitment Window |  |  |  |  | Install 2x6 MVAR reactors at Agate to control voltage on the 115 kV transmission system
210574 | 91884 | 143167 | SPS |  | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 817466 |  | NTC - Commitment Window |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.15
210574 | 91888 | 143168 | SPS |  | Line - Cargill - Deaf Smith #24 115 kV | Cargill - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 5501901 |  | NTC - Commitment Window |  |  |  |  | Rebuild 7.74 miles of 115 kV line from Cargill to Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210574 | 91889 | 143169 | SPS |  | Line - Parmer - Deaf Smith #24 115 kV | Parmer - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 824574 |  | NTC - Commitment Window |  |  |  |  | Rebuild 1.16 miles of 115 kV line from Parmer - Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 1.16
210574 | 91890 | 143170 | SPS |  | Line - Parmer - Deaf Smith #20 115 kV | Parmer - Deaf Smith #20 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2022-04-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 5402384 |  | NTC - Commitment Window |  |  |  |  | Rebuild 7.6 miles of 115 kV line from Parmer - Deaf Smith #20 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 7.6
210587 | 81741 | 143176 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | ITP |  | 2025-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 2288668 |  | NTC-C Project Estimate Window |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
210584 | 81497 | 143181 | NWE |  | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability | ITP |  | 2022-12-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 3277500 |  | NTC - Commitment Window |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
210575 | 81717 | 143182 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward Border 345 kV Ckt 1 (AEP) | Economic | ITP |  | 2022-01-01 | 2020-11-17 | 2020 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window |  |  |  |  | Build 0.84 miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm to achieve a summer emergency rating of 1792 MVA