## QPT Appendix 1
Quarter 1 2023 Project Tracking Appendix 1
COMPLETE |  |  |  | Complete and in-service
CLOSED OUT |  |  |  | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project; asterisk (*) indicates interim mitigation plan provided by SPP
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
REEVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
RFP RESPONSE WINDOW |  |  |  | RFP Issued
SUSPENDED |  |  |  | NTC/GIA suspended
NTC_ID | PID | UID | ProjectOwner | State(s) | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200397 | 242 | 10308 | WFEC | OK | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-03-31 | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3757406.6808 | 4339358 | 4171494.22 | Delay - Mitigation | 69 |  | 10.8
200397 | 844 | 11113 | WFEC | OK | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | 2023-12-01 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5479551.4095 | 4725000 | 643783.96 | Delay - Mitigation | 69 |  | 10
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 214576055.8119 | 204236579 |  | Delay - Mitigation | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 14385872.9756 | 13692681 |  | Delay - Mitigation | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 244694447.7113 | 232903698 |  | Delay - Mitigation | 345 | 124.3
210618 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2025-12-31 | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 591425 | 577000 |  | Delay - Mitigation | 345
| 30401 | 50492 | TBD | NE | Cass Co. - S.W. Omaha (aka S3454) 345 kV | Cass Co. - S.W. Omaha (aka S3454) 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 33126800 |  | Identified | 345
200200 | 30491 | 50600 | WFEC | OK | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | 2017-03-01 | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  | Complete | 69
200234 | 30503 | 50628 | WFEC | OK | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | 2017-03-01 | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  | Re-evaluation | 69
200245 | 30563 | 50702 | WFEC | OK | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  | Re-evaluation | 138
| 30599 | 50769 | AEP | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | South Fayetteville 345/161 kV Transformer Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 345/161
| 30599 | 50770 | TBD | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | Chamber Springs - South Fayetteville 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 21295800 |  | Identified | 345 | 18
| 30600 | 50771 | EMW | MO | XFR - Maryville 345/161 kV | Maryville 345/161 kV Transformer Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 345/161
| 30601 | 50772 | EM | KS | XFR - Nashua 345/161 kV | Nashua 345/161 kV Transformer Upgrade Ckt11 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 345/161
| 30602 | 50773 | TBD | NE | Line - Keystone - Red Willow 345 kV | Keystone - Red Willow 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 130141000 |  | Identified | 345 | 110
| 30603 | 50774 | TBD | TX | Line - Tolk - Tuco 345 kV | Tolk - Tuco 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 75718400 |  | Identified | 345 | 64
| 30604 | 50775 | SEPC | KS | XFR - 2nd Holcomb 345/115 kV | Holcomb 345/115 kV Transformer Ckt2 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 345/115
| 30605 | 50776 | TBD | KS | Line - Neosho - Wolf Creek 345 kV | Neosho - Wolf Creek 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 117126900 |  | Identified | 345 | 86.4
| 30606 | 50777 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | Clinton - Truman 161 kV Ckt1 Reconductor | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 15701325 |  | Identified | 161 |  | 29
| 30606 | 50778 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | North Warsaw - Truman 161 kV Ckt1 Reconductor | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 1082850 |  | Identified | 161 |  | 2
| 30608 | 50779 | EKC | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn 345/115 kV Transformer Ckt2 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 12600000 |  | Identified | 345/115
| 30608 | 50780 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Swissvale 345 kV Ckt1 Voltage Conversion | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 20112700 |  | Identified | 345 |  |  | 17
| 30608 | 50781 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Jeffrey EC 345 kV Ckt1 Voltage Conversion | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 35493000 |  | Identified | 345 |  |  | 30
| 30607 | 50782 | OGE | OK | Sub - Muskogee/Pecan Creek 345 kV | Muskogee/Pecan Creek 345 kV Terminal Upgrades | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  | 0 | 34605675 |  | Identified
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2025-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11338457.3874 | 9797157 |  | Delay - Mitigation | 345/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2025-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1134089.4193 | 913714 |  | Delay - Mitigation | 345
| 30959 | 51338 | EKC | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection | 2021-07-08 |  |  | GI STUDIES |  |  | 0 | 2098946 |  | In Service
| 30959 | 51360 | EKC | KS//KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | 2021-07-28 |  |  | GI STUDIES |  |  | 0 | 1674997 |  | In Service
200397 | 31002 | 51445 | WFEC | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | 2022-01-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6958160.52 | 7710000 |  | Delay - Mitigation | 138
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2025-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4638773.68 | 4500000 |  | Delay - Mitigation | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2627865.2897 | 2266000 |  | Re-evaluation | 161
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2023-05-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 637831.381 | 600000 |  | Delay - Mitigation | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2023-05-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3479080.26 | 3600000 |  | Delay - Mitigation | 138/69
200419 | 31042 | 51531 | WFEC | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | 2026-12-31 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1583971.494 | 5700000 |  | Delay - Mitigation | 138 | 2
200386 | 31057 | 51559 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146463.7 | 2016 | 17565254.2892 | 15595092.29 | 9226024 | Closed Out | 69
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20716215 |  | Delay - Mitigation | 69
200420 | 31063 | 51567 | SPS | NM | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | 2021-06-01 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | Complete | 115 |  | 0.03
200433 | 31144 | 51764 | WFEC | OK | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | 2023-10-31 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 113140.821 | 410000 |  | Delay - Mitigation | 138
200455 | 41198 | 61852 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 0 |  | Delay - Mitigation | 115
200455 | 41198 | 61853 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 0 |  | Delay - Mitigation | 115
| 51239 | 71933 | NPPD | NE/ | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2024-04-01 |  |  | GI STUDIES |  |  | 0 | 4700000 |  | On Schedule < 4
| 51239 | 71934 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2024-04-01 |  |  | GI STUDIES |  |  | 0 | 5900000 |  | On Schedule < 4 | 345
200479 | 51249 | 71954 | KPP | KS | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | 2020-12-31 | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | Complete |  |  | 4
200466 | 51249 | 71955 | EKC | KS | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | 2021-04-12 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 | 5156585 | NTC - Commitment Window | 69 |  | 5.1
210536 | 41199 | 71960 | SPS | TX | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | 2021-10-21 | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1367428 |  | Delay - Mitigation | 115 | 10.25
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 20279796 | 2022 | 20279796 | 20297796 |  | Delay - Mitigation | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5468352 | 2022 | 5468352 | 5468352 |  | Delay - Mitigation | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | Delay - Mitigation | 345/115
210682 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 13329402 | 2022 | 13329402 | 13329402 |  | Delay - Mitigation | 115 | 2.6
210682 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 1605462 | 2022 | 1605462 | 1605462 |  | Delay - Mitigation | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5656017 | 2022 | 5656017 | 5656017 |  | Delay - Mitigation | 115
| 51255 | 71970 | WFEC | OK | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection | 2019-08-15 |  |  | GI STUDIES |  |  | 0 | 1700000 |  | On Schedule < 4
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2023-01-31 | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 99343.1601 | 90000 |  | On Schedule < 4 | 115
200482 | 51280 | 72011 | WFEC | OK | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | 2022-12-31 | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 813590 |  | Delay - Mitigation | 69
200482 | 51281 | 72012 | WFEC | OK | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | 2027-12-31 | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1103812.89 | 1000000 |  | Delay - Mitigation | 69
210483 | 51282 | 72013 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | 2022-12-31 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2207625.78 | 2000000 |  | Delay - Mitigation | 138
210483 | 51282 | 72014 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2022-12-31 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 5187920.583 | 4700000 |  | Delay - Mitigation | 138 | 9.4
210483 | 51282 | 72015 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-12-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8775312.4755 | 12428000 |  | Delay - Mitigation | 138 |  | 7.9 | 7.9
210669 | 51282 | 72016 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-03-31 | 2019-06-01 | 2022-04-28 | DPA-2017-August-767-774-776 | 8600000 | 2018 | 9492790.854 | 7520000 |  | Delay - Mitigation | 138 |  | 13.5 | 13.5
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-08-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9272028.276 | 8400000 |  | Delay - Mitigation | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-08-31 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1379766.1125 | 2150000 |  | Delay - Mitigation | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-05-31 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5022348.6495 | 4550000 |  | Delay - Mitigation | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2026-05-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | Delay - Mitigation | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6236542.8285 | 5650000 |  | Delay - Mitigation | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 3500000 |  | Delay - Mitigation | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-12-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 11750000 |  | Delay - Mitigation | 138 |  | 21.3 | 21.3
210483 | 51282 | 72025 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-04-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11755607.2785 | 1172000 |  | Delay - Mitigation | 138 |  | 2.1 | 2.1
210483 | 51282 | 72026 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-12-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1159003.5345 | 10380000 |  | Delay - Mitigation | 138 |  | 10 | 10
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-01-31 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5519064.45 | 5300000 |  | Delay - Mitigation | 138 |  | 10.6 | 10.6
210483 | 51282 | 72029 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2023-02-28 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4500000 | 2018 | 4967158.005 | 6141513 | 5762250.69 | Delay - Mitigation | 138 | 9
210483 | 51282 | 72030 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | 2023-01-31 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4975000 |  | Delay - Mitigation | 138
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2023-09-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4691204.7825 | 4250000 |  | Delay - Mitigation | 138 | 8.5
| 51283 | 72032 | EKC | KS/ | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  | 0 | 591265 |  | In Service
| 51283 | 72033 | EKC | KS/ | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  | 0 | 13383717 |  | In Service
| 51283 | 72034 | OGE | OK | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 20000 |  | On Schedule < 4
210496 | 51316 | 72095 | SPS | TX | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | 2022-03-11 | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 0 |  | On Schedule < 4 | 115
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-07-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11038128.9 | 10000000 |  | Delay - Mitigation | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7616308.941 | 6900000 |  | Delay - Mitigation | 138
210489 | 51327 | 82113 | WFEC | OK | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8388977.964 | 7019000 |  | Delay - Mitigation | 138
210489 | 51327 | 82114 | WFEC | OK | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 331143.867 | 360000 |  | Delay - Mitigation | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6954021.207 | 6300000 |  | Delay - Mitigation | 138
| 51332 | 82126 | OGE | OK/ | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | 2022-10-14 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | On Schedule < 4
| 51332 | 82127 | OGE | OK/ | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | 2022-10-14 |  |  | GI STUDIES |  |  | 0 | 1025042 |  | On Schedule < 4
| 51333 | 82128 | OGE | OK/ | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2022-10-15 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | On Schedule < 4
| 51333 | 82129 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2022-10-15 |  |  | GI STUDIES |  |  | 0 | 9213042 |  | On Schedule < 4
210496 | 61346 | 92151 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | 2024-11-22 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 13967362.375 | 15272259 |  | Delay - Mitigation | 230 | 0.2
210496 | 61346 | 92152 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | 2024-11-22 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 6694970.975 | 6889918 |  | Delay - Mitigation | 230/115
210507 | 61347 | 92153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36985904 |  | Delay - Mitigation | 345 | 21
210507 | 61347 | 92154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32431792 |  | Delay - Mitigation | 345 | 19
210507 | 61347 | 102153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5713168 |  | Delay - Mitigation | 345/115
210507 | 61347 | 102154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 6086950 |  | Delay - Mitigation | 345/115
210507 | 61347 | 102157 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6439926 |  | Delay - Mitigation | 345
210507 | 61347 | 102158 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | 2020-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15125912 |  | Delay - Mitigation | 115
210548 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2023-05-31 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3927927.3066 | 3647471 |  | Delay - Mitigation | 161 |  | 3.3
210505 | 71352 | 102172 | WFEC | OK | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | 2023-05-31 | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 772355.6447 | 887000 |  | Delay - Mitigation | 69
210611 | 81474 | 112307 | AEP | OK/ | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2024-10-01 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 9689511.55 | 25800000 |  | Delay - Mitigation
| 81483 | 112331 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 1175646 |  | In Service |  | 0.04
| 81483 | 112332 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 9959548.73 |  | In Service |  | 1.32
| 81489 | 112333 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 1388819 |  | On Schedule < 4 |  | 0.18
| 81489 | 112334 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection | 2023-05-01 |  |  | GI STUDIES |  |  | 0 | 17798882 |  | In Service |  | 0.32
| 81491 | 112337 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 918474 |  | On Schedule < 4 |  | 0.04
| 81491 | 112338 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 7400346 |  | On Schedule < 4
| 81488 | 112339 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-09-01 |  |  | GI STUDIES |  |  | 0 | 250000 |  | In Service
| 81488 | 112340 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2023-09-01 |  |  | GI STUDIES |  |  | 0 | 8805000 |  | In Service
| 81495 | 112353 | SPS | TX | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4
210540 | 81498 | 112358 | OGE | OK | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 278071.225 | 271289 |  | Complete | 138
210623 | 81500 | 112360 | AEP | OK | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 43180687.5 | 46270466 |  | Delay - Mitigation | 138 | 1.56
210544 | 81501 | 112361 | AEP | OK | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | 2024-10-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4645175.5906 | 4194065 |  | Delay - Mitigation | 138
210541 | 81503 | 112363 | SPS | TX | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability | 2021-05-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1741940.4525 | 257408 |  | Complete | 115
210538 | 81505 | 112366 | NPPD | NE | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | 2020-02-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 | 2555908 | Complete | 115
210538 | 81506 | 112367 | NPPD | NE | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | 2021-01-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 | 434289 | Complete | 115
210538 | 81507 | 112368 | NPPD | NE | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | 2022-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 679553 |  | Delay - Mitigation | 138
210539 | 81508 | 112369 | EM | KS | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | 2021-06-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 327164.625 | 261935 | 261935 | Complete | 161
210539 | 81509 | 112370 | EM | MO | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | 2020-09-24 | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 400871 | 400871 | Complete | 161
210539 | 81511 | 112372 | EM | MO | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | 2021-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 944091.625 | 1522101 | 1522101 | Complete | 161
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2027-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 870294.6744 | 838500 |  | Delay - Mitigation | 138
210545 | 81514 | 112378 | WFEC | OK | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | 2023-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 55052.75 | 52400 |  | Delay - Mitigation | 69
210545 | 81515 | 112379 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | 2022-12-29 | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 4100000 |  | Delay - Mitigation
210545 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2024-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 134795.1875 | 204000 |  | Delay - Mitigation
210542 | 81516 | 112381 | EKC | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | 2022-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3222443.5901 | 4086989 |  | In Service | 115 | 4
210605 | 81516 | 112383 | EKC | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability | 2022-06-01 | 2021-04-01 | 2021-03-02 | 2019 ITP | 9204123 | 2020 | 9670081.7269 | 14299391 |  | Complete | 115 | 2.2
210544 | 81520 | 112389 | AEP | OK | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 |  | Delay - Mitigation | 138/138 | 2
210544 | 81523 | 112393 | AEP | OK | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1549008 |  | Complete | 138/138 |  | 1.5
210545 | 81525 | 112395 | WFEC | OK | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2025-11-28 | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 420250 | 400000 |  | Delay - Mitigation | 69/69
210642 | 81529 | 112399 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2023-06-01 | 2023-06-01 | 2022-03-11 | 2021 ITP | 231742 | 2022 | 231742 | 263236 |  | On Schedule < 4 | 230
210642 | 81529 | 112401 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability | 2022-06-01 | 2023-06-01 | 2022-03-11 | 2021 ITP | 397668 | 2022 | 397668 |  |  | Delay - Mitigation | 230
210540 | 81532 | 112402 | OGE | OK | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | Delay - Mitigation | 69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 639725.5625 | 608900 |  | Delay - Mitigation | 115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3782250 | 2991100 |  | Delay - Mitigation | 115
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2021-01-01 | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1025000 | 1000000 |  | Delay - Mitigation | 138
210586 | 81553 | 112443 | WFEC | OK | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-12-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 10524075.5803 | 10267390.81 |  | Delay - Mitigation | 138
210543 | 81557 | 112451 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 485388.75 | 963697 |  | On Schedule < 4 | 115
210543 | 81557 | 112452 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1716195.9375 | 437574 |  | On Schedule < 4 | 115
210543 | 81557 | 112453 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1635297.8125 | 467574 |  | On Schedule < 4 | 115
210570 | 81559 | 112456 | EDE | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | 2023-04-01 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 69054450 | 73054450 |  | On Schedule < 4 | 161 |  | 25.9
210569 | 81559 | 112457 | EKC | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EKC) | Transmission Service | 2022-12-31 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 4008402 | 2020 | 4211327.3513 | 7617027 |  | On Schedule < 4 | 161 | 2.7
210593 | 81561 | 112458 | TSOK | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | 2026-01-01 | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 102028138.4569 | 97111851 |  | On Schedule < 4 | 345 | 50.5
210544 | 81561 | 112460 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 770654.45 | 1242638 |  | On Schedule < 4 | 138
210544 | 81571 | 112488 | AEP | OK | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 |  | Complete | 138/115
210544 | 81561 | 112502 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3409095.4055 | 5329277 |  | On Schedule < 4 | 345 | 0.06
210540 | 81561 | 112504 | OGE | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic | 2024-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4349183.0094 | 4139615 |  | On Schedule < 4 | 345
210592 | 81547 | 112509 | EKC | KS | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-12-31 | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 11908479.725 | 17884513 |  | On Schedule < 4 | 345
210515 | 81581 | 112510 | SPS | NM | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3409095.4055 | 0 |  | Delay - Mitigation |  | 3.5
210515 | 81581 | 122510 | SPS | TX | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 4037504.1579 | 0 |  | Delay - Mitigation | 115
210609 | 81591 | 122537 | OGE | OK | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2024-04-20 | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4095900 | 3996000 |  | Delay - Mitigation
| 81594 | 122540 | SPS | NM | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 7365886 |  | On Schedule < 4
| 81600 | 122546 | SPS | TX | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-01 |  |  | GI STUDIES |  |  | 0 | 184651 |  | On Schedule < 4
| 81599 | 122547 | SPS | TX | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2022-12-15 |  |  | GI STUDIES |  |  | 0 | 210533 |  | On Schedule < 4
| 81606 | 122554 | SPS | NM | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 483969 |  | On Schedule < 4
| 81607 | 122556 | SPS | NM | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 413496 |  | On Schedule < 4
| 81608 | 122558 | SPS | NM | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 413496 |  | On Schedule < 4
| 81609 | 122560 | SPS | NM | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 413496 |  | On Schedule < 4
| 81613 | 122568 | SPS | TX | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 14055360 |  | On Schedule < 4 |  | 0.5
210560 | 81614 | 122570 | BEPC | ND | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33155575 | 2020 | 34834075.9844 | 29646000 |  | Delay - Mitigation | 230 | 30
210559 | 81614 | 122571 | MWE | ND | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | 2021-09-05 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19716372.125 | 19235485 |  | Delay - Mitigation | 115 | 20.5
210560 | 81614 | 122572 | BEPC | ND | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3176320 | 2020 | 3337121.2 | 3653000 |  | Delay - Mitigation | 230/115
210560 | 81614 | 122575 | BEPC | ND/ | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 21998353.9688 | 13612902 |  | Delay - Mitigation
210586 | 81617 | 122577 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | 2026-12-31 | 2023-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2994281.25 | 5750000 |  | Suspended | 138
210626 | 81547 | 122598 | NEET | KS/MO | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-01-01 | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 87298161.45 | 87298154 |  | On Schedule < 4 | 345
210522 | 81616 | 122599 | NWE | SD | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | 2019-06-01 | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 | 555000 | Complete | 115
210564 | 81489 | 122600 | OGE | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection | 2021-12-31 | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | Delay - Mitigation
210630 | 81490 | 122601 | OGE | OK | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection | 2023-12-31 | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  | 0 | 10000 |  | On Schedule < 4
210562 | 81628 | 122602 | WAPA | ND//ND | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2024-12-31 |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1586443.75 | 1510000 |  | In Service
210565 | 81481 | 122622 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection | 2025-12-31 |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 146903.6406 | 136893 |  | In Service
| 81481 | 122623 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES | 10000 | 2020 | 10506.25 | 10000 |  | In Service
| 81636 | 122635 | OGE | OK | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-14 |  |  | GI STUDIES |  |  | 0 | 1099871 |  | On Schedule < 4
210606 | 81636 | 122637 | EKC | KS | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 17039.6 | 16624.73 |  | In Service
| 81639 | 122640 | SPS | NM | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-17 |  |  | GI STUDIES |  |  | 0 | 4578401 |  | On Schedule < 4
| 81640 | 122641 | SPS | NM | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 697513 |  | On Schedule < 4
| 81641 | 122642 | SPS | NM | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4
| 81642 | 122643 | SPS | NM | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4
| 81645 | 122645 | SPS | NM | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-15 |  |  | GI STUDIES |  |  | 0 | 4852215 |  | On Schedule < 4 |  |  | 13
| 81644 | 122646 | SPS | NM | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-15 |  |  | GI STUDIES |  |  | 0 | 968567 |  | On Schedule < 4
| 81646 | 122647 | SPS | TX | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 5943138 |  | On Schedule < 4
| 81647 | 122648 | SPS | TX | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2021-10-28 |  |  | GI STUDIES |  |  | 0 | 3318135 |  | On Schedule < 4
210557 | 81652 | 122657 | CBPC | IA | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability | 2020-06-01 | 2020-06-01 | 2020-04-08 | DPA-2019-March-1011 | 1100000 | 2020 | 1100000 | 1227000 | 1253747.71 | Complete
210552 | 81654 | 122661 | NPPD | NE | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability | 2020-06-01 | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 | 3704140 | Complete | 230/115
| 81655 | 122662 | OGE | OK | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 15000 |  | On Schedule < 4
210563 | 81656 | 122664 | NPPD | NE | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | 2022-12-01 | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 6000000 |  | On Schedule < 4 |  |  | 13
| 81657 | 122665 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 1388819 |  | On Schedule < 4 |  | 0.18
| 81657 | 122666 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 10361130 |  | On Schedule < 4
210631 | 81657 | 122667 | OGE | OK | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection | 2025-12-31 | 2025-12-31 | 2022-01-31 | DISIS-2016-002 |  |  | 0 | 15000 |  | On Schedule < 4
| 81658 | 122669 | BEPC | ND | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2025-06-30 |  |  | GI STUDIES |  |  | 0 | 2776827 |  | On Schedule < 4
| 81660 | 122673 | EKC | KS | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 90000 |  | In Service
210612 | 81660 | 122674 | OGE | OK | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15375 | 15000 |  | On Schedule < 4
| 81662 | 122677 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4
| 81662 | 122678 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4
| 81665 | 122684 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  | 0 | 1636796 |  | On Schedule < 4
| 81665 | 122687 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  | 0 | 2155837 |  | On Schedule < 4
| 81666 | 122688 | WAPA | SD | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-08-30 |  |  | GI STUDIES |  |  | 0 | 644488 |  | In Service
210558 | 81673 | 122713 | AEP | OK | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-01 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 2752417 |  | On Schedule < 4 | 115 |  | 0.49
210578 | 81675 | 122717 | GRDA | OK/ | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2023-01-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 383760 | 374400 |  | Delay - Mitigation | 345/345
210578 | 81675 | 122718 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2023-01-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | Delay - Mitigation | 345/161
210586 | 81679 | 122722 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-12-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 932750 | 910000 |  | Delay - Mitigation
210574 | 81682 | 122725 | SPS | TX | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3035101.875 | 2961075 |  | Delay - Mitigation |  |  | 3.5
210574 | 81684 | 122727 | SPS | TX | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7534565.9 | 7350796 |  | Delay - Mitigation |  |  | 6
210575 | 81687 | 122730 | AEP | LA | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2024-06-03 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 24213141.425 | 20597910 |  | Delay - Mitigation |  | 11.2
210648 | 81691 | 122734 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 561800 | 561800 |  | On Schedule < 4
210639 | 81691 | 122735 | EREC | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic | 2023-11-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 587000 | 2022 | 587000 | 587000 |  | On Schedule < 4
210645 | 81694 | 122739 | NPPD | NE | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5080000 | 5080000 |  | Delay - Mitigation | 230/115
210645 | 81769 | 122741 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 7760000 | 7760000 |  | Delay - Mitigation
210581 | 81768 | 122745 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3474482.475 | 3910285 |  | Delay - Mitigation | 230/115
210581 | 81768 | 122746 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 177367.025 | 173041 |  | Delay - Mitigation | 230/115
210586 | 81617 | 122753 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic | 2026-12-31 | 2023-01-01 | 2020-11-17 | 2020 ITP | 1750000 | 2021 | 1793750 | 1750000 |  | Suspended
210589 | 81617 | 122755 | OGE | OK | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic | 2023-01-01 | 2023-01-01 | 2020-11-17 | 2020 ITP | 6075003 | 2021 | 6226878.075 | 1124593 |  | Suspended
| 81670 | 122791 | OGE | OK | Viola 345/138 kV Transformer CKT 2 | GEN-2016-119 Tap - Arcadia 345kV (DISIS-2016-002-3) | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES |  |  | 0 | 68725000 |  | On Schedule < 4
| 81670 | 122792 | EKC | KS | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 11450023 |  | In Service
210627 | 81717 | 122796 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2023-04-30 | 2022-01-01 | 2021-11-05 | 2020 ITP | 12210364 | 2021 | 12515623.1 | 8370000 |  | Delay - Mitigation |  | 0.2
210578 | 81675 | 122801 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-30 | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | Complete
210578 | 81675 | 122802 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-30 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | Complete | 161/0
210582 | 81719 | 122803 | SEPC | KS | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability | 2024-04-01 | 2022-06-01 | 2020-11-23 | 2020 ITP | 5306633 | 2021 | 5439298.825 | 7172538 |  | Delay - Mitigation
210583 | 81720 | 122804 | EM | KS | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-12-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 909665.975 | 914927 |  | Delay - Mitigation
210583 | 81722 | 122806 | EM | KS | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 300000 |  | In Service
210583 | 81723 | 122807 | EM | KS | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability | 2023-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 335416 | 2020 | 352396.435 | 355416 |  | Delay - Mitigation
210583 | 81724 | 122808 | EM | KS | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability | 2021-12-22 | 2022-06-01 | 2020-11-17 | 2020 ITP | 244265 | 2021 | 244265 | 386488 | 386488 | Complete
210589 | 81733 | 122818 | OGE | OK//OK | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4388178.75 | 4281150 |  | On Schedule < 4 |  |  | 4.71
210589 | 81733 | 122819 | OGE | OK/ | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1108690.225 | 1081649 |  | On Schedule < 4 |  |  | 1.19
210628 | 81717 | 122823 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2023-04-01 | 2022-01-01 | 2021-11-05 | 2020 ITP | 11500000 | 2021 | 11787500 | 11500000 |  | Delay - Mitigation
210616 | 81741 | 122848 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1889822.225 | 1843729 |  | On Schedule < 4 | 345
210616 | 81741 | 122849 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 31475649.775 | 30707951 |  | On Schedule < 4 | 345
210616 | 81741 | 122850 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5128925.75 | 5003830 |  | On Schedule < 4 | 345/138
210616 | 81741 | 122851 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5007790.225 | 4885649 |  | On Schedule < 4 | 345/138
210616 | 81741 | 122858 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2604730 | 2541200 |  | On Schedule < 4
210656 | 81741 | 122863 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 65000 |  | On Schedule < 4
210586 | 81751 | 122864 | WFEC | OK | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 871250 | 850000 |  | On Schedule < 4
210586 | 81679 | 122865 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 207562.5 | 202500 |  | Delay - Mitigation
210586 | 81679 | 122866 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 415125 | 405000 |  | Delay - Mitigation
210574 | 81755 | 122869 | SPS | TX//TX | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 366823 |  | Delay - Mitigation |  | 33
210574 | 81757 | 122871 | SPS | TX/ | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 11900197.725 | 11609949 |  | Delay - Mitigation |  | 17.4
210574 | 81758 | 122872 | SPS | TX | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | Delay - Mitigation |  |  | 4
210574 | 81760 | 122876 | SPS | TX | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7130500.65 | 6956586 |  | Delay - Mitigation |  | 7.3
210574 | 81763 | 122883 | SPS | TX | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 1042629 |  | On Schedule < 4 |  | 14.6
210584 | 81497 | 132893 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 | 989393 | Complete
210670 | 81741 | 133085 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic | 2024-07-01 | 2025-01-01 | 2022-04-28 | 2020 ITP | 38537430 | 2022 | 38537430 | 38537430 |  | On Schedule < 4
210670 | 81741 | 133106 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic | 2024-07-01 | 2025-01-01 | 2022-04-28 | 2020 ITP | 16516041 | 2021 | 16928942.025 | 16516041 |  | On Schedule < 4
210677 | 81802 | 143117 | OGE | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Degrasse345 kV Substation | Generation Interconnection | 2024-06-01 | 2024-07-12 | 2022-06-22 | DISIS-2017-001 |  |  | 0 | 30000 |  | On Schedule < 4
210704 | 81854 | 143125 | OGE | KS/ | Sub - Viola 345 kV | Viola 345 kV Substation | Generation Interconnection | 2024-05-08 | 2024-10-31 | 2022-10-16 | DISIS-2017-001 |  |  | 0 | 20000 |  | On Schedule < 4
210643 | 81773 | 143127 | OGE | OK | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection | 2022-09-01 | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | On Schedule < 4
210576 | 91875 | 143156 | AEP | OK | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | 2022-10-28 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1910669 |  | On Schedule < 4
210579 | 91876 | 143157 | WAPA | ND/ | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-10-01 | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2196797.425 | 2143217 |  | Delay - Mitigation
210585 | 91878 | 143159 | MRES | MN | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | 2024-12-31 | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 | 2022 | 4358300 | 6178200 |  | Delay - Mitigation
210591 | 91881 | 143162 | CPEC | ND | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability | 2022-09-26 | 2022-04-01 | 2020-11-23 | 2020 ITP | 1310400 | 2021 | 1343160 | 2000000 |  | Complete
210574 | 91884 | 143167 | SPS | TX | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1717624.275 | 1675731 |  | Delay - Mitigation |  |  | 1.15
210616 | 81741 | 143176 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6646646.325 | 6484533 |  | On Schedule < 4
210600 | 91885 | 143177 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S1260 - S1362 161 kV Ckt 1 Rebuild | Regional Reliability | 2022-08-01 | 2023-04-01 | 2021-02-16 | DPA-2018-October-949 | 858928 | 2021 | 880401.2 | 858928 |  | On Schedule < 4 | 161
210600 | 91885 | 143178 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-08-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 102500 | 100000 |  | On Schedule < 4 | 345
210600 | 91885 | 143179 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability | 2024-04-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 615000 | 600000 |  | On Schedule < 4 | 345
210584 | 81497 | 143181 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3359437.5 | 3277500 |  | On Schedule < 4 |  | 14.4
210627 | 81717 | 143182 | AEP | OK//OK | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2024-05-24 | 2022-01-01 | 2021-11-05 | 2020 ITP | 1259660 | 2021 | 1291151.5 | 5264319 |  | Delay - Mitigation | 345 | 1
210590 | 91891 | 143183 | EMW | KS | Sub - Greenwood 161 kV Terminal Upgrades | Greenwood 161 kV Terminal Upgrades | Transmission Service | 2022-03-15 | 2021-12-31 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 600168 | 2021 | 615172.2 | 564726 | 564726 | Complete | 161
210617 | 91939 | 143253 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2023-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8061625 | 7865000 |  | Delay - Mitigation | 69
210617 | 91939 | 143254 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5474012.5 | 5340500 |  | Delay - Mitigation Window | 69
210617 | 91939 | 143255 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 461250 | 450000 |  | Delay - Mitigation Window
210617 | 91939 | 143256 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 512500 | 500000 |  | Delay - Mitigation Window
210655 | 92112 | 143587 | EM | KS | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 55271.78 | 2022 | 55271.78 | 55271.78 |  | In Service | 161
210675 | 92113 | 143588 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 78293357 | 2022 | 78293357 | 78293357 |  | Suspended | 345
210675 | 92113 | 143589 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  | Suspended | 345
210675 | 92113 | 143590 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 342000 | 2022 | 342000 | 342000 |  | Suspended | 345
210633 | 92114 | 143591 | AEP | OK | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-05-01 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9020000 | 9020000 |  | Delay - Mitigation | 69
210645 | 81769 | 143599 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1194000 | 1194000 |  | Delay - Mitigation | 115
210645 | 81769 | 143600 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1129000 | 1129000 |  | Delay - Mitigation | 115
210648 | 81691 | 143613 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1744800 | 1744800 |  | On Schedule < 4 | 230
210648 | 81691 | 143614 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 5845900 | 5845900 |  | On Schedule < 4 | 230
210680 | 92123 | 143660 | OPPD | NE | Line - S3454 - S3740 345 kV | S3454 - S3740 345 kV New Line | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 64071687 | 2022 | 64071687 | 64071687 |  | Delay - Mitigation | 345
210680 | 92123 | 143661 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3454 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 2070042 | 2022 | 2070042 | 2070042 |  | Delay - Mitigation | 345
210680 | 92123 | 143662 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3740 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 1786830 | 2022 | 1786830 | 1786830 |  | Delay - Mitigation | 345
210637 | 92140 | 143663 | EKC | KS/ | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 236539 | 2022 | 236539 | 236539 |  | In Service | 115
210647 | 92144 | 143664 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 864676 |  | In Service | 161
210647 | 92144 | 143665 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 255075 | 255075 |  | In Service | 161
210647 | 92141 | 143666 | EM | KS | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 319002 | 2022 | 319002 | 319002 |  | In Service | 161
210640 | 92142 | 143667 | MRES | MN | Sub - Moorhead 230 kV Substation Reconfiguration | Moorhead 230 kV Substation Reconfiguration | Regional Reliability | 2024-12-31 | 2023-06-01 | 2022-03-11 | 2021 ITP | 9989000 | 2022 | 9989000 | 12921270 |  | Delay - Mitigation | 230
210654 | 92143 | 143668 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th - Stateline 161 kV Rebuild | Regional Reliability | 2026-06-01 | 2026-06-01 | 2022-03-11 | 2021 ITP | 10688750 | 2022 | 10688750 | 10688750 |  | On Schedule < 4 | 161
210654 | 92143 | 143669 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 | 2026-06-01 | 2022-03-11 | 2021 ITP | 393232 | 2022 | 393232 | 393232 |  | On Schedule < 4 | 161
210654 | 92143 | 143670 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Stateline 161 kV Terminal Upgrades | Regional Reliability | 2026-06-01 | 2026-06-01 | 2022-03-11 | 2021 ITP | 209518 | 2022 | 209518 | 209518 |  | On Schedule < 4 | 161
210619 | 92180 | 143705 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 11250834 | 11250834 |  | Delay - Mitigation
210675 | 92168 | 143714 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 67411405 | 67411405 |  | Delay - Mitigation
210656 | 92184 | 143786 | OGE | OK | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP | 168228 | 2022 | 168228 | 168228 |  | On Schedule < 4 | 69
210656 | 92190 | 143806 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1575000 | 1575000 |  | On Schedule < 4 | 138
210656 | 92190 | 143815 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5000000 | 5000000 |  | On Schedule < 4 | 69
210656 | 92190 | 143816 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 8806000 | 8806000 |  | On Schedule < 4 | 69
210656 | 92190 | 143817 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 250000 | 250000 |  | On Schedule < 4 | 69
210641 | 92213 | 143980 | NIPCO | IA//IA | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability | 2023-10-31 | 2023-06-01 | 2022-03-11 | 2021 ITP | 223750 | 2022 | 223750 | 233750 |  | Delay - Mitigation
210644 | 92238 | 144142 | TSGT | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic | 2023-12-13 | 2023-01-01 | 2022-03-11 | 2021 ITP | 380321 | 2022 | 380321 | 380321 |  | Delay - Mitigation
210645 | 92238 | 144143 | NPPD | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic | 2023-12-31 | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 281000 | 281000 |  | Delay - Mitigation
210663 | 92178 | 144148 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 22213115 | 19500000 |  | Delay - Mitigation
210663 | 92211 | 144163 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 613746 | 613746 |  | Delay - Mitigation
210675 | 92211 | 144171 | BEPC | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability | 2024-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 17766381 | 17766380 |  | Delay - Mitigation
210657 | 92190 | 144173 | WFEC | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability | 2023-06-01 | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 736000 | 736000 |  | On Schedule < 4
210663 | 92211 | 144177 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 3800000 | 2022 | 3800000 | 6490000 |  | Delay - Mitigation
210663 | 92211 | 144178 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 596597 | 596597 |  | Delay - Mitigation
210675 | 92211 | 144198 | BEPC | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability | 2024-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 5904650 | 6136273 |  | Delay - Mitigation
210663 | 92211 | 144199 | MWE | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability |  | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2511246 | 2511246 |  | On Schedule < 4
210663 | 92178 | 144202 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1087789 | 1500000 |  | Delay - Mitigation
210706 | 92237 | 144206 | SPS | TX | Line - Twist - Wilco 115 kV | Wilco 115 kV Substation | Regional Reliability | 2024-12-15 | 2022-06-01 | 2022-10-26 | DPA-2021-Feb-1279-1280 | 9044750 | 2022 | 9044750 | 9044750 |  | On Schedule < 4
210706 | 92237 | 144207 | SPS | TX//TX | Line - Twist - Wilco 115 kV | RB-Exum - Twist 115 kV Ckt 1 New Line | Regional Reliability | 2024-12-15 | 2022-06-01 | 2022-10-26 | DPA-2021-Feb-1279-1280 | 3622274 | 2022 | 3622274 | 3622274 |  | On Schedule < 4
210706 | 92237 | 144208 | SPS | TX | Line - Twist - Wilco 115 kV | T47 - Twist 115 kV Ckt 1 New Line | Regional Reliability | 2024-12-15 | 2022-06-01 | 2022-10-26 | DPA-2021-Feb-1279-1280 | 3315173 | 2022 | 3315173 | 3315173 |  | On Schedule < 4
210663 | 92168 | 144226 | MWE | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability | 2025-12-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 4702500 | 4702500 |  | Delay - Mitigation
210675 | 92168 | 144227 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 4675697 | 4675697 |  | Delay - Mitigation
210675 | 92168 | 144230 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 18822018 | 18822018 |  | Delay - Mitigation
210675 | 92168 | 144231 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 385021 | 385021 |  | Delay - Mitigation
210675 | 92168 | 144233 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5799981 |  | Delay - Mitigation | 345/115
210675 | 92168 | 144235 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5315254 | 5799981 |  | Delay - Mitigation | 345/115
210675 | 92168 | 144236 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 200761539 | 215340373 |  | Delay - Mitigation
210675 | 92168 | 144237 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 9277339 | 9277339 |  | Delay - Mitigation
210675 | 92168 | 144238 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5085047 | 5085047 |  | Delay - Mitigation
210663 | 92168 | 144239 | MWE | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability | 2025-12-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 3811190 | 3811190 |  | Delay - Mitigation
210665 | 92268 | 144276 | WFEC | AR | Multi - Elmore - Bradly 69 kV | Elmore 69 kV Terminal Upgrades | Regional Reliability | 2023-03-30 | 2022-06-01 | 2022-04-18 | DPA-2021-June-1332 | 228000 | 2022 | 228000 | 228000 |  | On Schedule < 4
210665 | 92268 | 144277 | WFEC | AR | Multi - Elmore - Bradly 69 kV | Bradly Tap 69 kV Cap Bank | Regional Reliability |  | 2022-06-01 | 2022-04-18 | DPA-2021-June-1332 | 803000 | 2022 | 803000 | 803000 |  | Delay - Mitigation
210664 | 92271 | 144278 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | West Oaks Terminal Upgrades | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 |  |  | 0 | 400000 | 400000 | In Service
210664 | 92271 | 144279 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen 138 kV Terminal Upgrades | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 |  |  | 0 | 600000 |  | In Service
210664 | 92271 | 144280 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Council - Mustang 138 kV Ckt 1 Reconductor | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 |  |  | 0 | 1390000 |  | In Service
210664 | 92271 | 144281 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen - Douglas Tap 138 kV Reconductor | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 |  |  | 0 | 790000 |  | In Service
210619 | 92180 | 144283 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1288644 | 1288644 |  | Delay - Mitigation
210619 | 92180 | 144284 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2692377 | 2692377 |  | Delay - Mitigation
210660 | 92305 | 144327 | EREC | SD/SD/SD | Onida Capicitor Bank | Onida capacitor bank | Sponsored Upgrade | 2020-06-01 | 2021-11-23 | 2022-03-21 | SUS-016 |  |  | 0 | 124885 | 424844 | Complete | 69
210661 | 92308 | 144328 | EREC | SD/SD/SD | Line Carpenter – Willow Lake 69 kV | Carpenter – Willow Lake 69 kV | Sponsored Upgrade | 2025-01-01 | 2021-11-23 | 2022-03-21 | SUS-018 |  |  | 0 | 0 |  | Delay - Mitigation | 69
210662 | 92309 | 144329 | EREC | SD/SD/SD | Sub-Hughes County 115/69kV | Hughes County 115/69kV substation | Sponsored Upgrade | 2021-06-01 | 2021-11-23 | 2022-03-21 | SUS-019 |  |  | 0 | 3075749 | 3456476 | Complete | 115/69
210674 | 92371 | 156240 | BEPC | ND | Line - Boundary Dam - Tande 230 kV | Boundary Dam - Tande 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2022-07-01 | 2022-05-18 | SPP- 2021-AG2 |  |  | 0 | 62383000 |  | Delay - Mitigation | 230
210674 | 92371 | 156241 | BEPC | ND | Line - Boundary Dam - Tande 230 kV | Tande 230 kV Terminal Equipment | Transmission Service | 2027-10-01 | 2022-07-01 | 2022-05-18 | SPP- 2021-AG2 |  |  | 0 | 2476563 |  | Delay - Mitigation | 230
210674 | 92372 | 156248 | BEPC | ND | Line - Boundary Dam - Wheelock 230 kV | Boundary Dam - Wheelock 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2027-10-01 | 2022-05-18 | SPP- 2021-AG2 |  |  | 0 | 70998000 |  | On Schedule > 4 | 230
210674 | 92372 | 156249 | BEPC | ND | Line - Boundary Dam - Wheelock 230 kV | Wheelock 230 kV Terminal Upgrade | Transmission Service | 2027-10-01 | 2027-10-01 | 2022-05-18 | SPP- 2021-AG2 |  |  | 0 | 2476563 |  | On Schedule > 4 | 230
210715 | 92394 | 156282 | WAPA | ND | Sub - Fargo 230 kV Terminal Upgrade | Fargo 230 kV Terminal Upgrade | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 2406249 |  | On Schedule < 4 | 230
210714 | 92382 | 156288 | SPS | NM | Device - Lea Road 115 kV Capacitor Bank | Lea Road 115 kV Capacitor Bank | Regional Reliability |  | 2028-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 5009320 |  | On Schedule > 4 | 115
210710 | 92381 | 156289 | EM | KS | Device - Craig 345 kV Relay | Craig 345 kV Relay | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 200000 |  | On Schedule < 4 | 345
210708 | 92393 | 156293 | AEP | AR | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs 161 kV Terminal Upgrade | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 698030 |  | On Schedule < 4 | 161
210711 | 92393 | 156294 | GRDA | AR | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs City 161 kV Terminal Upgrade | Regional Reliability | 2024-03-29 | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 324000 |  | On Schedule < 4 | 161
210708 | 92386 | 156299 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis - 52nd & Delaware Tap 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2027-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 4951250 |  | On Schedule > 4 | 138
210708 | 92386 | 156300 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis 138 kV Ckt 1 Terminal Upgrade | Regional Reliability |  | 2027-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 540691 |  | On Schedule > 4 | 138
210712 | 92389 | 156320 | NIPCO | IA | Line - Eagle - J1 Center 69 kV Rebuild | Eagle - J1 Center 69 kV Ckt 1 rebuild | Regional Reliability | 2024-07-01 | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 1644058 |  | On Schedule < 4 | 69
210679 | 92402 | 156334 | MWE | ND | Device - Twelve Mile 115 kV Capacitor Bank | Twelve Mile 115 kV Capacitor Bank | Transmission Service | 2029-10-01 | 2029-10-01 | 2022-06-30 | SPP- 2021-AG2 |  |  | 0 | 571195 |  | On Schedule > 4 | 115
210709 | 92403 | 156359 | EDE | MO | Device - Dadeville 161 kV Breaker | Dadeville 161 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 714104 |  | On Schedule < 4 | 161
210709 | 92404 | 156360 | EDE | MO | Device - Joplin 69 kV Breaker | Joplin 69 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 1719120 |  | On Schedule < 4 | 69
210709 | 92405 | 156361 | EDE | MO//MO | Device - Ozark Dam 161 kV Breaker | Ozark Dam 161 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 714104 |  | On Schedule < 4 | 161
210713 | 30823 | 156369 | OGE | OK | INACTIVES | Westmoore - Westmoore Tap 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2031-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 1000000 |  | On Schedule > 4 | 138 |  | 1
210713 | 30823 | 156370 | OGE | OK | INACTIVES | Westmoore 138 kV Terminal Upgrade | Regional Reliability |  | 2031-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 750000 |  | On Schedule > 4 | 138
210713 | 30823 | 156371 | OGE | OK | INACTIVES | Westmoore Tap 138 kV Terminal Upgrade | Regional Reliability |  | 2031-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 650000 |  | On Schedule > 4 | 138
210713 | 92411 | 156372 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #1 | Regional Reliability |  | 2014-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 462388 |  | Delay - Mitigation | 138
210713 | 92411 | 156373 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #2 | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 462388 |  | On Schedule < 4 | 138
210714 | 92412 | 156374 | SPS | TX | Device - Lubbock South 115 kV Breaker | Lubbock South 115 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 467987 |  | On Schedule < 4 | 115
210713 | 92413 | 156375 | OGE | OK | Device - Cherry Creek 138 kV Breaker | Cherry Creek 138 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 462388 |  | On Schedule < 4 | 138
210713 | 92414 | 156376 | OGE | OK | Device - Indian Hill 138 kV Breaker | Indian Hill 138 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 462388 |  | On Schedule < 4 | 138
210713 | 92415 | 156377 | OGE | OK | Device - Turner 138 kV Breaker | Turner 138 kV Breaker | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 462388 |  | On Schedule < 4 | 138
210681 | 92421 | 156407 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Crossroads 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP |  |  | 0 | 14606215 |  | Delay - Mitigation | 345
210681 | 92421 | 156408 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #1 | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP |  |  | 0 | 17827816 |  | Delay - Mitigation | 345
210681 | 92421 | 156409 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #2 | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP |  |  | 0 | 12230126 |  | Delay - Mitigation | 345
210681 | 92421 | 156410 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Roadrunner 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP |  |  | 0 | 13774899 |  | Delay - Mitigation | 345
210716 | 92639 | 156844 | OPPD | NE | Line - S1254 - S1281 161 kV Ckt 1 Reconductor | S1254 - S1281 161 kV Ckt 1 Reconductor | Transmission Service | 2023-10-01 | 2023-10-01 | 2022-11-29 | SPP-2022-AG1-AFS-2 |  |  | 0 | 1171441 |  | On Schedule < 4