## St.Louis1
Production Report for Partnering Agreement
District:Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Castlewood | Partial | 48.17 | 8 | 8 |  |  |  | 8
0
Des Peres | All | 29.22 | 29.22 | 28.64 | 0.58 |  |  | 29.22
0
Fenton | All | 58.32 | 58.32 | 8.8 | 46.29 | 1.72 | 1.51 | 58.32
0
Bowles | All | 22.62 | 22.62 |  | 5.97 | 16.55 | 0.1 | 22.62
0
Valley Park | Partial | 52.89 | 24.16 |  |  | 19.21 | 5.03 | 52.69
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 211.22 | 142.32 | 45.44 | 52.84 | 37.48 | 6.64 | 142.4
|  | Quarterly Goal |  | 29.38 | 33.12 | 39.31 | 40.51 | 142.32
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis2
Production Report for Partnering Agreement
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Schuetz | 56,56 | 56.4 | 5 | 5 |  |  |  | 5 | Not completed in 2004
0
Groby | All | 31.56 | 31.56 | 26.32 | 4.76 | 0.48 |  | 31.56
0
Midland | All | 34.77 | 34.77 | 2.76 | 31.01 | 1 |  | 34.77
0
Ashby | All | 26.38 | 26.38 |  | 6.83 | 17.15 | 2.4 | 26.38
0
Dougherty Ferry | All | 44.5 | 44.5 |  |  | 3.98 | 40.52 | 44.5
0
Woodson | Most | 24.63 | 19.95 |  |  |  | 19.95 | 19.95 | Bob and Chris's crews scehduled to
[8 empty] | 0 | help finish off Woodson.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 218.24 | 162.16 | 34.08 | 42.6 | 22.61 | 62.87 | 162.16
|  | Quarterly Goal |  | 30.56 | 56.07 | 35.55 | 39.98 | 162.16
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis3
Production Report for Partnering Agreement
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Hanley | 1 | 29.2 | 0.5 | 0.5 |  |  |  | 0.5 | Carry over from 2004
0
Dale | 03,04 | 16.49 | 5 | 5 |  |  |  | 5 | Carry over from 2004
0
Chouteau | All | 9.58 | 9.58 | 9.58 |  |  |  | 9.58
0
Ashley | All | 1.01 | 1.01 | 1.01 |  |  |  | 1.01
0
Hickory | All | 21.19 | 21.19 | 18.73 | 2.3 | 0.16 |  | 21.19
0
Vista | All | 5.93 | 5.93 | 5.93 |  |  |  | 5.93
0
Folsom | All | 25.46 | 25.46 | 8.3 | 16.16 | 1 |  | 25.46 | 3 line kills left
0
Vernon |  |  |  |  | 1 | 6.56 |  | 7.56
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 108.86 | 68.67 | 49.05 | 19.46 | 7.72 | 0 | 76.23
|  | Quarterly Goal |  | 37.28 | 5 | 5.93 | 20.46 | 68.67
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis4
Production Report for Partnering Agreement
District: metro
Substation | Feeder No. | Total feeder miles | feeder miles 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Sunset | partial | 28.3 |  | 4.14 |  |  |  | 4.14 | reflects 3.08 not reported in '04
0
Clydesdale | all | 19.42 | 0.34 | 19.08 |  |  |  | 19.08
0
Will | all | 35.48 |  | 24.55 | 10.93 |  |  | 35.48
0
Concord | all | 50.15 |  |  | 45.21 | 4.94 |  | 50.15
0
Sappington | all | 73.66 |  |  |  | 26.64 | 47.02 | 73.66
0
Tesson | all | 38.38 |  |  |  |  | 38.38 | 38.38
0
0
0
Total Miles = |  | 217.09 | 0.34 | 47.77 | 56.14 | 31.85 | 85.4 | 220.89
|  | Quarterly Goal |  | 54.9 | 50.15 | 51.58 | 60.46 | 217.09
Note on A9: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C22: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E21: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis5
Production Report for Partnering Agreement
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Webster | Partial | 46.6 | 39.6 | 31.9 | 7.7 |  |  | 39.6
0
Yorkshire | All | 22.59 | 22.59 |  | 20.3 | 4.02 |  | 24.32 | actual=24.32 vs.22.59
0
Telegraph | All | 54.15 | 54.15 |  |  | 28.92 | 25.22 | 54.14 | missing 7.1 miles???
0
Ripa | All | 17.38 | 17.38 |  |  |  | 17.38 | 17.38
0
Affton | All | 16.79 | 16.79 |  |  |  | 16.79 | 16.79
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 157.51 | 150.51 | 31.9 | 28 | 32.94 | 59.39 | 152.23
|  | Quarterly Goal |  | 34.27 | 29.42 | 45.55 | 34.17 | 143.41
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis6
Production Report for Partnering Agreement
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Larimore | Partial | 60.3 | 26.3 | 26 | 0.3 |  |  | 26.3 | Not completed in 2004
0
Gimblin | All | 16.9 | 16.9 | 12.25 | 4.55 | 0.1 |  | 16.9 | New sub made from part of Baden
0
Baden | All | 13.3 | 13.3 | 7 | 6.21 | 0.09 |  | 13.3 | Two feeders left from original sub.
0
Humboldt | All | 13.7 | 13.7 | 5 | 7.64 | 1.06 | 0.05 | 13.7
0
Bittner | All | 1 | 1 |  |  | 1 |  | 1
0
Prairie | All | 22.8 | 22.8 | 1 | 20.73 | 1.07 |  | 22.8
0
McPherson | All | 11.66 | 10 |  |  | 8.91 | 1.09 | 10
Duncan | All | 12.86 | 12.86 |  | 0.23 | 11.18 | 1.45 | 12.86
Laclede | All | 8.97 | 8.97 |  | 0.08 | 8.3 | 0.59 | 8.97
0
Enright | All | 25.32 | 25.32 |  |  | 2.76 | 22.56 | 25.32
Dyer | All | 31.4 | 31.4 |  |  |  | 31.4 | 31.4
0
Hoover | All | 3.67 | 3.67 |  |  |  | 3.67 | 3.67
[8 empty] | 0 | Help finish Woodson
Woodson | Partial | 24.63 | 1.5 |  |  |  | 1.5 | 1.5
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 246.51 | 187.72 | 51.25 | 39.74 | 34.47 | 62.31 | 187.72
|  | Quarterly Goal |  | 44.9 | 40.62 | 39.88 | 62.76 | 188.16
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.

## St.Louis7
Production Report for Partnering Agreement
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
St. John | All | 29.2 | 29.2 | 25.75 | 3.45 |  |  | 29.2
0
St. Louis Internat'l | All | 1.1 | 1.1 | 1.1 |  |  |  | 1.1
0
Black Jack | All | 42.2 | 42.2 | 4.52 | 26.16 | 11.52 |  | 42.2
0
Parker | All | 37.2 | 37.2 |  |  | 20.06 | 17.14 | 37.2
0
Pasadena | All | 31.6 | 31.6 |  |  |  | 31.6 | 31.6
0
Pine Lawn | All | 13.3 | 13.3 |  |  |  | 13.3 | 13.3
0
Delmar | All | 13.74 | 13.74 |  |  |  | 13.74 | 13.74
0
Woodson | All | 24.63 | 3.18 |  |  |  | 3.18 | 3.18 | Help finish Woodson
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 192.97 | 171.52 | 31.37 | 29.61 | 31.58 | 78.96 | 171.52
|  | Quarterly Goal |  | 40.15 | 41.67 | 40.63 | 49.07 | 171.52
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C43: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E42: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.