## St.LouisCityCounty
Production Report for Partnering Agreement
Date: 04/02/2005
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Schuetz | All | 56.4 | 5 | 5 |  |  |  | 5
Groby | All | 31.56 | 31.56 | 26.32 | 5.24 |  |  | 31.56
Larimore | Partial | 60.3 | 26.3 | 26 | 0.3 |  |  | 26.3
Gimblin | All | 16.9 | 16.9 | 12.25 | 4.65 |  |  | 16.9
Baden | All | 13.3 | 13.3 | 7 | 6.3 |  |  | 13.3
St. John | All | 29.2 | 29.2 | 25.75 | 3.45 |  |  | 29.2
St. Louis Internat'l | All | 1.1 | 1.1 | 1.1 |  |  |  | 1.1
Black Jack | All | 42.2 | 42.2 | 4.52 | 37.68 |  |  | 42.2
Hanley | Partial | 29.2 | 0.5 | 0.5 |  |  |  | 0.5
Dale | Partial | 16.49 | 5 | 5 |  |  |  | 5
Chouteau | All | 9.58 | 9.58 | 9.58 |  |  |  | 9.58
Ashley | All | 1.01 | 1.01 | 1.01 |  |  |  | 1.01
Hickory | All | 21.19 | 21.19 | 18.73 | 2.46 |  |  | 21.19
Midland | All | 34.77 | 34.77 | 2.76 | 32.01 |  |  | 34.77
Ashby | All | 26.38 | 26.38 |  | 15.3 | 11.08 |  | 26.38
Humboldt | All | 13.7 | 13.7 | 5 | 8.7 |  |  | 13.7
Bittner | All | 1 | 1 |  | 1 |  |  | 1
Prairie | All | 22.8 | 22.8 | 1 | 12.8 | 9 |  | 22.8
Dyer | All | 31.4 | 31.4 |  | 1.52 | 29.88 |  | 31.4
Pasadena | All | 31.6 | 31.6 |  |  | 12.75 | 18.85 | 31.6
Parker | All | 37.2 | 37.2 |  | 9.32 | 27.88 |  | 37.2
Vista | All | 5.93 | 5.93 | 5.93 |  |  |  | 5.93
Dougherty Ferry | All | 44.5 | 44.5 |  |  | 24.47 | 20.03 | 44.5
McPherson | All | 10 | 10 |  |  |  | 10 | 10
Duncan | All | 13.3 | 13.3 |  |  |  | 13.3 | 13.3
Folsom | All | 25.46 | 25.46 | 8.3 | 17.16 |  |  | 25.46
Delmar | All | 13.74 | 13.74 |  |  |  | 13.74 | 13.74
Hoover | All | 3.67 | 3.67 |  |  |  | 3.67 | 3.67
Pine Lawn | All | 13.3 | 13.3 |  |  |  | 13.3 | 13.3
Woodson | All | 24.63 | 24.63 |  |  |  | 24.63 | 24.63
Laclede | All | 8.97 | 8.97 |  |  |  | 8.97 | 8.97
Enright | All | 25.32 | 25.32 |  |  |  | 25.32 | 25.32
0
0
0
0
0
Total Miles = |  | 716.1 | 590.51 | 165.75 | 157.89 | 115.06 | 151.81 | 590.51
|  | Quarterly Goal |  | 152.89 | 143.36 | 121.99 | 172.27 | 590.51

## St.LouisCityCounty-
Production Report for Partnering Agreement
Date: 04/02/2005
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Castlewood | Partial | 48.17 | 8 | 8 |  |  |  | 8
0
Des Peres | All | 29.22 | 29.22 | 28.64 | 0.58 |  |  | 29.22
0
Fenton | All | 58.32 | 58.32 | 8.8 | 32.54 | 16.98 |  | 58.32
0
Bowles | All | 22.62 | 22.62 |  |  | 3.27 | 19.35 | 22.62
0
Valley Park | Partial | 52.89 | 24.16 |  |  |  | 24.16 | 24.16
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 211.22 | 142.32 | 45.44 | 33.12 | 20.25 | 43.51 | 142.32
|  | Quarterly Goal |  | 29.38 | 33.12 | 39.31 | 43.51 | 145.32

## St.LouisCityCounty1
Production Report for Partnering Agreement
Date: 04/02/2005
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Webster | Partial | 46.6 | 39.6 | 31.9 | 7.7 |  |  | 39.6
0
Yorkshire | All | 22.59 | 22.59 |  | 22.59 |  |  | 22.59
0
Telegraph | All | 54.15 | 54.15 |  | 1.5 | 45.55 |  | 47.05
0
Ripa | All | 17.38 | 17.38 |  |  |  | 17.38 | 17.38
0
Affton | All | 16.79 | 16.79 |  |  |  | 16.79 | 16.79
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 157.51 | 150.51 | 31.9 | 31.79 | 45.55 | 34.17 | 143.41
|  | Quarterly Goal |  | 34.27 | 29.42 | 45.55 | 34.17 | 143.41
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.

## St.LouisCityCounty2
Production Report for Partnering Agreement
Date: 04/02/2005
District: metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2004 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Sunset | partial | 28.3 |  | 4.14 |  |  |  | 1.06 | reflects 3.08 not reported in '04
0
Clydesdale | all | 19.42 | 0.34 | 19.08 |  |  |  | 19.08
0
Will | all | 35.48 |  | 24.55 | 10.93 |  |  | 35.48
0
Concord | all | 50.15 |  |  | 50.15 |  |  | 50.15
0
Sappington | all | 73.66 |  |  |  | 51.58 | 22.08 | 73.66
0
Tesson | all | 38.38 |  |  |  |  | 38.38 | 38.38
0
0
0
Total Miles = |  | 217.09 | 0.34 | 43.63 | 61.08 | 51.58 | 60.46 | 216.75
|  | Quarterly Goal |  | 54.9 | 50.15 | 51.58 | 60.46 | 217.09
Note on A9: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C22: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E21: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.