## Nelson-Koviak
Production Report for Partnering Agreement
2nd Q 2005 | [6 empty] | Contractor: ** ** |  |  | Date: 08/01/05
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
St. John | All | 29.2 | 29.2 | 25.75 | 3.45 |  |  | 29.2
0
St. Louis Internat'l | All | 1.1 | 1.1 | 1.1 |  |  |  | 1.1
0
Black Jack | All | 42.2 | 42.2 | 4.52 | 26.16 | 11.52 |  | 42.2 | 2.64 miles added due to switching
[8 empty] | 0 | after "the look" - on 215-54
Parker | All | 37.2 | 37.2 |  |  | 27.2 | 10 | 37.2
0
Pasadena | All | 31.6 | 31.6 |  |  | 12.75 | 18.85 | 31.6
0
Pine Lawn | All | 13.3 | 13.3 |  |  |  | 13.3 | 13.3
0
Delmar | All | 13.74 | 13.74 |  |  |  | 13.74 | 13.74
0
Woodson | All | 24.63 | 3.18 |  |  |  | 3.18 | 3.18 | Help finish Woodson
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 192.97 | 171.52 | 31.37 | 29.61 | 51.47 | 59.07 | 171.52
|  | Quarterly Goal |  | 40.15 | 41.67 | 40.63 | 49.07 | 171.52
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C43: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E42: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.
Note on M4: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles

## Nelson-Gettinger
Production Report for Partnering Agreement
2nd Q 2005 | [6 empty] | Contractor: ** ** |  |  | Date: 08/01/05
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Schuetz | 56,56 | 56.4 | 5 | 5 |  |  |  | 5 | Not completed in 2004
0
Groby | All | 31.56 | 31.56 | 26.32 | 4.76 | 0.48 |  | 31.56
0
Midland | All | 34.77 | 34.77 | 2.76 | 31.01 | 1 |  | 34.77
0
Ashby | All | 26.38 | 26.38 |  | 6.83 | 19.55 |  | 26.38
0
Dougherty Ferry | All | 44.5 | 44.5 |  |  | 24.47 | 20.03 | 44.5
0
Woodson | All | 24.63 | 24.63 |  |  |  | 19.95 | 19.95
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 218.24 | 166.84 | 34.08 | 42.6 | 45.5 | 39.98 | 162.16
|  | Quarterly Goal |  | 30.56 | 56.07 | 35.55 | 39.98 | 162.16
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C42: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E41: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.
Note on M4: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles

## Nelson-Hoffmiester
Production Report for Partnering Agreement
2nd Q 2005 | [6 empty] | Contractor: ** ** |  |  | Date:08/01/05
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Hanley | 1 | 29.2 | 0.5 | 0.5 |  |  |  | 0.5 | Carry over from 2004
0
Dale | 03,04 | 16.49 | 5 | 5 |  |  |  | 5 | Carry over from 2004
0
Chouteau | All | 9.58 | 9.58 | 9.58 |  |  |  | 9.58
0
Ashley | All | 1.01 | 1.01 | 1.01 |  |  |  | 1.01
0
Hickory | All | 21.19 | 21.19 | 18.73 | 2.3 | 0.16 |  | 21.19
0
Vista | All | 5.93 | 5.93 | 5.93 |  |  |  | 5.93
0
Folsom | All | 25.46 | 25.46 | 8.3 | 17.16 |  |  | 25.46
0
[8 empty] | 0 | Not part of partnering agreement -
[8 empty] | 0 | additional miles
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 108.86 | 68.67 | 49.05 | 19.46 | 0.16 | 0 | 68.67
|  | Quarterly Goal |  | 37.28 | 5 | 5.93 | 20.46 | 68.67
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C42: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E41: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.

## Nelson-Slover
[7 empty] | Contractor: ** ** |  |  | Date: 05/02/05
District: Metro
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Larimore | Partial | 60.3 | 26.3 | 26 | 0.3 |  |  | 26.3 | Not completed in 2004
0
Gimblin | All | 16.9 | 16.9 | 12.25 | 4.55 | 0.1 |  | 16.9 | New sub made from part of Baden
0
Baden | All | 13.3 | 13.3 | 7 | 6.21 | 0.09 |  | 13.3 | Two feeders left from original sub.
0
Humboldt | All | 13.7 | 13.7 | 5 | 7.64 | 1.06 |  | 13.7
0
Bittner | All | 1 | 1 |  | 1 |  |  | 1
0
Prairie | All | 22.8 | 22.8 | 1 | 20.73 | 1.07 |  | 22.8
0
Dyer | All | 31.4 | 31.4 |  |  | 31.4 |  | 31.4
0
McPherson | All | 10 | 10 |  |  | 10 |  | 10
0
Duncan | All | 13.3 | 13.3 |  |  |  | 13.3 | 13.3
0
Laclede | All | 8.97 | 8.97 |  |  |  | 8.97 | 8.97
0
Enright | All | 25.32 | 25.32 |  |  |  | 25.32 | 25.32
0
Hoover | All | 3.67 | 3.67 |  |  |  | 3.67 | 3.67
0
Woodson | Partial | 24.63 | 1.5 |  |  |  | 1.5 | 1.5 | Help finish Woodson
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 245.29 | 188.16 | 51.25 | 40.43 | 43.72 | 52.76 | 188.16
|  | Quarterly Goal |  | 44.9 | 40.62 | 39.88 | 62.76 | 188.16
Note on A5: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C43: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E42: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F3: E34432: 12kv and below overhead miles only.
Note on M3: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles

## Shade Tree-Still
Production Report for Partnering Agreement
[7 empty] | Contractor: ** ** |  |  | Date: | 2005-04-02
District: metro | [9 empty] | 005 schedule
Substation | Feeder No. | Total feeder miles | feeder miles 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Sunset | partial | 28.3 |  | 4.14 |  |  |  | 4.14 | reflects 3.08 not reported in '04
0
Clydesdale | all | 19.42 | 0.34 | 19.08 |  |  |  | 19.08
0
Will | all | 35.48 |  | 24.55 | 10.93 |  |  | 35.48
0
Concord | all | 50.15 |  |  | 45.21 | 4.94 |  | 50.15
0
Sappington | all | 73.66 |  |  |  | 51.58 | 22.08 | 73.66
0
Tesson | all | 38.38 |  |  |  |  | 38.38 | 38.38
0
0
0
Total Miles = |  | 217.09 | 0.34 | 47.77 | 56.14 | 56.52 | 60.46 | 220.89
|  | Quarterly Goal |  | 54.9 | 50.15 | 51.58 | 60.46 | 217.09
Note on A9: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C22: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E21: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.
Note on M4: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles

## Shade Tree-George
Production Report for Partnering Agreement
[7 empty] | Contractor: ** ** |  |  | Date: | 2094-09-03
District: |  | Total District Dist. Line Miles = |  |  |  | Projected cycle length based only on 2004 schedule
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Castlewood | Partial | 48.17 | 8 | 8 |  |  |  | 8
0
Des Peres | All | 29.22 | 29.22 | 28.64 | 0.58 |  |  | 29.22
0
Fenton | All | 58.32 | 58.32 | 8.8 | 46.29 | 3.23 |  | 58.32
0
Bowles | All | 22.62 | 22.62 |  | 5.97 | 16.65 |  | 22.62
0
Valley Park | Partial | 52.89 | 24.16 |  |  | 24.24 | 28.45 | 52.69
[7 empty] | need work | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 211.22 | 142.32 | 45.44 | 52.84 | 44.12 | 28.45 | 170.85
|  | Quarterly Goal |  | 29.38 | 33.12 | 39.31 | 43.51 | 145.32
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C42: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E41: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.
Note on M4: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles

## Shade Tree-Freeman
Production Report for Partnering Agreement
[7 empty] | Contractor: ** ** |  |  | Date:71105
District:
Substation | Feeder No. | Total feeder miles | Feeder Miles for 2005 | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR | Total feeder miles ytd | NOTES
Webster | Partial | 46.6 | 39.6 | 31.9 | 7.7 |  |  | 39.6
0
Yorkshire | All | 22.59 | 22.59 |  | 20.3 | 4.02 |  | 24.32 | actual=24.32 vs.22.59
0
Telegraph | All | 54.15 | 54.15 |  |  | 41.53 | 12.62 | 54.15 | missing 7.1 miles???
0
Ripa | All | 17.38 | 17.38 |  |  |  | 17.38 | 17.38
0
Affton | All | 16.79 | 16.79 |  |  |  | 5.79 | 5.79
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Miles = |  | 157.51 | 150.51 | 31.9 | 28 | 45.55 | 35.79 | 141.24
|  | Quarterly Goal |  | 34.27 | 29.42 | 45.55 | 34.17 | 143.41
Note on A6: E34432: Original Substation/miles agreed to at the beginning of the year as part of performance agreement. List Distribution miles first followed by any 34/69kv miles.
Note on C44: E20589: This is the quarterly mileage goal projected at the beginning of the year. These numbers remain constant for the year.
Note on E43: E20589: Need to put in scheduled line miles, by quarter. As year progresses this figure will go to actual and if needed, following quarter will be re-focasted with total miles for year in mind.
Note on F4: E34432: 12kv and below overhead miles only.
Note on M4: E34432: Distribution only: need to enter Total District Dist. Miles/Scheduled Distribution miles