## AMO
| TV-F1-2021 |  |  |  |  | Ameren MO Transmission Lines - 2021
Completed Work Listed By Miles Unless Otherwise Noted
[7 empty] | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line # | Line Name | ROW Name | Volt | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.34 | AU |  | Adair-Appanoose-2 |  | 161 | SG
25 | FD |  | Apache Flats-Mariosa Delta |  | 161 | SG | 25 | [8 empty] | 25 | [12 empty] | 2
14.9 | DN |  | Apache Flats-Sub Tap-1 (Barnett-California - 1 to Apache Flats) |  | 161 | SG | 15 | [8 empty] | 15
0.42 | DK |  | Ashley-Sub Tap - 2 (Cahokia-Venice-2 to Ashley) |  | 138 | TS | [20 empty] | 1
0.73 | EH |  | Baumgartner Sub Tap (Meramec-Watson - 2 to Baumgartner) |  | 138 | TS | [20 empty] | 1
43.24 | WA |  | Belleau-Montgomery-6 |  | 345 | SG | [22 empty] | 15 | 5
55.2 | FF |  | Belleau-Pike-1 |  | 161 | SG | [9 empty] | 55 | [12 empty] | 5 | 1
11.18 | EO |  | Big River-Rockwood |  | 138 | TS
13.5 | DS |  | Big River-Tyson 3 & 4 |  | 138 | TS | 13 | [19 empty] | 1 | 1
1.09 | EU |  | Blanchette-Sub Tap |  | 138 | TS | [20 empty] | 1
44.2 | BF |  | Bland-Franks-3 |  | 345 | RT | [10 empty] | 44
28.7 | QQ |  | Buck Knob-Rivermines-2 |  | 138 | RT | [22 empty] | 5
9 | O |  | Cahokia-Central 1 & 2 |  | 138 | TS | [20 empty] | 1
0.48 | AD |  | Cahokia-Meramec |  | 138 | TS | [22 empty] | 1 | 1
2.47 | CL |  | Cahokia-Popular-5 |  | 138 | TS
31.6 | CD |  | Callaway-Bland-1 (Paralleled Circuits) |  | 345 | SG | [20 empty] | 3 |  | 4 | 1
16.6 | FH |  | Callaway-Loose Creek |  | 345 | SG |  |  | 17 | [19 empty] | 3
1 | CO |  | Calumet-Sub Tap 3 & 4 (Pike-Dundee 3 & 4 to Calumet) |  | 161 | SG | [10 empty] | 1
3.23 | DO |  | Camden-Sub Tap - 2 (Camdenton - 2 - Lakeview to Camden) |  | 161 | SG |  |  | 3 | [17 empty] | 1 | 2 | 1
2.8 | Q |  | Campbell-Euclid - 4 (Partially Paralleled Circuits) |  | 138 | TS | [9 empty] | 0 | 0 | 0
3.2 | BX |  | Campbell-Maline-1 & 2 |  | 138 | TS | [20 empty] | 1
1.6 | BZ |  | Campbell-Sub Tap-4 (Cahokia-Roxford - 4 to Campbell) |  | 345 | TS | [20 empty] | 1 |  |  | 1
6.36 | UU |  | Cape-Joppa-1 - (MO side) |  | 161 | RT | [20 empty] | 2
6.1 | CS |  | Cape-Kelso - 2 East Line |  | 161 | RT | [21 empty] | 2
7.1 | CW |  | Cape-Kelso -3 (West line) |  | 161 | RT | [21 empty] | 2
4.5 | AF |  | Cape-Viaduct Tap |  | 138 | RT | [21 empty] | 1
19.2 | DL |  | Cape-Wedekind-2 |  | 161 | RT | [22 empty] | 2
8.5 | BP |  | Carbide-Sub Tap - 2 (Palmyra-Viele-2) |  | 161 | SG | [10 empty] | 9 | [9 empty] | 1
5.9 | AJ |  | Central-Watson-1 |  | 138 | TS | [9 empty] | 3 | [12 empty] | 0 | 1
24.1 | DT |  | Clark-Cominco-2 |  | 161 | RT | [22 empty] | 5
95.4 | AE |  | Clark-Osage-2 |  | 138 | RT | [22 empty] | 15
17.7 | PP |  | Clark-Pea Ridge 3 & 4 |  | 138 | RT | [12 empty] | 10 | 5 | 0 | 3 |  |  |  |  | 5 |  | 2
27.8 | EB |  | Clark-Pilot Knob-1 |  | 161 | RT | 28 | 0 | [11 empty] | 10 | 0 | 18 | [5 empty] | 2
46 | E |  | Conway-Tyson 3 & 4 |  | 138 | TS | [21 empty] | 1
3.5 | D |  | Dorsette-Sub Tap 4 |  | 138 | TS | [9 empty] | 2 | [10 empty] | 1 | 1 | 1
2 | AG |  | Dorsette-Sub Tap 8 |  | 138 | TS | [9 empty] | 2 | [11 empty] | 1
2.2 | ET |  | Dupo Ferry-Selma |  | 138 | RT
13.5 | DU |  | Fletcher-Cominco - 1 |  | 161 | RT | [22 empty] | 5
30.5 | EA |  | Fletcher-Pilot Knob - 2 |  | 161 | RT | [9 empty] | 30 | [11 empty] | 5 | 2 | 2
9.4 | DZ |  | Fletcher-Sweetwater - 3 |  | 161 | RT
0.9 | AH |  | Ft. Zumwalt-Sub Tap |  | 138 | TS
56.6 | AI |  | Gasco-Osage-2 |  | 138 | RT |  |  |  | 57 | [18 empty] | 15 | 4
12.13 | CG |  | General Motors-Sub Tap |  | 161 | SG
6.1 | R |  | Gray Summit-Franklin 1 & 2 |  | 138 | RT | [9 empty] | 6 | [11 empty] | 2
21.84 | EF |  | Gray Summit-Rockwood 3 & 4 |  | 138 | TS | 21 | [20 empty] | 1
14.2 | CP |  | Guthrie-Moreau-1 |  | 161 | SG | [23 empty] | 1
30.7 | CC |  | Guthrie-Overton-3 |  | 161 | SG | [23 empty] | 1
1.7 | DJ |  | Hall Street-Ashley 1 |  | 138 | TS
8.28 | FA | 4549 | Herlman-Maywood(Missouri) | ITC | 345 | SG | [10 empty] | 1 | [9 empty] | 2 |  | 1 | 0
16.5 | FE |  | Hughes-High Prairie Wind |  | 345 | SG | [23 empty] | 3
5.2 | BL |  | Hunter-Sub Tap 1 & 2 (Page-Mason 1 & 2 to Hunter) |  | 138 | TS | [21 empty] | 1
18.86 | HA |  | Joachim-St. Francis 1&2 |  | 138 | RT
5.14 | ES |  | Joppa-Kelso (MO side) |  | 345 | RT | [10 empty] | 0 | 6 | [10 empty] | 1
17.7 | EX |  | Kelso-Lutesville-1 |  | 345 | RT | [22 empty] | 1
19.1 | CT |  | Kelso-Miner-2 |  | 161 | RT | [9 empty] | 19 | [11 empty] | 2
29.41 | CX |  | Kelso-Stoddard-3 |  | 161 | RT | [9 empty] | 29 | [11 empty] | 7
40.2 | BE |  | Labadie-Bland-3 |  | 345 | RT | [10 empty] | 40
6 | AP |  | Labadie-Gray Summit-3 |  | 138 | TS | [9 empty] | 1 | [10 empty] | 1
50 | AS |  | Labadie-Montgomery-4 |  | 345 | RT |  | 50 | [8 empty] | 50 | [11 empty] | 1
60 | AV |  | Labadie-Tyson 1 & 2 |  | 345 | TS | [20 empty] | 1 | 2 | 1 | 1
0.25 | DP |  | Lathrop-Sub Tap (NW Electric Co-op to Lathrop) |  | 161 | SG
5 | J |  | Lemay-Sub Tap 1 & 2 (Cahokia-Meramec 1 & 2 to Lemay) |  | 138 | TS | [20 empty] | 1 | 1 |  | 1
37.29 | FI |  | Loose Creek-Franks-2 |  | 345 | RT |  |  | 37 | [17 empty] | 0 | 2
12 | FM |  | Loose Creek-Mariosa Delta |  | 345 | SG | [22 empty] | 1
13 | AK |  | Lutesville-Heritage |  | 345 | RT
63 | AQ |  | Lutesville-St. Francois-1 |  | 345 | RT | [10 empty] | 0 | 63 | [10 empty] | 5
9.6 | DD |  | Marion Tap-2 (Pike-Palymyra - 2 to Marion Sub) |  | 161 | SG | [10 empty] | 10 | [11 empty] | 1
8.3 | BV |  | Marshall-Lakeshire-4 |  | 138 | TS | [21 empty] | 1 | 2 | 1
8.2 | ED |  | Marshall-Sub Tap-1 (Central-Watson - 1 to Marshall) |  | 138 | TS | [9 empty] | 0 | 8 | [9 empty] | 1 | 2 | 1
14.6 | AW |  | Marshall-Tyson 1 & 2 |  | 138 | TS | [20 empty] | 1 |  | 1
11.16 | DH |  | Mason-Carrollton-8 |  | 138 | TS | [9 empty] | 1
26.3 | LL |  | Mason-Gray Summit 1 & 2 |  | 138 | TS | [20 empty] | 1 | 1 | 1 | 1
50 | AR |  | Mason-Labadie 3 & 4 |  | 345 | TS | [20 empty] | 1 | 1 | 1 | 1
11.17 | ER |  | Mason-McClay -9 |  | 138 | TS | [20 empty] | 1 | 1
47 | C |  | Mason-Meramec 1 & 2 |  | 138 | TS | [21 empty] | 1 | 3 | 1
26.9 | BQ |  | Mason-Sioux-7 |  | 345 | TS | [21 empty] | 1 |  | 1
3 | DQ |  | Maurer Lake Sub Supply (MO City-Carrollton to M. Lake) |  | 161 | SG | [21 empty] | 3
121.75 | I |  | Maywood-Hills |  | 345 | SG | [10 empty] | 122 | [9 empty] | 1 |  | 4 | 0
65 | FB |  | Maywood-Zachary | ITC | 345 | SG
5.3 | DC |  | McClay-Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to McClay) |  | 138 | TS | [20 empty] | 1 | 2
4.69 | F |  | Meramec-Baumgartner - 1 |  | 138 | TS | [20 empty] | 1 | 1 | 2 | 1
16.27 | H |  | Meramec-Joachim 1 & 2 |  | 138 | TS | [20 empty] | 1 | 1 | 5
13.9 | G |  | Meramec-Watson - 2 |  | 138 | TS | [9 empty] | 3 | [10 empty] | 1 | 1 | 1
18.6 | CR |  | Miller-Zion-1 |  | 138 | SG
10 | CV |  | Miner-Charleston-1 |  | 161 | RT | [20 empty] | 2
10 | CU |  | Miner-Sikeston-1 |  | 161 | RT | [20 empty] | 2
1.41 | AL |  | Mississippi-Sub Tap-1 & 2 MO |  | 138 | TS
46.44 | CB |  | Montgomery-Callaway 7 & 8 |  | 345 | SG | [9 empty] | 46 | [10 empty] | 2 |  | 2 | 0
38 | AT |  | Montgomery-Guthrie-3 |  | 161 | SG | [22 empty] | 4 | 2
64.7 | II |  | Montgomery-Maywood |  | 345 | SG | [10 empty] | 65 | [11 empty] | 3 | 0
64 | ZZ |  | Montgomery-Overton-5 |  | 345 | SG | [9 empty] | 0 | 64 | [11 empty] | 1 | 2
5 | EL |  | Moreau-Mariosa Delta |  | 161 | SG | [20 empty] | 3 | 5
1 | CF |  | O'Fallon Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to O'Fallon) |  | 138 | SG
52.26 | VV |  | Osage-Overton |  | 138 | SG
12.29 | AC |  | Outlaw Wind |  | 345 | SG
35.9 | BS |  | Overton-Moberly-1 |  | 161 | SG | [9 empty] | 0 | 36 | [9 empty] | 5 |  | 2
10.1 | BT |  | Overton-Sedalia-1 |  | 161 | SG |  |  | 10 | [6 empty] | 10 | [12 empty] | 3
2.5 | P |  | Page-Euclid-1 (Paralleled Circuits) |  | 138 | TS | [9 empty] | 0 | 0 | 0 | [10 empty] | 1
19.6 | A |  | Page-Mason 1 & 2 |  | 138 | TS | [9 empty] | 2 | 0 | 0 | [8 empty] | 1 | 1 | 1 | 1
21.6 | U |  | Page-Sioux-4 |  | 138 | TS | [20 empty] | 1 | 1 | 2 | 1
11.6 | B |  | Page-Warson 5 & 6 |  | 138 | TS | [9 empty] | 2 | 0 | 0
2.5 | BM |  | Palmyra Sub Supply - 1 (Montgomery Sub T-1 to Palmyra) |  | 345 | SG
6.2 | BN |  | Palmyra-North Marblehead-1 |  | 161 | SG | [10 empty] | 6
70 | BH |  | Palmyra-Viele-2 |  | 161 | SG | 35 | 35 | [8 empty] | 70 | [9 empty] | 10 |  |  | 4
16.4 | CN |  | Pike-Dundee 3 & 4 |  | 161 | SG |  |  | 16 | [7 empty] | 16 | [9 empty] | 1
40 | GG |  | Pike-Palmyra-2 |  | 161 | SG | [10 empty] | 40 | [9 empty] | 2 |  | 3
71 | TT |  | Rivermines-Cape-1 |  | 138 | RT | [22 empty] | 6 | 12
24.9 | NN |  | Rivermines-Clark-2 |  | 138 | RT |  |  | 25 | [18 empty] | 5 |  | 3
29.8 | SS |  | Rivermines-Taum Sauk 1 & 2 |  | 138 | RT | 4 | 26 | [19 empty] | 2 | 4
1.7 | EK |  | Rush Island-Holcim-1 (Distribution) |  | 345 | RT
17 | BO |  | Rush Island-St. Francois-1 |  | 345 | RT |  |  | 17 | [7 empty] | 17 | [12 empty] | 8
66.2 | BI |  | Rush Island-Tyson 1 & 2 |  | 345 | TS | [20 empty] | 1 | 2 | 1 | 1
11.9 | JJ |  | Salisbury-Moberly - 10 |  | 161 | SG | [20 empty] | 2 | 12 | 1
23.34 | W |  | Sioux-Belleau-6 |  | 345 | TS | [22 empty] | 1 | 1
32 | AB |  | Sioux-Maline 3 & 4 |  | 138 | TS | [9 empty] | 5 | [11 empty] | 1 | 0 | 1
4.82 | AO |  | Sioux-Meppen MO |  | 138 | TS | [21 empty] | 1
28.6 | AA |  | Sioux-Roxford 5 MO |  | 345 | TS | [21 empty] | 1 | 0 | 1
24.46 | EP |  | St. Francois-New Bourbon |  | 138 | RT | [9 empty] | 24 | [11 empty] | 4 | 1
10 | BC |  | St. Francois-Rivermines 1 |  | 138 | RT | [22 empty] | 2
10 | BC |  | St. Francois-Rivermines 2 |  | 138 | RT | [22 empty] | 2
10 | BC |  | St. Francois-Rivermines 3 |  | 138 | RT | [22 empty] | 2
1.04 | BD |  | St. Francois-Sub Tap-2 |  | 138 | RT
12.4 | CZ |  | Stoddard-Berntie - 1 (Includes Stoddard to Richland) |  | 161 | RT | [10 empty] | 0 | 12
6.25 | CQ |  | Tegeler-Explorer-1 |  | 138 | RT | [9 empty] | 6 | [11 empty] | 3
44.1 | AM |  | Thomas Hill-Adair-1 |  | 161 | SG | [23 empty] | 1
1.45 | CY |  | Trail of Tears-Charmin |  | 161 | RT | [22 empty] | 1
0 | EW |  | Troy sub Tap (C.E.P.C. owned) |  | 161 | SG
11.96 | AX |  | Tyson-Meramec-4 |  | 138 | TS | [21 empty] | 1 | 1 | 1
3.15 |  |  | Venice-Campbell 1 |  | 138 | TS
3.91 | BW |  | Venice-Campbell-1 & 2 MO |  | 138 | TS | [20 empty] | 1 | 1
4.56 | YY |  | Wedekind-Sub Tap-1 |  | 161 | RT | [21 empty] | 2 | 1
11.36 | AN |  | Wedekind-Trail of Tears |  | 161 | RT | [22 empty] | 5
31.03 | FC | 5944 | Zachary-Ottumwa | ITC | 345 | SG
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [5 empty] | Totals | 141 | 111 | 125 | 57 | 0 | 0 | 0 | 0 | 0 | 286 | 599 | 81 | 10 | 15 | 0 | 21 | 0 | 0 | 0 | 0 | 68 | 94 | 166 | 68
[29 empty] | 1Q | 219
[29 empty] | 2Q | 506
Radial Taps | [28 empty] | 3Q | 890
[29 empty] | 4Q | 227
1842
Note on AD6: Graham, Sharon K: work identified from 2021 patrol
Note on D8: Strauss, Anthony D: includes Cahokia - Ashley 2 (MO Side) and Ashley - Venice 2 (MO Side)
Note on D9: Strauss, Anthony D: Meramec Watson from str 40 to Baumgartner
Note on AD10: Graham, Sharon K: work identified from 2021 patrol
Note on AE10: Graham, Sharon K: work found from 2021 patrol
Note on AD11: Graham, Sharon K: work identified in 2021 patrol
Note on AE11: Graham, Sharon K: work found from 2021 patrol
Note on AC13: Strauss, Anthony D: Helicopter cleanups
Note on D14: Strauss, Anthony D: Includes Mason-McClay from str 53 to Blanchette
Note on AE18: Strauss, Anthony D: work completed at request of Meramec power plant
Note on D19: Strauss, Anthony D: Includes Cahokia Russell 2 & 4 (MO side). Includes Cahokia Gratiot str 6 to Gratiot sub. Includes Cahokia - Central Str 9-1010-1011-Gratiot
Note on J21: Graham, Sharon K: trimmed due to availability of helicopter saw
Note on J23: Graham, Sharon K: trimmed due to availability of helicopter saw
Note on AD23: Graham, Sharon K: work identified in 2021 patrol
Note on Q24: Strauss, Anthony D: RR Poles Only Str 8-29 pushed back to qtr 3 due to permitting issues
Note on R24: Strauss, Anthony D: pushed back to q4 due to permitting issues
Note on S24: Strauss, Anthony D: non priority work moved to q1 2022
Note on D26: Strauss, Anthony D: Includes Cahokia Roxford from str 1150 to Campbell sub
Note on AE26: Strauss, Anthony D: work completed due to accessability
Note on Q33: Strauss, Anthony D: RR Poles only 46-23
Note on AD33: Strauss, Anthony D: non prioirity work moved to q4
Note on T36: Thurman, Ralph E: Only 10 miles was completed in 1st quarter due to weather
Note on U36: Thurman, Ralph E: Only 5 miles was completed in 2nd quarter due to weather
Note on V36: Thurman, Ralph E: Non priority work was pushed to 4th Qtr. Due to mower availability
Note on AD36: Thurman, Ralph E: Work identified on 2021 patrol
Note on H37: Thurman, Ralph E: Work was completed ahead of schedule due to helicopter availbility
Note on U37: Thurman, Ralph E: Only 10 miles was completed in 2nd quarter due to weather
Note on V37: Thurman, Ralph E: Non priority work was pushed to 4th Qtr. Due to mower availability
Note on D38: Porcelli, Jennifer L: Includes portion of Marshall-Tyson
Note on AC38: Strauss, Anthony D: prioirty work discovered on 2021 patrol, reclamation project
Note on D39: Strauss, Anthony D: Includes Warson - Mason from str 57 to Dorsette sub. Includes Mason - Carrolton from Dorsette sub to str 129
Note on Q39: Strauss, Anthony D: RR Poles Only 80-118
Note on AC39: Strauss, Anthony D: Work completed due to availability of crews.
Note on AD39: Strauss, Anthony D: permitted removals
Note on Q40: Strauss, Anthony D: RR Poles only 148-129
Note on AD43: Thurman, Ralph E: Work identified on 2021 patrol
Note on AE43: Thurman, Ralph E: Work identified on 2021 patrol
Note on K46: Thurman, Ralph E: Trimmed per capital project
Note on AE46: Thurman, Ralph E: Crew cleaning up debris per capital project
Note on D47: Graham, Sharon K: includes Belleau-GM-3 and GM-Point Prairie-3
Note on AC49: Strauss, Anthony D: Helicopter skips
Note on AE50: Graham, Sharon K: work found from 2021 patrol
Note on AE51: Graham, Sharon K: work found from 2021 patrol
Note on R53: Graham, Sharon K: sprayed island due to spray crew being on island for other line
Note on AD53: Graham, Sharon K: work completed in 3rd quarter due to crew availability
Note on AE54: Graham, Sharon K: work found from 2021 patrol
Note on D55: Strauss, Anthony D: Includes Page-Mason from Str 22 to Hunter sub. Includes Central - Watson str 55-2056-1079. Includes Marshall Lakeshire from structure 1079 to Hunter sub
Note on R57: Thurman, Ralph E: work was completed in early 4th Qtr. Due to weather
Note on AD57: Thurman, Ralph E: Work identified on 2021 patrol
Note on AD58: Thurman, Ralph E: Work identified on 2021 patrol
Note on AD63: Thurman, Ralph E: Work identified on 2021 patrol
Note on AB64: Strauss, Anthony D: Work completed due to availability of crews
Note on AC64: Strauss, Anthony D: Capital Project, priority work found on 2021 patrol
Note on AD64: Strauss, Anthony D: priority work found on 2021 patrol
Note on AE64: Strauss, Anthony D: priority work found on 2021 patrol
Note on D66: Strauss, Anthony D: Includes Meramec-Watson from Mackenzie Switch to str 86
Note on AC66: Strauss, Anthony D: customer complaint
Note on AE66: Strauss, Anthony D: Work completed on capital
Note on J67: Thurman, Ralph E: This was scheduleduled for 2022 but was able to move up due to helicopter availibilty.
Note on AB67: Thurman, Ralph E: Work was moved to 2nd qtr. for foliar spray.
Note on AD68: Graham, Sharon K: work identified in 2021 patrol
Note on R70: Thurman, Ralph E: work was completed in early 4th Qtr. Due to weather
Note on AD70: Thurman, Ralph E: Work identified on 2021 patrol
Note on AD71: Graham, Sharon K: work identified in 2021 patrol
Note on D72: Strauss, Anthony D: Str 37A to Lakeshire sub
Note on AE72: Strauss, Anthony D: permitted removals
Note on D73: Strauss, Anthony D: Includes Central - Watson and Marshall - Lakeshire from Marshall to str 1079
Note on Q73: Strauss, Anthony D: Pushed back to Qtr 3 due to permitting issues
Note on AD73: Strauss, Anthony D: priority work found on 2021 patrol
Note on AB74: Strauss, Anthony D: work completed due to availability of crews
Note on AD74: Strauss, Anthony D: Jaraffe cleanup
Note on D75: Strauss, Anthony D: Includes Mason - Carrolton and Carrollton Sioux from str 52 to carrolton sub
Note on Q75: Strauss, Anthony D: RR Poles Only 1056-1064
Note on D76: Strauss, Anthony D: only includes isolated section of Mason Gray Summit from str 98 to 327
Note on AB76: Strauss, Anthony D: Non priority reclamation work completed in cooperation with customer
Note on AD76: Strauss, Anthony D: priority work found on 2021 patrol
Note on AE76: Strauss, Anthony D: priority work found on 2021 patrol
Note on D77: Strauss, Anthony D: Includes Mason-Wildwood and Wildwood - Gray Summit from wildwood sub to Str 98
Note on AB77: Strauss, Anthony D: Priority work addressed due to crew availability
Note on AC77: Strauss, Anthony D: Priority work found on 2021 patrol
Note on AD77: Strauss, Anthony D: priority work found on 2021 patrol
Note on AE77: Strauss, Anthony D: priority work found on 2021 patrol
Note on AB78: Strauss, Anthony D: Normally flooded area addressed due to access
Note on AE79: Strauss, Anthony D: priority work found on 2021 patrol
Note on D80: Strauss, Anthony D: Includes Mason Carrolton from Mason Sub to str 52. Includes Carrolton - Sioux from Sioux to str 52.
Note on AC80: Strauss, Anthony D: Priority work found on 2021 patrol
Note on AE80: Strauss, Anthony D: priority work found on 2021 patrol
Note on AD82: Graham, Sharon K: work completed in 3rd quarter due to crew availability additional work found on 2021 patrol
Note on A83: Paries, Dieter E: approximate mileage,once line is in service will get true miles
Note on D85: Strauss, Anthony D: Includes Baumgartner Watson from Baumgartner to str 54
Note on AB85: Strauss, Anthony D: Work completed due to availability of equipment
Note on AE85: Strauss, Anthony D: priority work found on 2021 patrol
Note on D86: Porcelli, Jennifer L: Includes Meramec-Sandy Creek and Sandy Creek-St. Francois
Note on AC86: Strauss, Anthony D: permitted removals, work on concerned customers property
Note on D87: Strauss, Anthony D: Includes Baumgartner Watson from str 54 to Watson
Note on Q87: Strauss, Anthony D: RR Poles Only 100-132
Note on AB87: Strauss, Anthony D: addressed Hazard tree
Note on AC87: Strauss, Anthony D: non priority work completed due to availability of crews
Note on AD87: Strauss, Anthony D: Captial work
Note on D91: Strauss, Anthony D: Includes Sioux - Roxford 1 & 2 from str 51 to 57
Note on AD92: Graham, Sharon K: work completed in 3rd quarter due to crew availability
Note on AD93: Graham, Sharon K: work identified from 2021 patrol
Note on AE93: Graham, Sharon K: work found from 2021 patrol
Note on D94: Graham, Sharon K: include Montgomery-Spencer Creek, Spencer Creek-Maywood
Note on AD94: Graham, Sharon K: work completed in 3rd quarter due to crew availability
Note on Q95: Graham, Sharon moved to 3rd quarter due to rain
Note on AD95: Graham, Sharon K: work started in 3rd quarter due to crew availability
Note on D98: Graham, Sharon K: includes: Osage Plant-Osage Sub (4 circuits), Osage-Eldon, Eldon-Barnett, Barnett-California, California-Overton
Note on D99: Paries, Dieter E: not yet in service
Note on Q100: Graham, Sharon K: moved to 3rd quarter due to rain
Note on AD100: Graham, Sharon K: work identified in 2021 patrol
Note on J101: Graham, Sharon K: trimmed due to availability of helicopter saw
Note on AD101: Graham, Sharon K: work identified in 2021 patrol
Note on Q102: Strauss, Anthony D: RR Poles Only str 26-4 Delayed to q3 due to permitting issues
Note on R102: Strauss, Anthony D: pushed back to q4 due to permitting issues
Note on S102: Strauss, Anthony D: non priority work moved to q1 2022
Note on D103: Strauss, Anthony D: Includes Warson - Mason
Note on Q103: Strauss, Anthony D: RR Poles Only 3-56 part of lines pushed back to q3 due to permitting issues
Note on R103: Strauss, Anthony D: pushed back to q4 due to permitting issues
Note on S103: Strauss, Anthony D: non priority work moved to q1 2022
Note on AB103: Strauss, Anthony D: permitted removals
Note on AE103: Strauss, Anthony D: priority work found on 2021 patrols
Note on D104: Strauss, Anthony D: Runs from Page to str 50 on Mason - Sioux.Includes Page - Berkeley and Berkeley - Sioux
Note on AB104: Strauss, Anthony D: Addressed complaint on Ameren owned property
Note on AE104: Strauss, Anthony D: addressing complaints on ameren owned property
Note on Q105: Strauss, Anthony D: RR Poles Only 3-39A Part of spraying pushed back to q3 due to permitting issues
Note on R105: Strauss, Anthony D: pushed back to q4 due to permitting issues.
Note on S105: Strauss, Anthony D: non priority work moved to q1 2022
Note on I108: Graham, Sharon K: finished in 1st quarter due to AS starting early
Note on AE108: Graham, Sharon K: work found from 2021 patrol
Note on J109: Graham, Sharon K: trimmed due to availability of helicopter saw
Note on AD110: Graham, Sharon K: work identified from 2021 patrol
Note on AD111: Thurman, Ralph E: Work identified on 2021 patrol
Note on AE111: Thurman, Ralph E: Crew hotspot trimming with Jaraffe
Note on J112: Thurman, Ralph E: This was scheduleduled for 2022 but was able to move up due to helicopter availibilty.
Note on AE112: Thurman, Ralph E: Work identified on 2021 patrols
Note on H113: Thurman, Ralph E: 4 miles was completed ahead of schedule due to helicopter availability
Note on AD113: Thurman, Ralph E: Work identified on 2021 patrol
Note on J115: Thurman, Ralph E: This was scheduleduled for 2022 but was able to move up due to helicopter availibilty.
Note on AE115: Thurman, Ralph E: Crew removing totems left by helicopter
Note on D116: Porcelli, Jennifer L: Includes portion of Rush Island Subtap
Note on AB116: Strauss, Anthony D: Work completed in cooperation with concerned customer
Note on AC116: Strauss, Anthony D: priorities found on 2021 patrol, reclamation project
Note on AD116: Strauss, Anthony D: priority work found on 2021 patrol
Note on AE116: Strauss, Anthony D: priority work found on 2021 patrol
Note on AD117: Graham, Sharon K: work identified from 2021 patrol
Note on AD118: Strauss, Anthony D: vines on pole
Note on AE118: Strauss, Anthony D: priority work found on 2021 patrol
Note on Q119: Strauss, Anthony D: RR Poles Only 43-90
Note on AD119: Strauss, Anthony D: Non Priority Work moved to Q4
Note on D120: Strauss, Anthony D: Includes Sioux - Meppen North 4 From str 176E to Str 146. Includes Out of Service lines from 146 to 122
Note on AC120: Strauss, Anthony D: Capital project
Note on D121: Strauss, Anthony D: Runs from Sioux to str 77. Includes Sioux - Roxford 1 & 2
Note on AC121: Strauss, Anthony D: work moved up due to dry conditions and availability of crews
Note on AE121: Strauss, Anthony D: priority work found on 2021 patrol
Note on AD122: Thurman, Ralph E: Work identified on 2021 patrol
Note on R127: Thurman, Ralph E: work was completed in early 4th Qtr. Due to weather
Note on AE129: Graham, Sharon K: work found from 2021 patrol
Note on D132: Porcelli, Jennifer L: Includes Tyson-Arnold and Arnold-Meramec
Note on AC132: Strauss, Anthony D: work completed after working with customer.
Note on AD132: Strauss, Anthony D: permitted removals
Note on AE132: Strauss, Anthony D: work completed after meeting with customer.
Note on D134: Strauss, Anthony D: Include Venice - Campbell from st 2020 to Campbell. Includes Venice Hall st from str 2020 to 1020
Note on AB134: Strauss, Anthony D: Capital Work
Note on AD135: Thurman, Ralph E: Work identified on 2021 patrol