## AUE
| TV-F1-2010 |  | AmerenUE Transmission Lines - 2010
Completed Work Listed by Miles Unless Otherwise Noted - (Red is Scheduled/Black is Completed)
|  |  |  | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line Name | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
4.74 | CJ | Arnold-Meramec - 3 | PV
19.6 | A | Page-Mason 1 & 2 | PV | [21 empty] | 0 | 2 | 1
28.6 | AA | Sioux-Roxford 1,2 & 5 - MO (345KV) | PV
32 | AB | Sioux-Maline 3 & 4 | PV | [8 empty] | 32
2.5 | AD | Lemay Tap - 2 (Meramec-Watson - 2 to Lemay) (Paralleled Circuits) | PV
3 | AH | Cahokia-Russell - 2 | PV
5.9 | AJ | Central-Watson - 1 | PV | [8 empty] | 6
6 | AP | Labadie-Gray Summit - 3 | PV | [21 empty] | 1
50 | AR | Mason-Labadie 3 & 4 (345KV) | PV | [12 empty] | 50 | [8 empty] | 2 | 3
60 | AV | Labadie-Tyson 1 & 2 (345KV) | PV | [12 empty] | 60 | [7 empty] | 1 | 2 | 2
14.6 | AW | Marshall-Tyson 1 & 2 | PV | [8 empty] | 14.6
11.96 | AX | Tyson-Meramec - 4 | PV
6.1 | R | Gray Summit-Franklin 1 & 2 | RT
| AY | Venice-Campbell - 1 (Partially Paralleled Circuits) | PV
11.6 | B | Page-Warson 5 & 6 | PV | [8 empty] | 6 | 6
8 | BG | Warson-Mason 3 & 4 | PV
66.2 | BI | Rush Island-Tyson 1 & 2 (345KV) | PV | [21 empty] | 1
63.5 | W | Sioux-Montgomery - 6 (345KV) | CW |  | 64 | 0 | [6 empty] | 0 | 64 |  |  | 10 |  |  | 0 | 34 | 30 |  | 0 | 6
15.01 | Y | Sioux-Huster - 1 | CW
15.01 | Z | Sioux-Huster - 3 | CW
3.5 | BJ | Dorsette Sub Tap - 8 (Mason-Carrollton-8 to Dorsett) | PV | [21 empty] | 1 | 0 | 1
5.3 | BB | Huster-Belleau 1 & 3 | CW
30.7 | CC | Guthrie-Overton - 3 (161KV) | CW | [12 empty] | 8 | 22.7 | [5 empty] | 31 |  |  |  | 3
9.6 | DD | Marion Tap - 2 (161KV) (Pike-Palymyra - 2 to Marion Sub) | CW | [15 empty] | 9.6 | [5 empty] | 1
| EE | Marion Tap - 4 (Sioux-South Quincy-4 to Marion Sub) | CW
55.2 | FF | Belleau-Pike - 1 (136/161KV) | CW | [16 empty] | 0 | 0 | 0 | 35 | 3
40 | GG | Pike-Palmyra - 2 (161KV) | CW | [22 empty] | 3
27.5 | II | Montgomery Spencer Creek (345KV) | CW | [21 empty] | 1
11.9 | JJ | Salisbury-Moberly - 10 (161KV) | CW | [21 empty] | 2
14.9 | KK | Barnett-California - 1 (161KV) | CW | [9 empty] | 0 | 17 | [11 empty] | 3
6.7 | BK | Rush Islands Sub Tap -2 (Selma-Rivermines-2 to Rush Island) | PV
204 | MM | Rivermines-Maires - 1 | RT
60 | NN | Rivermines-Clark - 2 | RT | 26 |  | 0
35 | OO | Maries-Osage - 1 (138KV) | RT
17.7 | PP | Clark-Pea Ridge 3 & 4 | RT
5.2 | BL | Hunter Sub Tap 1 & 2 (Page-Mason 1 & 2 to Hunter) | PV | [21 empty] | 1 | 1
59.6 | SS | Rivermines-Taum Sauk 1 & 2 | RT | [12 empty] | 52 | 8
71 | TT | Rivermines-Cape - 1 (138/161KV) | RT
1.8 | VV | Osage Plant-Osage Sub (Four Circuits) | CW
26.9 | BQ | Mason-Sioux - 7 (345KV) | PV
5 | UU | Cape-Joppa-1 (161KV) MO side | RT |  | 5 | [11 empty] | 5 | [7 empty] | 5
4.3 | YY | Wedekind Sub Supply - 1 (161KV) (Rivermines-Cape - 1 to Wedekind) | RT | [9 empty] | 4 | 0
64 | ZZ | Montgomery-Overton-5 (345KV) | CW | [14 empty] | 0 | 5 |  |  | 0 | 64 | 2
8.3 | BV | Marshall-Lakeshire - 4 | PV
| BW | Venice-Campbell - 2 | PV
35 | AE | Clark-Osage - 2 (138KV) | RT
170 | AG | Montgomery-Sub T - 1 (345KV) | CW | [12 empty] | 0 | 0 | 0 | 15 |  | 8 |  |  | 5
3.2 | BX | Campbell-Maline - 1 | PV | [8 empty] | 3.2
56.3 | AI | Gasco-Osage - 2 (138KV) | RT
6.94 | BY | Campbell-Maline - 2 | PV | [8 empty] | 6.94
18.21 | AK | Franklin-Tegeler - 1 (138KV) | RT
44.1 | AM | Thomas Hill-Adair - 1 (161 KV) | CW | 44 | 0 | [21 empty] | 2
10.2 | AN | Trail of Tears Supply - 1 (161KV) (Rivermines-Cape - 1 to Trail of Tears) | RT | [9 empty] | 10 | 0
1.6 | BZ | Campbell Sub Tap - 4 (345KV) (Cahokia-Roxford - 4 to Campbell) | PV
63 | AQ | Lutesville-St. Francois - 1 (345KV) | RT | [21 empty] | 0 | 10
47 | C | Mason-Meramec 1 & 2 | PV | [12 empty] | 0 | 0 | 16 | 31 |  | 47
50 | AS | Labadie-Montgomery - 4 (345KV) | RT | [21 empty] | 10
38 | AT | Montgomery-Guthrie - 3 (161KV) | CW | [21 empty] | 2
32 | AU | Adair-Wapello - 2 (161KV) | CW |  | 0 | 0 | [20 empty] | 2
3 | CA | Cahokia-Russell - 4 | PV
7.18 | CI | Tyson-Arnold - 3 | PV
2.47 | CL | Cahokia-Popular - 5 | PV
2.8 | CM | Cahokia-Gratiot - 3 | PV
30 | BC | St. Francois-Rivermines 1 & 2 & 3 | RT | [9 empty] | 29 | 1 | [9 empty] | 5 | 4 | 1
1.1 | BD | St. Francois Sub Tap - 2 (Selma-Rivermines - 2 to St. Francois) | RT | [20 empty] | 1
84 | BE | Labadie-Bland - 3 (345KV) | RT | [15 empty] | 84 | [5 empty] | 10 | 0
36 | BF | Bland-Franks - 3 (345KV) | RT | [21 empty] | 7 | 0
3.5 | D | Dorsett Sub Tap-4 (Warson-Mason-4 to Dorsett) | PV | [21 empty] | 1 | 1 | 0
96.9 | BH | Palmyra-Viele - 2 (161KV) | CW | [10 empty] | 0 |  |  |  | 0 | 12 |  |  |  |  | 0 | 2
0.06 | DE | Gratiot Sub Tap 1 & 3 (Cahokia-Central - 1 to Gratiot) | PV
11.16 | DH | Mason-Carrollton - 8 | PV
14.79 | DI | Carrollton-Sioux - 8 | PV
| DJ | Ashley Tap - 1 (Venice-Cambell -1 to Ashley ?) | PV
2.4 | BM | Palmyra Sub Supply - 1 (345KV) (Montgomery Sub T-1 to Palmyra) | CW | [23 empty] | 1
6.2 | BN | Palmyra-North Marblehead - 1(161KV) | CW | [23 empty] | 1
17 | BO | Rush Island-St. Francois - 1 (345KV) | RT | [20 empty] | 8
8.5 | BP | Carbide Sub Supply - 2 (161KV) (Palmyra-Viele-2 to | CW | [20 empty] | 0 | 1
| DK | Ashley Tap - 2 (Cahokia-Venice-2 to Ashley ?) | PV
12.2 | BR | Osage-Eldon - 1 (161KV) | CW | [9 empty] | 0 | 12 | [11 empty] | 1
35.9 | BS | Overton-Moberly - 1(161KV) | CW | 36 | 0 | [19 empty] | 2
10.1 | BT | Overton-Sedalia - 1 (161KV) | CW | 10 | [22 empty] | 1
6.74 | BU | Point Prairie-Big Creek - 3 (161KV) | CW
13.5 | DS | Big River-Tyson 3 & 4 | PV
46 | E | Conway-Tyson 3 & 4 | PV
8.7 | EC | Hunter Sub Tap - 4 (Marshall-Lakeshire - 4 to Hunter) | PV
8.2 | ED | Marshal Sub Tap - 1 (Central-Watson - 1 to Marshall) | PV
21.84 | EF | Gray Summit-Rockwood 3 & 4 | PV | [12 empty] | 21.84 | [10 empty] | 0
9.57 | EG | Baumgartner-Watson - 1 | PV
46.44 | CB | Montgomery-Callaway 7 & 8 (345KV) | CW | [21 empty] | 2
31.6 | CD | Callaway-Bland - 1 (345KV) (Paralleled Circuits) | CW | 32 | 0 | [7 empty] | 0 | 32 | [9 empty] | 1
1 | CF | O'Fallon Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to O'Fallon) | CW
12.13 | CG | Belleau-GM - 3 (138/161KV) | CW
16.9 | CH | Sub T-Hills - 1 (345KV) | CW | [13 empty] | 0 | 3 | 14 |  |  |  | 17 | 0 | 3
0.73 | EH | Baumgartner Sub Tap (Meramec-Watson - 2 to Baumgartner) | PV
11 | EJ | McClay-Mason | PV
8.86 | CK | GM-Point Praire - 3 (161KV) | CW
12.65 | EM | Meremac Sandy Creek | PV
24.71 | EN | Sandy Creek St.Francios | PV
16.4 | CN | Pike-Dundee 3 & 4 (161KV) | CW | 16 | [9 empty] | 16 | [11 empty] | 1
1 | CO | Calumet Sub Tap 3 & 4 (161KV) (Pike-Dundee 3 & 4 to Calumet) | CW | [10 empty] | 1
14.2 | CP | Guthrie-Moreau - 1 (161KV) | CW | [20 empty] | 0 | 1
6.25 | CQ | Tegeler-Explorer - 1(138KV) | RT
18.6 | CR | Miller-Zion-1 (138KV) | CW
6.1 | CS | Cape-Kelso - 2 (161KV) East Line | RT
18.9 | CT | Kelso-Miner - 2 (161KV) | RT | [13 empty] | 19
9.5 | CU | Miner-Sikeston - 1 (161KV) | RT | [9 empty] | 10 | 0
10.1 | CV | Miner-Charleston - 1 (161KV) | RT | [9 empty] | 10 | 0
7.1 | CW | Cape-Kelso -3 (161KV) West line | RT
29.3 | CX | Kelso-Stoddard - 3 (161KV) | RT |  | 29 | 0
5.3 | CY | Stoddard-Richland - 3 (161KV) | RT
12.4 | CZ | Stoddard-Berntie - 1(161KV) | RT
24.78 | DA | Big Creek-Montgomery -3 (161KV) | CW
0.57 | DB | Esther Sub Tap - 1 (Ste. Genevieve-Rivermines - 1 to Esther) | RT
5.3 | DC | McClay Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to McClay) | CW
11.17 | ER | Mason McClay -9 | PV
0.96 | DF | Eldon-Barnett - 1 (161KV) | CW | [23 empty] | 1
22.4 | DG | California-Overton - 1 (161KV) | CW | [9 empty] | 0 | 22 | [12 empty] | 2
1.09 | EU | Blanchette sub tap | PV
4.69 | F | Meramec-Baumgartner - 1 | PV | [20 empty] | 1
13.9 | G | Meramec-Watson - 2 | PV | [8 empty] | 13.9 |  |  |  | 13.9 | [7 empty] | 3 |  | 2
34 | H | Meramec-St. Francois 1 & 2 | PV | [20 empty] | 10 |  |  | 3
8 | DL | Cape-Wedekind - 2 (161KV) | RT
14.9 | DN | Apache Flats Tap - 1 (161KV) (Barnett-California - 1 to Apache Flats) | CW | 15 | [20 empty] | 2
3.23 | DO | Camden Sub Tap - 2 (161KV) (Camdenton - 2 - Lakeview to Camden) | CW | [14 empty] | 3 | [5 empty] | 0 | 1
0.25 | DP | Lathrop Sub Tap (161KV) (NW Electric Co-op to Lathrop) | CW | [13 empty] | 1
3 | DQ | Maurer Lake Sub Supply (161KV) (MO City-Carrollton to M. Lake) | CW | [13 empty] | 3 | [9 empty] | 1
54 | FH | Callaway-Franks - 2 (345KV) | CW | [22 empty] | 3
25 | FD | Apache Flats - Mariosa Delta (161KV) | CW | 25 | [15 empty] | 0 | 1 |  |  |  |  | 1
12 | FM | Loose Creek - Mariosa Delta (345KV) | CW | 12 | [20 empty] | 1
75.27 | DR | Tegeler-Osage - 1 | RT
5 | J | Lemay Tap 1 & 2 (Cahokia-Meramec 1 & 2 to Lemay) | PV | [12 empty] | 0 | 0 | 3 | [6 empty] | 1 | 1
21.2 | DT | Clark-Cominco - 2 (161KV) | RT
12.8 | DU | Fletcher-Cominco - 1 (161KV) | RT | [14 empty] | 0 | 2 |  |  |  |  | 6
0.7 | DV | Buick Mine Sub Tap - 1 (161KV) (Fletcher-Cominco -1 to Buick Mine) | RT | [20 empty] | 1
0.7 | DW | Buick Mine Sub Tap - 2 (161KV) (Clark-Cominco - 2 to Buick Mine) | RT | [20 empty] | 1
0.7 | DX | Buick Smelter Sub Tap - 1 (161KV) (Fletcher-Cominco -1 to Buick Smelter) | RT | [20 empty] | 1
0.7 | DY | Buick Smelter Sub Tap - 2 (161KV) (Buick Mine Sub Tap - 2 to Buick Smelter) | RT | [20 empty] | 1
9.4 | DZ | Fletcher-Sweetwater - 3 (161KV) | RT
30.5 | EA | Fletcher-Pilot Knob - 2 (161KV) | RT | [14 empty] | 11 | 20
27.8 | EB | Clark-Pilot Knob - 1 (161KV) | RT
26.3 | LL | Mason-Gray Summit 1 & 2 | PV | [15 empty] | 26
9 | O | Cahokia-Central 1 & 2 | PV
2.5 | P | Page-Euclid - 1 (Paralleled Circuits) | PV | [8 empty] | 0 | 2.5
2.8 | Q | Campbell-Euclid - 4 (Partially Paralleled Circuits) | PV | [8 empty] | 0 | 3
27.5 | QQ | Buck Knob-Selma-Rivermines - 2 (Partially Paralleled Circuits) | PV
0.06 | EI | Wallen Creek Sub Tap (Rivermines-Maries - 1 to Wallen Creek) | RT
14 | S | Page-Berkeley 1 & 2 | PV
| T | Page-Keokuk - 3 (110KV) | PV
21.6 | U | Page-Sioux - 4 | PV
24.46 | EP | St Francios-New Bourbon | RT
29.2 | V | Berkeley-Sioux 1 & 2 | PV
1.4 | XX | Crystal Sub Tap - 1 | PV
5.3 | EV | McClay -Belleau | CW
0 | EW | Troy sub Tap (C.E.P.C.) owned 161 kv | CW
| ES | Joppa-Kelso (345KV) MO side | RT | [23 empty] | 5
17.7 | EX | Kelso-Lutesville-1 (345kv) | RT | [23 empty] | 7
|  | Viaduct Tap from Cape-Kelso (110KV) | RT
17 | EY | Rush St.Francios - 2 (345kv) | RT | [20 empty] | 8
|  | Sytem totals |  | 216 | 98 | 0 | 0 |  |  |  |  | 82.64 | 74.5 | 165 | 0 | 205.74 | 68.7 | 36 | 218.6 | 0 | 90 | 30 | 147 | 58 | 73 | 35 | 31
3211.78 |  |  | TOTALS |  |  |  | 314 |  |  |  | 0 |  |  |  | 322.14 |  |  |  | 529.04 |  |  |  | 267 |  |  |  | 197
Follow up ground crew to be charged to aerial trimming, not tree crew work.
[26 empty] | TOTAL | 1629.18
Note on C9: e42362: ref Lemay Tap 1 & 2 for work and miles
Note on C19: e42362: Hotspot trimming included with Page Mason
Note on C20: e42362: ref Page-Mason for mileage
Note on C92: e42362: Ref Meramec-Watson for miles and work
Note on C101: e42362: Mowing and Hotspot miles on Meramec-St Francois
Note on C102: e42362: Mowing and Hotspot miles included on Meramec St Francios
Note on C145: e42362: hotspot included with Mason Labadie Gray Summit to Rockwood
Note on C156: e91489: This line has been removed
Note on E37: e91489: This was completed in the 1st quarter because of helicopter availability
Note on F45: e91489: This was not on the schedule but bumped up as A Sol. cost per mile came in under estimated costs on another line.
Note on F56: Chad Warren: Miles completed ahead of schedule in 1st qtr
Note on F63: Chad Warren: Will be unable to work due to budget constraints; non priority work
Note on F84: Chad Warren: Miles completed ahead of schedule in 1st qtr
Note on F94: Chad Warren: Miles completed ahead of schedule in the 1st qtr
Note on F113: e91489: This was completed in the 2nd qtr. We were trying a new vendor and they were able to get started earlier sooner than scheduled.
Note on G22: Chad Warren: Miles completed ahead of schedule in 2nd quarter
Note on G37: e91489: This was completed in the 1st quarter due to helicopter availability
Note on G63: Chad Warren: Chad Warren: Will be unable to work 32 miles due to budget constraints; non-priority work; will carry over to 2011 aerial trimming work
Note on M19: E42362: 6 miles not complete due access restriction from Terminal RR will complete in April
Note on M147: E42362: delays due to access from Terminal RR
Note on M148: E42362: delays due to Terminal RR
Note on N22: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N34: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N46: e91489: Work was completed in the 2nd Qtr. Work completed sooner than scheduled
Note on N57: e91489: Work was completed in the 2nd Qtr. Work completed sooner than scheduled
Note on N68: e91489: Work was completed in the 2nd Qtr. Work completed sooner than scheduled
Note on N83: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N94: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N110: e91489: Work was completed in the 2nd Qtr. Work completed sooner than scheduled
Note on N111: e91489: Work was completed in the 2nd Qtr. Work completed sooner than scheduled
Note on N121: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on O73: Chad Warren: 70 miles taken off spray list for 2010 due to budget overruns; will work in 2011, non priority work
Note on Q27: Chad Warren: 8 of 31 total mow miles for this line have been completed ahead of schedule. Work pushed up due to priority. Remaining work will be completed in 2nd qtr
Note on Q41: e91489: 52 miles of the 60 were completed in the 1st quarter crew as was pulled off to follow the helicopter and to help with priority 2 work. Will complete in 2nd Q.
Note on Q51: Chad Warren: Work not completed in 1st qtr due to inaccessibiltiy from inclement weather; work anticipated to be completed in 2nd qtr; non priority work
Note on Q60: e26073: area has been wet and is flooded at this time, will get in second quarter.
Note on Q135: e26073: too wet, to mow at this time will get in second quarter
Note on R22: Chad Warren: Reclamation mowing work only. Approximately 60 total spans of work.
Note on R51: Chad Warren: Reclamation and valley mow work; close to 100 spans total reclamation mowing; unable to work due to flood condtions; will work in third quarter; non priority work
Note on R60: E42362: area has been wet and is flooded at this time can wait until the third quarter, no priority work.
Note on R97: Chad Warren: Unable to mow this area due to flood conditions; work will be performed in third quarter; non priority work
Note on R135: e26073: mower was broke for 3 weeks, expect work to be complete in July
Note on S47: Chad Warren: No-Spray locations for mow work; 3 spans of border zone reclamation; not complete in third quarter; mower being shared with other MO supervisor, non priority
Note on S51: Chad Warren: not completed in third quarter due to sharing of mower with other supervisors in MO, non priority
Note on S60: E42362: mowing is started not complete, high water is still an issue on some parts of the line. Non priority work.
Note on S73: Chad Warren: Border zone reclamation mow work; approximately 72 spans slated for mowing; not completed in third quarter due to sharing of mower with other MO supervisors, non priority work.
Note on S97: Chad Warren: Partial completion in third quarter; rest of work to be performed in fourth quarter, non priority work
Note on S137: e91489: This will be mowed in the 4th qtr.crew is mowing from Pilot Knob to Fletcher and then from Fletcher to Cominco, non priority work.
Note on T70: e91489: This line does not need mowed after patrolling, no work needed at this time
Note on T137: e91489: Crew mowed 2 miles in 2010 and will finish in 1st Qtr.2011. Fletcher Pilot Knob line slowed the crew down due to major hand cutting because of steep terrain; non-priority work.
Note on U22: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on U30: Chad Warren: Work not completed in 1st qtr due to customer refusals and permission/easement issues; anticipated work in 2nd qtr; non priority work
Note on U132: Chad Warren: Work not yet completed due to availability of specialty equipment (ATAB); anticipated to work in 2nd qtr
Note on V22: Chad Warren: This portion of 64 total miles completed in second quarter; rest will be worked in third quarter; non priority work
Note on V30: Chad Warren: Work not completed in second quarter due to discovery of other priority work; will be worked in third quarter; non priority work
Note on V51: Chad Warren: Several spans of reclamation work completed; approximately 50 spans of work total
Note on V60: E42362: Line was orginally scheduled to be hot spotted and not maint trimmed
Note on V132: Chad Warren: Specialty work completed; several spans of reclamation; 6 spans total
Note on W22: Chad Warren: Completed remaining work left from second quarter
Note on W30: Chad Warren: Work not completed in third quarter due to discovery of other priority work; will be worked in fourth quarter; non priority work
Note on W47: Chad Warren: Not completed in third quarter due to discovery of other priority work; non-priority
Note on X30: Chad Warren: 20 Miles of non-priority work will be carried over into 2011; inclement weather prevented completion of all identified trimming work.
Note on Y22: Chad Warren: Work not completed in 1st qtr due to flooded, inclement weather and inaccessibility; anticipated completion in 2nd qtr
Note on Y68: e91489: All priority 2 work was completed in 1st quarter and crew has to go back and finish priority 3 work
Note on Y73: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on Y81: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on Y97: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on Y105: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on Y125: e42362: miliage includes work on Meramec-Sandy Creek and Sandy Creek-St Francois
Note on Y128: Chad Warren: Work not completed in 1st qtr due to inclement/flooded areas and weather; anticipated work for 2nd qtr
Note on Z6: e42362: Includes ROW miles for Page-Warson and Warson-Mason -Wk is for 34.5 crews working on 345 lines
Note on Z70: e91489: This was patrolled in March and moved up on the schedule.
Note on Z71: e91489: This was patrolled in March and moved up on the schedule.
Note on AA25: E42362: switched with Dorsett sub tap 4 sch for 4th qtr due to priority wk needed on Dorsett Sub Tap 4
Note on AA59: e91489: Priority 3 work to be completed in third quarter.Work has been completed.
Note on AA68: e91489: Priority 3 work to be completed in third quarter.Work has been completed.
Note on AB6: e42362: Includes ROW Miles for Page-Warson and Warson to Mason
Note on AB72: E42362: completed 3rd qtr switched with Dorsett sub tap 8.
Note on AB91: E42362: prop owner agreed to do bulldozer work in Jan 2011, non-priority work.

## ACIPS
AMERENCIPS TRANSMISSION LINES - 2010
Completed Work Listed By Miles Unless Otherwise Noted - (Red is Scheduled/Black is Completed)
|  |  |  | Aerial Side Trimming Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line Name | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
47.65 | A | W. Frankfort-Joppa (230KV) | KDE | [22 empty] | 0 | 5
1.89 | B | Palmyra-N. Marblehead (161KV) | TJM | [21 empty] | 1
41.37 | C | Macomb Northeast-Niota (138KV) | TJM | [20 empty] | 0 | 3
31 | D | Meredosia East - Roodhouse West | TJM | [20 empty] | 0.5 | 2.5
28.24 | E | Roodhouse West - Jerseyville Northwest | TJM | [20 empty] | 3
0.65 | F | Meredosia - Meredosia East Lines 1,2,3,4 | TJM | [20 empty] | 1
26.22 | G | Mattoon West - Kansas West | JRW
53.93 | H | Pawnee West - Jerseyville Northeast | TJM | 53.93 | [11 empty] | 0 | [7 empty] | 2 | 1 | 0 | 1.5
0.28 | I | Coffeen P.P. - Coffeen North | KDE | [22 empty] | 0 | 0.28
16.66 | J | Grand Tower - Carbondale Northwest | KDE | [21 empty] | 0.25 | 1.25
27.58 | K | Carbondale Northwest - W. Frankfort | KDE | [21 empty] | 3
5.25 | L | W. Frankfort - W. Frankfort East | KDE | [9 empty] | 5.25
20.2 | M | W. Frankfort East - Muddy | KDE |  | 20.2
20.49 | N | Newton - Louisville South | KDE | [21 empty] | 0 |  | 2
45.44 | O | Hutsonville - Neoga South | KDE |  | 45.44
34.2 | P | Neoga South - Pana North | KDE | [10 empty] | 34.2
12.91 | Q | Pana North - Taylorville South | JRW | [20 empty] | 1
8.45 | R | Taylorville South - Taylorville Northeast | JRW | [17 empty] | 8 | 0 | 1
18 | S | Taylorville South - Pawnee West | TJM | 18 | 0 | [20 empty] | 0 | 1.5
7.86 | T | Pawnee West - Auburn North | TJM | [9 empty] | 6 | 1 | 1 | [10 empty] | 1
29.09 | U | Auburn North - Jacksonville Ind. Park, I.P. | TJM | [9 empty] | 15 | 13 | 1 | [9 empty] | 1 | 0.1 | 1.9
18.79 | V | Jacksonville Ind. Park, I.P. | TJM | [10 empty] | 18.79 | [11 empty] | 0.1 | 1
33.66 | W | Hutsonville - Kansas West | JRW | [17 empty] | 32 | 1.66 |  | 3
18.98 | X | Kansas West - Murdock | JRW | [22 empty] | 2
15.02 | Y | Kansas West - Paris South | JRW | [10 empty] | 1 | [6 empty] | 14 | 1 |  | 2
15.46 | Z | Murdock - Sidney, I.P. | JRW
30.53 | AA | Sidney, I.P. - Paxton East | JRW | [10 empty] | 31 | [9 empty] | 3 |  |  | 3
16.5 | BB | Rantoul - Rising, I.P. | JRW | [22 empty] | 2
16.79 | CC | Paxton East - Gibson City South | JRW | [20 empty] | 2
86.55 | DD | Meredosia East - Quincy (North Line No. 1) | TJM | [12 empty] | 1 | 0 | 1 | [6 empty] | 1 | 0.1 | 7.9
10.21 | EE | W. Frankfort - Benton Northwest | KDE | 0 | 10.21 |  |  |  |  | 10.21 | [5 empty] | 3.21
13.16 | FF | Benton Northwest - Ina | KDE | 13.16 | [5 empty] | 13.16 | [5 empty] | 0 | 13.16
11.04 | GG | Ina - Mt. Vernon 42nd St., I.P.(note Ip tap at structure 763) Same Circuit as HH | KDE | 11.04 | [5 empty] | 11.04
3.14 | HH | Mt. Vernon 42nd St., I.P. - Mt. Vernon West, I.P.(Structure 763 to MT Vernon IP sub) | KDE | 3.14 | [5 empty] | 3.14
31.06 | II | Mt. Vernon West, I.P. - Ramsey East | KDE |  |  |  | 31.06 | [19 empty] | 3
18.43 | JJ | Ramsey East - Pana North | KDE | [23 empty] | 2
22 | KK | Vermilion, I.P. - Hoopeston | JRW | [17 empty] | 22
20.88 | LL | Hoopeston - Paxton East | JRW | [10 empty] | 0 | 21 | [8 empty] | 2
41.31 | MM | Meredosia East - Ipava South | TJM | [21 empty] | 2 | 3
21.41 | NN | Ipava South - Macomb West | TJM | [21 empty] | 5
2.82 | OO | Macomb West - Macomb Northeast | TJM | [22 empty] | 1
21.94 | PP | Newton - Effingham | KDE | [9 empty] | 21.94 | [10 empty] | 1 |  |  | 1
13.36 | QQ | Effingham - Neoga South | KDE |  | 13.36
14.2 | RR | Neoga South - Mattoon West | JRW | [10 empty] | 0 | 10 | [7 empty] | 14 | 1 |  |  | 1
40.8 | SS | Mattoon West - Murdock | JRW | [20 empty] | 4
30.54 | TT | Grand Tower - Marion South | KDE | [6 empty] | 0 | [14 empty] | 2.75 | 0.25
9.1 | UU | Marion South - Crab Orchard | KDE | 9.1
19.11 | VV | Crab Orchard - Muddy | KDE | 19.11
13.91 | WW | Grand Tower - Steelville, I.P. | KDE | [12 empty] | 3.5 | [9 empty] | 2
12.51 | XX | Hutsonville - Robinson (Marathon Oil) | KDE |  | 12.51 | [8 empty] | 12.51 | [11 empty] | 1 | 0
34.32 | YY | Robinson - Newton | KDE |  | 34.32 | [7 empty] | 34.22 | [10 empty] | 0 | 2.5 | 0.5
21.63 | ZZ | Robinson - Lawrenceville South | KDE | [21 empty] | 1 | 1 | 0
22.8 | AB | Lawrenceville South - Olney North | KDE |  | 22.8
22.5 | AC | Olney North - Louisville South | KDE | [10 empty] | 22.5 | [9 empty] | 1 |  | 1.5
9.89 | AD | Lawrenceville South - Vincennes, I.P. | KDE | [22 empty] | 0 | 1
14.07 | AE | Havana, I.P. - Ipava South | JRW | [20 empty] | 1 |  |  | 1
21.18 | AF | Ipava South - Canton South | JRW | [18 empty] | 0 | 0
11.63 | AG | Canton South - I.P. Interconnection | JRW |  | 12 | [18 empty] | 1
11.29 | AH | W. Frankfort East - Herrin East | KDE |  |  |  | 11.29 | [18 empty] | 1 | 0
13.19 | AI | Herrin East - Crab Orchard | KDE | [22 empty] | 1.5 | 0
45.43 | AJ | Meredosia - East Quincy (South Line No. 2) | TJM | [12 empty] | 1 | 0 | 1 | [7 empty] | 1 | 0
28.01 | AK | Olney North - Albion South | KDE | [20 empty] | 1 |  | 1
39.87 | AL | Albion South - Norris City North | KDE
23.14 | AM | Norris City North - Muddy | KDE |  | 23.14
3.37 | AN | I.P. Tap - Moweaqua North | JRW
5.72 | AO | I.P. Tap - Blue Mound North | JRW
37.31 | AP | Paxton East - Watseka | JRW | [20 empty] | 4 |  | 1
14.55 | AQ | Watseka - Goodland | JRW | [22 empty] | 1
6.48 | AR | E. Quincy - Quincy South | TJM | [21 empty] | 1
4.6 | AS | Quincy South - N. Marblehead | TJM | [21 empty] | 1
4.35 | AT | N. Marblehead - Quincy, 3rd & Jefferson | TJM | [21 empty] | 1
32.44 | AU | Joppa - Marion South (161KV) | KDE | [6 empty] | 32.44 | [14 empty] | 3.25
23.42 | AV | Joppa - Mound City West (161KV) | KDE | 23.42 | [5 empty] | 23.42
30.4 | AW | Coffeen - Pana North (345KV) | KDE | [21 empty] | 3
22.34 | AX | Coffeen North - Ramsey East (345KV) | KDE | [20 empty] | 1 |  | 0 | 1
30.45 | AY | Ramsey East - Neoga South (345KV) | KDE | [20 empty] | 1.5 |  | 0 | 1.5
21.13 | AZ | Neoga South - Casey West (345KV) | KDE | [21 empty] | 2
27.45 | BA | Casey West - Breed, I.M.P.C. Indiana (345KV) | KDE | [23 empty] | 3
6.11 | BC | Com. Ed., Kincaid - Pawneed West (345KV) | TJM | 6.11 | 0 | [18 empty] | 1 | 1
16.97 | BD | Shawnee, TVA - W. Frankfort East (345KV) | KDE | [21 empty] | 1.5
26.54 | BE | Newton - Casey West (345KV) | KDE | [22 empty] | 2.5 | 0
21.16 | BF | Casey West - Kansas West (345 KV) | JRW | [23 empty] | 2
27.81 | BG | Newton - Mt. Vernon, I.P. (345KV) | KDE | [23 empty] | 2.75
9.46 | BH | Ipava South - Duck Creek, Cilco (345KV) | JRW
17.25 | BI | Albion South - Gibson, P.S. Indiana (345KV) | KDE | [21 empty] | 3
33.1 | BJ | W. Frankfort East - Norris City North (345KV) | KDE | [20 empty] | 0 | 2.3 | 1
2.84 | BK | Gibson City S-Gibson City PP | JRW
0 | BL | Joppa,E.E.I -Joppa (161kv) | KDE
27.6 | BM | Louisville,south - Kinmundy | KDE | [21 empty] | 1.5 | 1.3 | 0
29.5 | BN | Kinmundy - Ramsey East | KDE |  |  |  | 29.5 | [18 empty] | 1.5 | 1.5
0.26 | BO | Grand Tower - perryville | KDE
40.3 | UU | Cape-Joppa - 1 (161KV) | KDE | [20 empty] | 4
7.6 | AO | Shawnee-Joppa - 1 (345KV) | KDE | [21 empty] | 0.76
32.6 | ES | Joppa - Kelso 345kv | KDE | [6 empty] | 32.6 | [16 empty] | 3
36.4 | I | Cahokia-Meramec 1 & 2 | TJM | [20 empty] | 0 | 0 | 3
0 | K | Cahoka-Dupo Ferry - 1 (Paralleled Circuits) | TJM
88.9 | L | Cahokia-West Frankfort - 1 (230KV) | TJM | [10 empty] | 58.76 |  | 2 | [7 empty] | 4 | 0.5 | 0.5 | 2
3.2 | M | Cahokia-Ridge 1& 2 | TJM | [10 empty] | 3.2 | [10 empty] | 0 | 0 | 1
4.5 | N | Cahokia-Venice 1 & 2 | TJM | [10 empty] | 4.5 |  | 2.5 | 2 | [7 empty] | 0 | 0 | 0.75
| AA | Sioux-Roxford 1 & 2 - IL | TJM | [20 empty] | 0 | 1
1 | WW | Laclede Steel Supply - 1 (1436) & 2 (1456) | TJM | [22 empty] | 1
17.6 | AC | Cahokia-Roxford - 4 (345KV) (Partially Paralleled Circuits) | TJM | [10 empty] | 17.6 | [9 empty] | 1 |  | 0 | 0
5 | AL | Venice-Ridge - 4 | TJM | [10 empty] | 5 | [10 empty] | 0 | 0 | 0
1 | AY | Venice-Campbell - 1 (Partially Paralleled Circuits) | TJM | [10 empty] | 1 | [10 empty] | 0 | 1
1 | BA | Mississippi Sub Supply 1 & 2 (Sioux-Roxford 1 & 2 to Mississippi) | TJM | [21 empty] | 0 | 1
1 | BW | Venice-Campbell - 2 | TJM | [10 empty] | 1 | [10 empty] | 1
30.3 | CE | Dupo Ferry-Buck Knob - 1 (Paralleled Circuits) | TJM | [20 empty] | 1 | 1 | 0 | 1
0.9 | DM | Mississippi Sub 3rd Supply (Laclede - 1 (1436) to Mississippi) | TJM | [22 empty] | 1
32.6 | ET | Pickney ville -w.Frankfort 230kv | KDE | [20 empty] | 2 |  | 0 | 1.25
143.5 | T | Page-Keokuk - 3 (110KV) | TJM
7 | EE | MARION TAP - 4 (Sioux S.Quincy to River) | TJM | [20 empty] | 1
87.43 | X | Sioux-South Quincy - 4 | TJM | [9 empty] | 0 | 87.43 | [9 empty] | 2 | 2 | 4
30.5 | HH | East Quincy-Hamilton - 4 | TJM | [9 empty] | 0 | 30.5 | [11 empty] | 0 | 2
6.48 | AF | South Quincy-East Quincy - 4 | TJM | [9 empty] | 0 | 6.48 | [9 empty] | 2 | 1
|  | System Totals |  | 157.01 | 193.98 | 0 | 71.85 | 0 | 0 | 126.01 | 0 | 0 | 82.41 | 349.47 | 33 | 13.21 | 15.16 | 2 | 0 | 0 | 76 | 2.66 | 15 | 54 | 53.81 | 41.1 | 55.83
2480.94 |  |  | Totals |  |  |  | 422.84 |  |  |  | 126.01 |  |  |  | 464.88 |  |  |  | 30.37 |  |  |  | 93.66 |  |  |  | 204.74
[26 empty] | TOTAL | 1342.5
Follow up ground crew to be charged to aerial trimming, not tree crew work | [23 empty] | 224.22 | 421.36 | 521.24 | 175.68
Note on E23: E34686: COMPLETED IN 1ST QUARTER BECAUSE HELICOPTER FINISHED TO PAWNEE
Note on E35: e26073: This line has been postponed to 2nd qtr, because of notification; no priority work, can wait.
Note on E83: E34686: COMPLETED IN 1ST QUARTER BECAUSE HELICOPTER FINISHED TO PAWNEE
Note on H39: e79753: This line was moved up from 2011 schedule due to other 2010 aerial trim work being completed sooner than anticipated.
Note on H63: e79753: This line was moved up from 2011 schedule due to other 2010 aerial trim work being completed sooner than anticipated.
Note on H94: e79753: This line was moved up from 2011 schedule due to other 2010 aerial trim work being completed sooner than anticipated.
Note on K50: e79753: This line was entered in error, it will not be sprayed in 2010, hotspot work completed.
Note on N16: e79753: Work was completed prior to scheduled date.
Note on N24: E34686: IN PROGRESS - TOWNSEND WILL FINISH IN 2ND QUARTER - BASAL WILL BE DONE IN 4TH
Note on N46: e79753: Work was completed prior to scheduled date.
Note on N55: e79753: Work was completed prior to scheduled date.
Note on N116: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N117: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on N118: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on O29: e29513: This line scratched from list. Was done by air in 2009. Tree crew cut what little was left by hand.
Note on O42: e29513: This work was not done do to late start by contractor, non priority work.
Note on O48: e29513: This work was not done due to late start by contractor, non priority work.
Note on P48: e29513: Approximately 4 miles of foliage work (non-priority) left for 2011,crew did all basal work
Note on Q12: E34686: SPRAY SKIPS RE-EVALUATED AND WON'T DO - WILL HOT SPOT INSTEAD
Note on Q34: E34686: MOWING CEDAR VALLEY & KNOWN SPRAY SKIPS DIDN'T FINISH DUE TO WEATHER WILL DO IN 2ND Q.
Note on Q36: e79753: Work was not complete due to weather, mower could not do work without tearing up ROW. No priority work here.
Note on Q65: E34686: MOWING CEDAR VALLEY & KNOWN SPRAY SKIPS DIDN'T FINISH DUE TO WEATHER WILL BE BACK IN EARLY MAY
Note on Q101: E34686: MOWING OLIVE STANDS AS PER CUSTOMER
Note on Q103: E34686: DIDN'T FINISH DUE TO RIVER COMING UP WILL COMPLETE IN 2ND QUARTER
Note on R34: e26073: Working with NWTF to complete, no priority work.
Note on R65: e26073: Working with NWTF to complete, no priority work.
Note on V22: e29513: Approximately one mile is underwater, will finish in 3Q if possible no priority work left
Note on V27: e29513: Lack a little bit being done, will finish work in 3q, no priority work left
Note on V29: e29513: Lack a little bit being done, will finish work in 3Q, no priority work left
Note on W22: e29513: Crew was working on priority work. Did not get to this non priority work. Will move to 4Q.
Note on W61: e29513: Crew was working on priority work. Did not get to this non priority work will do in 4Q.
Note on X61: e29513: crew did not get to routine maintenance (non-priority) because of doing priority work found on 2010 patrols
Note on Y7: e26073: Moved to 2nd Q due to P1 work as this was not priority work.
Note on Y8: e26073: Will complete the P3's in the 2nd Q, as not an immediate priority.
Note on Y46: e79753: Priority 2 work complete, priority 3 work will be completed later in year.
Note on Y55: e79753: This line postponed - line will be aerial trimmed in 2nd qtr. And work will be completed then, no priority work.
Note on Y58: e79753: Priority 2 work complete, priority 3 work will be completed later in year.
Note on Y66: e79753: Priority 2 work complete, priority 3 work will be completed later in year.
Note on Y79: e79753: Priority 2 work complete, priority 3 work will be completed later in year.
Note on Y80: e79753: Priority 2 work complete, priority 3 work will be completed later in year.
Note on Y90: e79753: Work postponed to 2nd qtr because higher priority work on other lines, no priority work.
Note on Y99: E34686: Will complete in the 2nd Q due to other priority work as this work can wait.
Note on Y104: E34686: Moved to 2nd Q due to other priority work as this work can wait.
Note on Y113: e79753: Priority 2 work is complete, priority 3 work will be completed later in year.
Note on Z14: e79753: Work was begun in the last part of 2nd qutr and will be completed in 3rd qtr. Crew is working on this line.
Note on Z18: e79753: This work has been postponed until 4th qtr. To perform higher priority work on other lines.
Note on Z50: e79753: Crew is completing bucket work on this line and will be complete early in 3rd qtr.
Note on Z55: e79753: Crew is still working on this line and will complete in early 3rd qtr.
Note on Z56: e79753: Not all the work has been completed, priority 3 work has been re-scheduled for the 4th qtr.
Note on Z90: e79753: Crew is still working on line but remainder of work will be completed in 3rd. Qtr.
Note on Z93: e79753: Priority 3 work has not been completed it has been postponed until 4th qtr.
Note on Z99: E34686: Will complete in the 3Rd Q due to other priority work as this work can wait.
Note on Z102: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 3RD QUARTER.
Note on Z103: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 3RD QUARTER.
Note on Z107: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 3RD QUARTER.
Note on Z108: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 3RD QUARTER.
Note on Z109: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 3RD QUARTER.
Note on AA5: e79753: Work has been postponed until 4th qtr. At this time ground patrol will be done and crew can utilize notes, non priority work.
Note on AA12: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA13: E34686: NON PRIORITY WORK, CAN BE DONE IN 4th QUARTER.
Note on AA23: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA25: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA26: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA28: e29513: Priority work found on 2010 patrol
Note on AA32: e29513: priority work found on 2010 patrol
Note on AA34: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA71: e29513: Priority work found on 2010 patrol
Note on AA72: e29513: Priority work found on 2010 patrol
Note on AA79: e79753: Work has been postponed until 4th qtr. At this time ground patrol will be done and crew can utilize notes, non priority work.
Note on AA80: e79753: Work has been postponed until 4th qtr. At this time ground patrol will be done and crew can utilize notes, non priority work.
Note on AA102: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA103: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA106: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA107: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA111: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AA113: e79753: Work has been postponed until 4th qtr. At this time ground patrol will be done and crew can utilize notes, non priority work.
Note on AA117: E34686: NO PRESSING PRIORITY WORK CAN BE DONE IN 4th QUARTER.
Note on AB26: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AB31: e29513: Priority work found on 2010 patrol
Note on AB48: e29513: priority work found on 2010 patrol
Note on AB54: e26073: Was able to complete ahead of schedule, in 3rd Q.
Note on AB56: e26073: Was able to complete ahead of schedule, in 3rd Q.
Note on AB60: e29513: priority work found on 2010 patrol
Note on AB63: e26073: Was able to complete ahead of schedule, in 3rd Q.
Note on AB64: e26073: Was able to complete ahead of schedule, in 3rd Q.
Note on AB65: e44348: NON-PRIORITY WORK, RE-SCHEDULED FOR 1ST QUARTER 2011
Note on AB85: e26073: Was able to complete ahead of schedule, in 3rd Q.
Note on AB86: e29513: priority work found on 2010 patrols
Note on AB102: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AB106: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AB107: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AB111: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011

## AIP
AMEREN IP TRANSMISSION LINES - 2010
Completed Work Listed by Miles Unless Noted Otherwise - (Red is Scheduled/Black is Completed)
[5 empty] | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Trimming Maintenance |  |  |  | Trimming Hotspot
Circuit Miles | Alpha Code | IP Line # | Line Name | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
0.19 |  | 1302 | UNION ELECTRIC CO.-DUPO FERRY ROAD | TJM
10 |  | 1302A | AMEREN/UE LINE TO NEW VALMEYER SUB. | TJM | [9 empty] | 0 | 10 | [9 empty] | 2 | 0.5
50.68 | V | 1306 | C.I.P.S.-JACKSONVILLE INDUSTRIAL PARK - 138 KV LINE 1 | TJM | [21 empty] | 1 | 1
14.64 | RA | 1312 | SIDNEY-CHAMPAIGN S.W. CAMPUS | JRW | [9 empty] | 0 | 0 | 15 | [8 empty] | 1 | 1
1.95 | RA | 1312A | WINDSOR ROAD SUBSTATION SPUR LINE | JRW
20.06 | RB | 1313 | NORTH DECATUR - CLINTON RT. 54 - 138 KV LINE 1313 | JRW | [19 empty] | 20 | 2 |  | 2
24.9 | GG | 1322 | MT. VERNON 42ND ST. - WEST FRANKFORT - 138 KV LINE 13 | KDE
3.72 | GG | 1322A | WALTONVILLE SHELL PUMPING STA. SPUR - 138 KV LINE 132 | KDE
2.7 | GG | 1322C | NASON POINT-CONSOL COAL 138 KV L1322C SPUR | KDE
7.28 | RC | 1326 | SOUTH BLOOMINGTON - RAAB ROAD SW. STA. 138 KV LINE 13 | JRW | [17 empty] | 7
0.83 | RC | 1326A | DIAMOND STAR SPUR - 138 KV LINE 1326A | JRW
3.96 | HH | 1336 | MT. VERNON 42ND. ST. SPUR - 138 KV LINE - 1336 | KDE
32.89 | RD | 1342 | NORTH DECATUR - WEST ILLIOPOLIS - 138 KV LINE 1342 | JRW | [16 empty] | 3 | 30
0.18 | RD | 1342 T | STR. 174 - BORDEN SUB. - TAP FOR LINE 1342 - 138 KV | JRW
0.98 | RD | 1342A | LATHAM SPUR - 138 KV LINE - 1342A | JRW
8.58 | RD | 1342C | TURRIS COAL CO SPUR | JRW
51.07 | RE | 1346 | WEST MASON CITY - NORTH DECATUR - 138 KV LINE - 1346 | JRW | [9 empty] | 0 | 51 | [6 empty] | 2 | 4 | 0 |  |  | 2
0.38 | RE | 1346 T | STR. 466 - LATHAM SUB. - IP'S TAP FOR LINE 1346 - 138 KV | JRW
82.84 | RF | 1352 | HAVANA P.S. - BLOOMINGTON OLD DANVERS RD. LINE 1352 | JRW | [19 empty] | 0 | 8 |  | 2
14.91 |  | 1356 | HAVANA P.S. - IPAVA (C.I.P.S.) - 138 KV LINE 1356 | JRW | [23 empty] | 1
53.9 | RG | 1362 | HAVANA P.S. - GALESBURG MONMOUTH BLVD. - 138 KV LINE | JRW | [16 empty] | 7 | 21 | 26 |  | 5
5.58 | RH | 1364 | SO. BLOOMINGTON - BLOOMINGTON OLD DANVERS RD. LINE 1364 | JRW | [17 empty] | 6
2.32 | RH | 1364A | DIAMOND STAR SPUR - 138 KV LINE 1364A | JRW
32.13 | RI | 1366 | EAST GALESBURG - EAST KEWANEE - 138 KV LINE - 1366 | JRW | [20 empty] | 2 | 1 |  | 1
3.25 | RI | 1366A | KEWANEE SOUTH STREET SPUR - 138 KV LINE - 1366A | JRW
23.01 | RJ | 1372 | SOUTH BLOOMINGTON - CLINTON ROUTE 54 - 138 KV | JRW | [20 empty] | 2
8.46 | RJ | 1372B | CLINTON POWER STATION SPUR - 138 KV | JRW
34.66 | RK | 1376 | BLOOMINGTON BROKAW - MAHOMET - 138 KV LINE 1376 | JRW | [20 empty] | 2 | 1 | 2
53.05 | RL | 1382 | NORMAL RAAB RD. SW. STA. - OGLESBY - 138 KV LINE 1382 | JRW | [20 empty] | 4 | 1 | 1
2.68 | RL | 1382A | EL PASO SPUR - 138 KV LINE - 1382A | JRW
16.55 | RM | 1386 | NORTH CHAMPAIGN - SIDNEY - 138 KV LINE - 1386 | JRW | [20 empty] | 1 |  | 1 | 1
0.66 | RM | 1386B | MIRA SPUR - 138 KV LINE - 1386B | JRW
8.63 | RN | 1392 | E. GALESBURG - GALESBURG MONMOUTH BLVD. 138 KV LINE 1 | JRW | [22 empty] | 1
26.8 | RO | 1396 | VERMILION P.S. - NORTH CHAMPAIGN - 138 KV LINE 1396 | JRW | [20 empty] | 3 |  | 1
7.28 |  | 1402 | UNION ELECTRIC CO. - DUPO FERRY ROAD - 138 KV LINE 14 | TJM
20.2 | RP | 1406 | HAVANA POWER STA. - WEST MASON CITY - 138 KV LINE - 1 | JRW | [9 empty] | 0 | 20 | [9 empty] | 2
2.44 | RQ | 1416 | DECATUR E. MAIN ST. - DECATUR RT. 51 - 138 KV LINE - | JRW
48.17 | MY | 1422 | HAVANA P.S. - ELKHART SW. STA. (CILCO) 138 KV LINE 14 | JRW | [9 empty] | 0 | 0 | 48 | [8 empty] | 5
6.64 | MY | 1422A | TURRIS COAL COMPANY SPUR - 138 KV LINE 1422A | JRW
8.6 | RS | 1426 | STALLINGS - E. COLLINSVILLE - 138 KV LINE - 1426 | TJM | [20 empty] | 0 | 2 | 0.1 | 0
5.87 | RT | 1432 | E. COLLINSVILLE-PORTER RD.-138 KV LINE 1432 | TJM | [22 empty] | 0.1 | 0
4.38 | RU | 1434 | PORTER RD - E BELLEVILLE - 138 KV LINE 1434 | TJM | [22 empty] | 2
25.46 | RV | 1436 | WOOD RIVER P.S. - NORTH STAUNTON - 138 KV LINE 1436 | TJM | [10 empty] | 25.46 | [10 empty] | 0 | 4 | 1
5.75 | RV | 1436A | GILLESPIE SPUR - 138 KV LINE - 1436A | TJM | [21 empty] | 0 | 2
0 |  | 1442 | O'FALLON PORTER ROAD-AVISTON SUB. 138 KV LINE 1442 | TJM
22.93 | RW | 1446 | NORTH STAUNTON - MIDWAY - 138 KV LINE - 1446 | TJM | [10 empty] | 22.93 | [10 empty] | 0 | 0 | 4
7.2 | RW | 1446A | LITCHFIELD-138 KV SPUR LINE NO. 1446A | TJM | [10 empty] | 7.2 | [10 empty] | 0 | 2
17.5 | RX | 1452 | WOOD RIVER P.S. - VENICE P.S. (U.E.) - 138 KV LINE 14 | TJM | [20 empty] | 1 | 1 | 1 | 0
0 | RX | 1452 T | TAP TO MADISON STATE ST. SUB. - 138 KV LINE 1452 T | TJM
6.82 | RX | 1452A | MADISON INDUSTRIAL - STALLINGS - 138 KV LINE - 1452A | TJM | [20 empty] | 0 | 0 | 0 | 0
2.63 | RX | 1452B | AMERICAN STEEL FOUNDRIES SPUR - 138 KV LINE - 1452B | TJM | [22 empty] | 1
17.84 | RY | 1456 | WOOD RIVER POWER STA. - STALLINGS - 138 KV LINE - 145 | TJM | [21 empty] | 4 | 1
31.91 | RZ | 1462 | DECATUR RT. 51 - NORTH PANA - 138 KV LINE - 1462 | JRW | [20 empty] | 3 |  |  | 1
4.43 | RZ | 1462A | MT. ZION P.P.G. INDUSTRIES SPUR - 138 KV LINE 1462A | JRW
12.55 | RZ | 1462B | MT. AUBURN SHELL OIL SPUR 138 KV LINE 1462B | JRW
33.8 | SA | 1466 | NORTH PANA - MIDWAY - 138 KV LINE - 1466 | KDE | [10 empty] | 33.8
5.75 | SA | 1466A | SCHRAM CITY SPUR - 138 KV LINE - 1466A | KDE | [10 empty] | 5.75
4.92 | SB | 1472 | E. COLLINSVILLE - BELLEVILLE TURKEY HILL 138 KV LINE | TJM | [20 empty] | 1 |  | 2
17.5 | SC | 1476 | NO. COULTERVILLE - STEELEVILLE 138 KV LINE 1476 | TJM | [20 empty] | 4
0 | SC | 1476A | AYRSHIRE SPUR - 138 KV LINE - 1476A | TJM
2.34 | SC | 1476C | SPARTA SPUR - 138 KV LINE - 1476C | TJM | [20 empty] | 2
0 | SC | 1476D | SOUTHWESTERN COAL SPUR - 138 KV LINE - 1476D | TJM
0 | SC | 1476E | CONSOLIDATION MINE CO. SPUR - 138 KV LINE - 1476E | TJM
43.57 | SD | 1482 | BELLEVILLE TURKEY HILL - ASHLEY - 138 KV LINE - 1482 | TJM | [21 empty] | 1 | 0 | 5
10.56 | SD | 1482A | AVISTON (ALBERS) 138 KV SPUR LINE 1482A | TJM | [21 empty] | 0 | 0.5 | 1.5
0 | SD | 1482T | STR. 73, L1482 - ALBERS MONTEREY COAL | TJM
12.17 | SE | 1486 | ASHLEY - WEST MT. VERNON - 138 KV LINE - 1486 | KDE | [6 empty] | 12.17
18.89 | SF | 1492 | U.E. CAHOKIA P.S.-BELLEVILLE TURKEY HILL 345 KV LINE | TJM | [10 empty] | 18.89 | [10 empty] | 1 | 1 | 0.5
5.93 | SF | 1492A | CENTERVILLE SPUR - 138 KV LINE - 1492A | TJM | [10 empty] | 5.93 | [9 empty] | 1 |  | 0 | 1
3.89 | SG | 1496 | OGLESBY - LASALLE - 138 KV LINE 1496 | JRW | [18 empty] | 4 |  |  |  | 1
4.36 | SH | 1502 | WOOD RIVER P.S. - ROXFORD (U.E.) - 138 KV LINE 1502 | TJM
4.07 | SH | 1506 | WOOD RIVER P.S. - ROXFORD (U.E.) - 138 KV LINE 1506 | TJM
37.68 | MZ | 1512 | HENNEPIN P.S. - SPRING BAY (C.I.L.CO.) 138 KV LINE 15 | JRW | [17 empty] | 14 | 0 | 0 | 4
0.71 | MZ | 1512A | J. & L. STEEL CO. COLD MILL SPUR - 138 KV LINE 1512A | JRW
14.51 | SI | 1516 | HENNEPIN PWR. STA. - OGLESBY - 138 KV LINE - 1516 | JRW | [20 empty] | 1
1.16 | SI | 1516A | MARQUETTE CEMENT SPUR - 138 KV LINE 1516A | JRW
16.4 | SI | 1516B | OGLESBY - OTTAWA - 138 KV LINE - 1516B | JRW
2.67 | SJ | 1522 | NORTH DECATUR - DECATUR EAST MAIN ST. 138 KV LINE 152 | JRW | [18 empty] | 3
2.54 | SJ | 1522A | DECATUR NORTH 27TH STREET SUB. SPUR - 138 KV LINE - 1 | JRW | [19 empty] | 1
36.77 | SK | 1526 | SOUTH BELLEVILLE - TILDEN - 138 KV LINE - 1526 | TJM | [12 empty] | 1 | [7 empty] | 1.5 | 0 | 0 | 0
2 | SK | 1526A | BALDWIN SPUR - 138 KV LINE - 1526A | TJM | [20 empty] | 1
1.17 | SK | 1526B | PEABODY COAL PIT 5 SPUR - 138 KV LINE - 1526B | TJM
4.09 | SK | 1526D | FAYETTEVILLE BEE HOLLOW SPUR - 138 KV LINE 1526D | TJM | [20 empty] | 1 | 0 | 0 | 0
14.28 | SK | 1526E | FAYETTEVILLE BEE HOLLOW SPUR - 138 KV LINE 1526E | TJM | [20 empty] | 2 | 0 | 0 | 0
2.29 | SL | 1532 | BELLEVILLE TURKEY HILL - SO. BELLEVILLE 138 KV LINE 1 | TJM | [22 empty] | 1
35.44 | SM | 1536 | ASHLEY - WEST FRANKFORT - 138 KV LINE - 1536 | KDE | [20 empty] | 1 | 0 |  | 2.5
1.7 | SM | 1536A | WALTONVILLE INLAND SPUR - 138 KV LINE - 1536A | KDE
28.23 | SN | 1542 | MIDWAY - SOUTH CENTRALIA - 138 KV LINE - 1542 | KDE | [20 empty] | 2 | 1
15.8 | SO | 1546 | SOUTH CENTRALIA - WEST MT. VERNON - 138 KV LINE 1546 | KDE |  |  |  | 15.8 | [16 empty] | 1 |  | 1
31.39 | SP | 1552 | HENNEPIN P.S. - EAST KEWANEE - 138 KV LINE 1552 | JRW | [9 empty] | 0 | 0 | 31 | [8 empty] | 3
1.71 | SP | 1552A | J. & L. STEEL CO. COLD MILL SPUR - 138 KV LINE 1552A | JRW | [9 empty] | 0 | 0 | 2
16.46 | SP | 1552B | PRINCETON 138 KV SPUR LINE 1552B | JRW | [9 empty] | 0 | 0 | 16 | [6 empty] | 16 |  | 1 |  | 1
13.38 | SQ | 1556 | HENNEPIN POWER STA. - OGLESBY - 138 KV LINE - 1556 | JRW
10.51 | SQ | 1556A | NORTH LASALLE SPUR - 138 KV LINE - 1556A | JRW | [15 empty] | 0 |  | 11 |  |  |  |  | 1
4.93 | SR | 1562 | S. BLOOMINGTON - Brokaw - 138 KV L. 1 | JRW
14.99 | ST | 1566 | LATHAM - NORTH DECATUR - 138 KV LINE - 1566 | JRW | [19 empty] | 15 | 1
11.44 | SU | 1572 | VERMILION P.S. - TILTON GENERAL MOTORS 138 KV - LINE | JRW | [10 empty] | 0 | 6 | [8 empty] | 1
9.28 | SV | 1576 | BUNSONVILLE - TILTON GENERAL MOTORS 138 KV - LINE 157 | JRW | [9 empty] | 0 | 0 | 9 | [8 empty] | 1
9.1 | SW | 1578 | BLOOMINGTON BROKAW - NORMAL EAST - 138 KV LINE 1578 | JRW | [21 empty] | 1
28.54 | SX | 1582 | BROKAW - GIBSON CITY - 138 KV LINE 1582 | JRW | [20 empty] | 3
8.34 | SY | 1586 | SOUTH BELLEVILLE - CENTERVILLE - 138 KV LINE 1586 | TJM | [21 empty] | 1 | 1.5 | 0.5
0.99 | SY | 1586A | BELLEVILLE 17TH. ST. SPUR - 138 KV LINE - 1586A | TJM | [21 empty] | 0 | 1
3.37 | SY | 1586B | BELLEVILLE 65TH ST 138 KV SPUR LINE 1586B | TJM | [21 empty] | 0 | 1
9.02 | SZ | 1592 | RISING - NORTH CHAMPAIGN - 138 KV LINE - 1592 | JRW | [20 empty] | 1
1.55 | SZ | 1592A | MAHOMET SPUR - 138 KV LINE - 1592A | JRW
5.63 | TA | 1596 | SOUTH BLOOMINGTON - BROKAW - 138 KV LINE - 1596 | JRW | [9 empty] | 0 | 0 | 6 |  |  |  |  | 1 | 5
0 | TA | 1596A | NORMAL EAST SPUR - 138 KV LINE - 1596A | JRW | [17 empty] | 1
2.18 | TB | 1602 | NORTH DECATUR - DECATUR NORTH 27TH ST. 138 KV LINE 16 | JRW | [17 empty] | 1 | 1
1.93 | TC | 1604 | DECATUR 27TH ST. SUB. - ADM NORTH SUBSTATION | JRW
3.23 | TD | 1606 | OREANA - DECATUR ADM NORTH SUB. - 138 KV LINE 1606 | JRW
1.1 | TE | 1608 | A.D.M. NORTH - FARIES PARKWAY - 138 KV SPUR L1608 | JRW
3.07 | TF | 1610 | OREANA SUB. - ADM NORTH - 138 KV LINE | JRW
20.04 | V | 1612 | C.I.P.S. CONCORD - JACKSONVILLE IND PARK 138 KV LINE | TJM | [21 empty] | 2
12.18 | TG | 1616 | DECATUR FARIES PKWY. - MT ZION PPG IND. 138 KV LINE 1 | JRW | [18 empty] | 0 | 0 | 1
4.74 | TH | 1626 | COFFEEN P.S. (C.I.P.S.) - MIDWAY 138 KV LINE 1626 | KDE |  | 4.74
27.93 | WW | 1636 | STEELEVILLE - GRAND TOWER P.S. (C.I.P.S.) 138 KV L. 1 | KDE | [20 empty] | 1 |  | 2
0.65 | TI | 6101 | HENNEPIN - COMMONWEALTH EDISON - 138 KV SPUR - LINE 6 | JRW
6.6 | TJ | 6102 | MARSEILLES - COMMONWEALTH EDISON 138 KV SPUR LINE 610 | JRW | [19 empty] | 0
230 kV
0.47 | ET | 2303 | NORTH COULTERVILLE (U.E.) - 230KV LINE - 2303 | TJM | [10 empty] | 1 |  | 0.47 | [7 empty] | 1
0 |  | 2304 | (U.E.) - 230 KV - ST. JOHN'S SUB. | KDE
345 kV
31.3 | TK | 4501 | SIDNEY - EUGENE (I. & M.) - 345 KV LINE - 4501 | JRW | [20 empty] | 3 |  |  | 3
36.23 | TL | 4511 | BALDWIN P.S. - CAHOKIA P.S. (U.E.) - 345 KV LINE - 45 | TJM | [12 empty] | 1 | [7 empty] | 1 | 3
20.78 | TM | 4521 | BALDWIN PWR. STA. - TURKEY HILL - 345 KV LINE - 4521 | TJM | [20 empty] | 0 | 3
35.19 | TN | 4525 | SIDNEY - WEST KANSAS - 345 KV LINE - 4525 | JRW | [18 empty] | 35 |  |  |  |  | 3
46.29 | TO | 4531 | BALDWIN POWER STATION - STALLINGS - 345 KV LINE 4531 | TJM | [20 empty] | 4 | 1
22.41 | TP | 4535 | CLINTON P.S. - BLOOMINGTON BROKAW - 345 KV LINE 4535 | JRW | [9 empty] | 0 | 22 | [8 empty] | 22 | 2 |  |  | 2
50.8 | TQ | 4541 | BALDWIN PWR. STA - W. MT. VERNON - 345 KV LINE - 4541 | TJM | [20 empty] | 5 | 0
43.16 | TR | 4545 | CLINTON PWR. STA. - GOOSE CREEK P.S. - 345 KV LINE - 4545 | JRW | [19 empty] | 43 | 4
8.49 | TR | 4545A | OREANA SPUR - 345 KV LINE - 4545A | JRW | [19 empty] | 8 | 1
50.07 | TS | 4551 | COFFEEN PWR. STA. (CIPS) - ROXFORD (U.E.) - 345 KV | TJM |  | 50 | [18 empty] | 1 |  | 0 | 2
51.96 | TU | 4561 | JOPPA - WEST MT. VERNON - 345 KV LINE - 4561 | KDE
62 | BD | 4565 | SHAWNEE - E. W. FRANKFORT - LINE 4565 - 345 KV | KDE | [21 empty] | 6.2
29.61 |  | 4571 | LATHAM - RISING - 345 KV LINE - 4571A | JRW | [20 empty] | 3
8.49 |  | 4571A | OREANA SPUR LINE 4571A | JRW | [19 empty] | 8
14.71 | TR | 4575 | GOOSE CREEK P.S. - RISING SUBSTATION - 345 KV LINE 4575 | JRW | [19 empty] | 15
8.54 | TW | 4581 | STALLINGS - ROXFORD (U.E.) | TJM | [22 empty] | 0 | 1
62 | BG | 4591 | W. MT. VERNON - XENIA (C.I.P.S.) - 345 KV LINE - 4591 | KDE | [20 empty] | 2 |  | 2
|  |  | System Totals |  | 0 | 54.74 | 0 | 15.8 | 0 | 0 | 12.17 | 0 | 0 | 0 | 223.96 | 133 | 2.47 | 0 | 0 | 0 | 11 | 98 | 89 | 132 | 105.5 | 32.7 | 42.2 | 31
2094.99 |  |  |  | TOTALS |  |  |  | 70.54 |  |  |  | 12.17 |  |  |  | 356.96 |  |  |  | 2.47 |  |  |  | 330 |  |  |  | 211.4
Follow up ground crew to be charged to aerial trimming, not tree crew work | [26 empty] | TOTAL | 983.54
[25 empty] | 118.97 | 185.44 | 367.33 | 311.8
Note on I93: e79753: This line was moved up from 2011 schedule due to other 2010 aerial trim work being completed sooner than anticipated.
Note on O6: Chad Warren: Will be worked in third quarter due to schedule of spray contractor; non priority work
Note on O8: e29513: All spray work postponed until 3Q due to late by contractor
Note on O21: e29513: postponed until 3Q due to late start by contractor
Note on O40: e29513: postponed until 3Q due to late start by contractor
Note on O42: e29513: postponed until 3Q do to late start by contractor
Note on O94: e29513: postponed until 3Q due to late start by contractor
Note on O95: e29513: postponed until 3Q due to late start by contractor
Note on O96: e29513: postponed until 3Q due to late start by contractor
Note on O102: e29513: postponed until 3Q due to late start by contractor
Note on O110: e29513: postponed until 3Q due to late start by contractor
Note on O132: e29513: postponed until 3Q due to late start by contractor
Note on P8: e29513: Non priority work, will complete in 4Q.
Note on P42: e29513: Non priority work, will complete in 4Q.
Note on P94: e29513: Non priority work, will complete in 4Q.
Note on P95: e29513: Non priority work, will complete in 4Q.
Note on P96: e29513: Non priority work, will complete in 4Q.
Note on P101: e29513: Work did not get done due to late start by contractor. Non priority work, will complete in 4Q.
Note on P102: e29513: Non priority work, will complete in 4Q.
Note on P110: e29513: Non priority work, will complete in 4Q.
Note on Q101: e29513: All basal work complete, will do foliage work (non-priority) in 2011.
Note on Q110: e29513: tree crew cut what little brush was on this line.
Note on R84: E34686: ENTIRE LINE WAS SPRAYED IN 2008 - THIS IS NURSERY THAT WOULD LIKE OLIVE MOWED OUT ONLY
Note on R124: E34686: WHOLE LINE IS ONLY .47 MILES AND WE ARE DOING ENTIRE LINE
Note on R128: E34686: NWTF ONLY DOING 1 MILE OF LINE FOR CUSTOMER WILDLIFE AREA
Note on U98: e29513: routine work (non-priority) was not completed due to working on priority work found on 2010 patrols
Note on V17: e29513: Got caught up on priority work so statred crew trimming on this line.
Note on V25: e29513: Got caught up on priority work so I had crew start trimming this line.
Note on V110: e29513: Completed other priority work, was able to complete this work sooner than planned
Note on W21: e29513: Got the opportunity to remove some trees early on this line so we did that.
Note on W25: e29513: Work not complete. Very wet conditions and flooding.
Note on W77: e29513: Work not compltee do to wet conditions and flooding, will do 3Q if possible
Note on W112: e29513: Work not complete, pulled crew off to do priority work
Note on X21: e29513: Crew completed work in Decatur, didn't get to rurals due to working on priority work, will complete non priority work in 4Q
Note on X77: e29513: Crew was working on priority work, will complete non priority work in 4Q.
Note on X118: e29513: Crew was working on priority work, will complete non priority work in 4Q.
Note on Y21: e29513: did not complete routine maintenance (non-priority) due to working on priority work found on 2010 patrols
Note on Y23: e29513: did not complete routine maintenance (non-priority) due to working on priority work found on 2010 patrols
Note on Y77: e29513: did not complete routine maintenance work (non-priority) due working on priority work found on 2010 patrols
Note on Y118: e29513: did not complete routine maintenance (non-[priority) due to working on priority work found on 2010 patrols
Note on Y122: e29513: did not complete routine maintenance (no-priority) due to working on priority work found on 2010 patrols
Note on Z6: E34686: ONLY 2LOCATIONS LEFT - WILL DO AFTER HELI FOLLOWUP - BEFORE MAY1, THESE 2 CAN WAIT
Note on Z8: e29513: waiting on one spot to dry out, will get 2Q
Note on Z28: e29513: hedge row near Kewanee left, waiting on ground to dry out, will get in April
Note on Z32: e29513: one P2 left on creek that is under water, will get in April
Note on Z33: e29513: one spot left in wet area,will get in April
Note on Z44: E34686: THIS WORK MOVED TO 2ND Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on Z54: E34686: THIS WORK MOVED TO 2ND Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on Z90: e26073: Completed priority 2 work, wil complete lower priority work in 2nd Q
Note on Z92: e26073: Completed priority 2 work, wil complete lower priority work in 2nd Q
Note on Z93: e26073: Completed priority 2 work, wil complete lower priority work in 2nd Q
Note on Z120: e79753: Priority 2 work is complete, priority 3 work will be done by 3rd qtr.
Note on Z129: E34686: WILL DO IN 2ND Q DUE TO OTHER PRIORITY WORK AS THIS CAN WAIT.
Note on Z143: e79753: Priority 2 work is complete, priority 3 work will be completed later in year.
Note on AA47: E34686: NO PRESSING PRIORITY WORK. CREW WORKING HOT SPOT ON OTHER LINE. ONLY P2 & P3 WORK WILL BE STARTED IN JULY
Note on AA48: E34686: NO PRESSING PRIORITY WORK. CREW WORKING HOT SPOT ON OTHER LINE. ONLY P2 & P3 WORK WILL BE STARTED IN JULY
Note on AA50: E34686: NO PRESSING PRIORITY WORK. CREW WORKING HOT SPOT ON OTHER LINE. ONLY P2 & P3 WORK WILL BE STARTED IN JULY
Note on AA51: E34686: NO PRESSING PRIORITY WORK. CREW WORKING HOT SPOT ON OTHER LINE. ONLY P2 & P3 WORK WILL BE STARTED IN JULY
Note on AA54: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA69: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA84: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA87: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA88: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA90: e79753: This work has been postponed until summer patrol is complete; re-schedule for 4th qtr.
Note on AA106: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AA107: E34686: THIS WORK MOVED TO 3RD Q DUE TO OTHER PRIORITY WORK AS THIS WORK CAN WAIT.
Note on AB10: e29513: Priority work found on 2010 patrols
Note on AB21: e29513: Priority work found on 2010 patrols
Note on AB23: e29513: Priortiy work found on 2010 patrols
Note on AB32: e29513: Priority work found on 2010 patrols
Note on AB33: e29513: priority work found on 2010 patrols
Note on AB35: e29513: priority work found on 2010 patrols
Note on AB37: e29513: priority work found on 2020 patrols
Note on AB38: e29513: priority work found on 2010 patrols
Note on AB44: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB45: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB50: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB52: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB54: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB68: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB69: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB73: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB74: e29513: priority work found on 2010 patrols
Note on AB84: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB87: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB88: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB96: e29513: priority work found on 2010 patrols
Note on AB98: e29513: priority work found on 2010 patrols
Note on AB136: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AB142: E34686: THIS WORK MOVED TO 4th Q DUE TO OTHER PRIORITY WORK AS THIS IS NON PRIORITY WORK.
Note on AC24: e29513: priority work found on 2010 patrol
Note on AC28: e29513: priority work found on 2010 patrol
Note on AC35: e29513: priority work found on 2010 patrol
Note on AC44: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC45: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC52: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC54: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC57: e29513: priority work found on 2010 patrol
Note on AC73: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC84: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC87: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC88: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011
Note on AC127: e29513: priority work found on 2010 patrols
Note on AC130: e29513: priority work found on 2010 patrols
Note on AC132: e29513: priority work found on 2010 patrols
Note on AC136: e44348: Did not complete non-priority work, rescheduled for 1 Q 2011

## ACILCO
AMERENCILCO TRANSMISSION LINES - 2010
Completed Work Listed by Miles Unless Noted Otherwise - (Red is Scheduled/Black is Completed)
[6 empty] | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | CILCO Line # | Line Name | Ameren CILCO # | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.57 | MA | 1325 | Kickapoo-Mcgrath | 200 | JRW | [18 empty] | 2
1.55 | MB | 1325 | McGrath- Limit | 201 | JRW
11.41 | MC | 1344 | Wallace - Spring Bay | 202 | JRW | [19 empty] | 11 |  |  |  | 1
5.81 | MD | 1345 | Edwards - (Cat) Mapleton | 203 | JRW | [10 empty] | 6 | [5 empty] | 6
9.4 | ME | 1346 | Kickapoo -Havana/Latham-IP | 204 | JRW | [22 empty] | 1
13.07 | MF | 1347/1326 | Fargo - Hines | 205 | JRW | [18 empty] | 13 |  | 1
14.99 | MG | 1353 | Wallace-Tazewell | 206 | JRW | [15 empty] | 5 |  |  |  |  | 1 |  |  | 1
9.88 | MH | 1354 | Tazewell-Eastern | 207 | JRW
20.8 | MI | 1357 | Hines-Catrpillar Sub. 1 | 208 | JRW | [17 empty] | 5 | 15 | 1 | 2 |  |  | 2
23.51 | MJ | 1358 shared | Edwards -Fargo 2 | 209 | JRW
24 | MK | 1394 | Edwards - Fargo (Mapleton Tap) | 209 | JRW | [18 empty] | 0 | 0
9 | ML | 1361 | Wallace - Caterpillar Sub 1 | 210 | JRW
9 | MN | 1363 shared | Edwards - Tazewell 3 | 211 | JRW
9.47 | MO | 1373 shared | Edwards - Tazewell 2 | 211 | JRW
10.87 | MP | 1374 shared | Edwards - Caterpillar sub 1 | 212 | JRW
13.24 | MQ | 1375 shared | Tazewell - Caterpillar Sub 2 | 213 | JRW
12 | MR | 1377 | Fargo - Moss Cat | 214 | JRW | [20 empty] | 1
12.12 | MS | 1384 | New Holland - Kickapoo | 215 | JRW | [10 empty] | 12 | [9 empty] | 1 |  |  | 1
61.75 | MT | 1384 | Tazewell- E. Springfiel | 216 | JRW | [10 empty] | 46 | 16 | [10 empty] | 2 | 2
2.1 | MU | 1392 | Edwards-(C.E.) pwerton-Kewanee Tap | 217 | JRW | [10 empty] | 2.1
5.23 | MV | 1395 | Moss-Cat - Hallock | 218 | JRW | [9 empty] | 0 | 0 | 5
3.27 | MW | 1396 | Wallace-Keystone | 219 | JRW
14.62 | MX | 1397 | Edwards-Keystone | 220 | JRW | [9 empty] | 0 | 0 | 0
9.99 | MY | 1422 | E. Sprinfield Tap - (I.P.) Havana Latham | 221 | JRW |  | 10
0.21 | MZ | 1512 | Hallock - Richland | 222 | JRW | [10 empty] | 0 | 0 | [8 empty] | 1 |  | 1
14 | NA | 1512 | Spring Bay - Richland | 223 | JRW | [17 empty] | 0 | 4 | 0 | 1
0.64 | NB | 4521 | Tazewell- Powerton (C.E.) 345kv | 224 | JRW
0.64 | NC | 4525 | Tazewell-Joliet (C.E.) (345Kv) | 224 | JRW
21.26 | ND | 4563 | Duck Creek- Tazewell (345Kv) | 225 | JRW |  | 21 | [8 empty] | 21 | [9 empty] | 2 |  | 1
9.46 | NE | 4573 | Duck Creek - (CIPS) Ipava (345kv) | 226 | JRW | [20 empty] | 1
|  |  | System Totals |  |  | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.1 | 21 | 0 | 0 | 0 | 5 | 6 | 5 | 34 | 12 | 11 | 0 | 5 | 7
354.86 |  |  |  |  | TOTALS |  |  |  | 31 |  |  |  | 0 |  |  |  | 108.1 |  |  |  | 5 |  |  |  | 57 |  |  |  | 23
[28 empty] | TOTAL | 224.1
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [25 empty] | 17 | 36 | 126.1 | 45
Note on P25: e29513: Postponed until 3Q due to late start by contractor, no priority work
Note on P27: e29513: postponed to 3Q due to late start by contractor, no priority work
Note on Q25: e29513: Postponed until 4Q due to late start by contractor, no priority work
Note on Q27: e29513: Postponed until 4Q due to late start by contractor, no priority work
Note on Q29: e29513: Postponed until 4Q due to late start by contractor, no priority work
Note on R27: e29513: this routine work (non-priority) was not completed, rescheduled for 2011.
Note on R29: e29513: this routine work (non-priority) was not completed, rescheduled for 2011.
Note on V11: e29513: This area mowed is along the bike trail only and cannot be sprayed
Note on X13: e29513: Work not complete, underestimated the amount of work
Note on X14: e29513: This line is double circuit, will get 3Q with Edwards to Fargo Mapleton tap
Note on X30: e29513: Did not get started on this line. Underestimated the amout of work for this crew, no priority work
Note on Y13: e29513: approximately one mile left on this line, will do in 4Q.
Note on Y15: e29513: Did not get to this work, non priority work; will get in 4Q. Crew spent time on priority work fonnd on 2010 patrols
Note on Y30: e29513: Non priority work, will complete in 4Q.
Note on Z15: e29513: this routine work (non-priority) was not completed, rescheduled for 2011.
Note on Z30: e29513: this routine work (non-priority) was not completed, rescheduled for 2011.
Note on AC9: e29513: priority work found on 2010 patrols
Note on AC23: e29513: priority work found on 2010 patrols
Note on AC29: e29513: priority work found on 2010 patrols
Note on AC33: e29513: priority work found on 2010 patrols
Note on AD7: e29513: priority work found on 2010 patrol
Note on AD11: e29513: priority work found on 2010 patrol
Note on AD13: e29513: priority work found on 2010 patrol
Note on AD22: e29513: priority work found on 2010 patrol
Note on AD23: e29513: priority work found on 2010 patrol

## IL
IL - 2009 - Scheduled vs. Completed Work
Quarter | Scheduled Miles | Completed Miles | Percentage Completed
1 | 338 | 358 | 105.9%
2 | 1190 | 642 | 53.95%
3 | 971 | 1013 | 104.3%
4 | 281 | 533 | 189.7%
Totals | 2780 | 2546 | 91.58%
374 miles of 2nd Q ground herbicide work was deferred to the 3rd Q as a result of work visa problems experienced by the contractor. Also, 50 miles of 2nd Q work was delayed due to flooding. It is expected that, with normal weather, all delayed/deferred work should be made up in the 3rd Q. No priority work had been identified on any of the lines so affected.
219 miles of 3Q ground herbicide work was deferred to 4Q due to availability of herbicides crews. Contracted with a second herbicide vendor to assist with work. 44 miles of hotspot work deferred to 4Q to manage priority work found during routine patrols. No priority work had been identified on any of the scheduled lines so affected.
The majority of the scheduled work not completed (8%) for 2010 was routine maintenance work (non-priority work) that has been rolled over into 2011. One line of aerial herbicide work (31 miles) was entered in error at the beginning of the year and did not require herbicide work, only minor hotspot work.