## STEP Appendix 1
2020 STEP Appendix 1
Project Status Definitions
CLOSED OUT |  |  |  | Upgrade is operation, all project activities are complete, & all close-out requirements fulfilled
COMPLETE |  |  |  | Upgrade is operation and all project activities are complete
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project; asterisk (*) indicates interim mitigation plan provided by SPP
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
RE-EVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
SUSPENDED |  |  |  | NTC/GIA suspended
NTC_ID | PID | UID | ProjectOwner | State(s) | Project Name | Upgrade Name | Project Type | STEP Upgrade Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | NTC Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200397 | 242 | 10308 | WFEC | OK | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2022-03-01 | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3489126 | 3240000 | 3790002 | DELAY - MITIGATION | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
200216 | 451 | 10583 | AEP | AR | Multi - Chamber Springs - Farmington 161 kV | Chamber Springs - Farmington REC 161 kV Ckt 1 | Regional Reliability | ITP | 2017-03-28 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12705537 | 2013 | 14734528 | 12705537 |  | COMPLETE | 506944 | CHAMBER SPRINGS 161KV | 504020 | FARMINGTON AECC | Rebuild and reconductor 11.1-mile 161 kV line from Chamber Springs to Farmington REC with 2-959.6 ACSR/TW. Upgrade wavetraps, CT ratios, and relay settings at Chamber Springs. | 161 |  | 11.1
200166 | 461 | 10597 | SPS | TX/NM | Line - Curry - Bailey 115kV | Bailey County Interchange - Curry County Interchange 115 kV Ckt 1 | Regional Reliability | ITP | 2016-09-29 | 2012-06-01 | 2012-04-09 | 2012 ITPNT | 35099588 | 2012 | 41722380 | 38607163 | 38607163 | COMPLETE | 524822 | Curry County Interchange 115 kV | 525028 | Bailey County Interchange 115 kV | Build 40 miles of 115 kV transmission line between Bailey County and Curry County. | 115 | 41.5
200216 | 478 | 10615 | AEP | LA | Line - Forbing Tap - South Shreveport 69 kV | Forbing Tap - South Shreveport 69 kV Ckt 1 | Regional Reliability | ITP | 2016-04-13 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1221505 | 2013 | 1416572 | 1221505 |  | COMPLETE | 507728 | FORBING TAP | 507754 | SOUTH SHREVEPORT 69KV | Rebuild 2.3-mile 69 kV line from Forbing to South Shreveport with 1233.6 ACSR/TW. | 69 |  | 2.3
200216 | 501 | 10646 | AEP | TX | Line - Evenside - Northwest Henderson 69 kV | Evenside - Northwest Henderson 69 kV Ckt 1 | Regional Reliability | ITP | 2018-05-11 | 2018-06-01 | 2013-02-20 | 2013 ITPNT | 11980465 | 2013 | 13893666 | 11980465 |  | COMPLETE | 509061 | EVENSIDE | 509075 | NORTHWEST HENDERSON 69KV | Rebuild 6.4-mile 69 kV line from Evenside to Northwest Henderson with 1233.6 ACSR/TW. Replace breaker at Evenside. | 69 | 6.4
200167 | 503 | 10648 | AEP | TX | Line - Diana - Perdue 138 kV | Diana - Perdue 138 kV Ckt 1 | Regional Reliability | ITP | 2014-12-31 | 2013-06-01 | 2012-04-09 | 2012 ITPNT | 1004187 | 2012 | 1193662 | 1004187 |  | COMPLETE | 508351 | PERDUE 138KV | 508831 | DIANA 138KV | Replace two breakers, jumpers, and wave traps at Perdue substation. Replace wave traps at Diana substation. | 138
200216 | 504 | 10649 | AEP | LA | Line - Brownlee - North Market 69 kV | Brownlee - North Market 69 kV Ckt 1 | Regional Reliability | ITP | 2017-03-22 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 12424849 | 2013 | 14409016 | 17162457 |  | COMPLETE | 507718 | BROWNLEE | 507745 | NORTH MARKET | Rebuild 4.7-mile 69 kV line from Brownlee to North Market with 1233.6 ACSR/TW. | 69 | 4.7
200246 | 512 | 10657 | AEP | LA | Line - Ellerbe Road - Forbing Tap 69 kV Ckt 1 | Ellerbe Road - Forbing T 69 kV Ckt 1 | Regional Reliability | ITP | 2016-04-13 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8174689 | 2014 | 9248911 | 8174689 |  | COMPLETE | 507723 | ELLERBE ROAD 69 kV | 507728 | FORBING TAP | Rebuild 2.0-mile 69 kV line from Ellerbe Road to Forbing T with 1233.6 ACSR/TW conductor. | 69 | 2
20130 | 764 | 11007 | SPS | TX | XFR - Happy County 115/69 kV Transformers | HAPPY INTERCHANGE 115/69KV TRANSFORMER CKT 1 | Regional Reliability | ITP | 2016-06-30 | 2012-06-01 | 2011-02-14 | 2010 STEP | 2809520 | 2014 | 3178714 | 1518414 |  | COMPLETE | 525154 | Happy Interchange 115 kV | 525153 | Happy Interchange 69 kV | Upgrade Happy County 115/69 kV Transformer #1 to 84/96 MVA | 115/69
20130 | 764 | 11009 | SPS | TX | XFR - Happy County 115/69 kV Transformers | HAPPY INTERCHANGE 115/69KV TRANSFORMER CKT 2 | Regional Reliability | ITP | 2016-06-30 | 2012-06-01 | 2011-02-14 | 2010 STEP | 2812436 | 2014 | 3182013 | 1565056 |  | COMPLETE | 525154 | Happy Interchange 115 kV | 525153 | Happy Interchange 69 kV | Upgrade Happy County 115/69 kV Transformer #2 to 84/96 MVA | 115/69
200256 | 766 | 11010 | SPS | TX | XFR - Newhart 230/115 kV Ckt 2 | Newhart 230/115 kV Ckt 2 Transformer | Regional Reliability | ITP | 2016-12-02 | 2015-06-01 | 2014-02-19 | 2014 ITPNT | 6886931 | 2014 | 7791930 | 13001665 | 13001665 | COMPLETE | 525461 | Newhart Interchange 230 kV | 525460 | Newhart Interchange 115 kV | Add second 230/115 kV 250 MVA transformer at Newhart substation. | 230/115
200229 | 772 | 11017 | SPS | TX | Line - Carlisle - Wolfforth 230 kV | Carlisle Interchange - Wolfforth Interchange 230 kV Ckt 1 | Regional Reliability | ITP | 2018-03-27 | 2017-06-01 | 2013-09-10 | 2013 ITPNT | 32429240 | 2013 | 37607976 | 29400000 |  | IN SERVICE | 526525 | Wolfforth Interchange 230 kV | 526161 | Carlisle Interchange 230 kV | Build new 16.8-mile 230 kV line from Carlisle to Wolfforth South and install necessary terminal equipment. | 230 | 16.8
200381 | 777 | 11027 | SPS | TX | Sub - East Plant 115 kV Terminal Upgrade | East Plant 115 kV Terminal Upgrade | Regional Reliability | TS | 2017-06-01 | 2017-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 5000 | 2016 | 5384 | 0 |  | COMPLETE | 524162 | East Plant Interchange 115 kV | 524224 | Manhattan Sub 115 kV | Replace CT at East Plant 115 kV substation to increase the rating of the 115 kV line from East Plant to Manhattan. | 115
200214 | 802 | 11064 | SPS | NM | XFR - Eddy Co. 230/115 kV Transformer Ckt 1 | Eddy County Interchange 230/115 kV Transformer Ckt 1 | Regional Reliability | ITP | 2017-03-31 | 2016-06-01 | 2013-02-20 | 2013 ITPNT | 4255145 | 2013 | 4934664 | 4529862 |  | COMPLETE | 527800 | Eddy County Interchange 230 kV | 527798 | Eddy County Interchange 115 kV | Upgrade Eddy County 230/115 kV transformer Ckt 1 to 250 MVA. | 230/115
20084 | 834 | 11101 | SPS | NM | Line - Portales - Zodiac 69 kV to 115 kV Conversion | PORTALES INTERCHANGE - ZODIAC 115KV CKT 1 | Regional Reliability | ITP | 2015-11-30 | 2013-06-01 | 2010-02-08 | 2009 STEP | 6500000 | 2014 | 7354153 | 7588596 | 8084263 | COMPLETE | 524924 | Portales Interchange 115 kV | 524935 | Zodiac Sub 115 kV | Convert existing 3 mile Portales Interchange - Zodiac 69 kV line to operate at 115 kV. | 115 |  |  | 3
200166 | 836 | 11104 | SPS | TX | Sub - Convert Muleshoe East 69 kV to 115 kV | Convert Muleshoe 69 kV to 115 kV | Regional Reliability | ITP | 2015-12-18 | 2012-06-01 | 2012-04-09 | 2012 ITPNT | 4673759 | 2012 | 5555630 | 1569093 | 1631376 | COMPLETE | 524030 | Muleshoe E 115 kV |  |  | Tap Bailey County Interchange - Plant X 115 kV line and convert Muleshoe East substation to 115 kV operation. | 115 | 0.3 |  | 1.5
200214 | 841 | 11110 | SPS | TX | XFR - Graham 115/69 kV Ckt 1 | Graham Interchange 115/69 kV Transformer Ckt 1 | Regional Reliability | ITP | 2015-12-09 | 2014-06-01 | 2013-02-20 | 2013 ITPNT | 2101391 | 2013 | 2436969 | 1337225 | 1337255 | COMPLETE | 526693 | Graham Interchange 69 kV | 526694 | Graham Interchange 115 kV | Upgrade Graham 115/69 kV transformer Ckt 1 to 84 MVA. | 115/69
200397 | 844 | 11113 | WFEC | OK | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-12-31 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5088308 | 4725000 | 643784 | ON SCHEDULE < 4 | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10
200256 | 856 | 11127 | SPS | TX | Multi - Centre St. - Hereford NE 115 kV Ckt 1 and Centre St. and Hereford 115 kV Load Conversion | Centre St. - Hereford NE 115 kV Ckt 1 | Regional Reliability | ITP | 2018-04-06 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 9247136 | 2014 | 10462286 | 10000000 |  | IN SERVICE | 524567 | Northeast Hereford Interchange 115 kV | 524555 | Hereford Centre Street Sub | Build new 5.1-mile 115 kV line from Centre St. to Hereford NE. Convert distribution transformer high side at Centre St. from 69 kV to 115 kV. Install any necessary terminal equipment at Hereford NE. | 115 | 7.8
200207 | 865 | 11142 | OPPD | NE | Line - Sub 917 - Sub 918 69 kV Ckt 1 | Sub 917 - Sub 918 69 kV Ckt 1 | Regional Reliability | ITP | 2018-05-21 | 2018-06-01 | 2013-02-20 | 2013 ITPNT | 475340 | 2013 | 551249 | 155546 | 155546 | CLOSED OUT | 647917 | Sub 917 | 647918 | Sub 918 | Increase line clearances and upgrade terminal equipment on Sub 917 - Sub 918 69 kV line to allow the use of a higher conductor rating. | 69
200216 | 879 | 11158 | AEP | OK | Line - Bluebell - Prattville 138 kV | Bluebell - Prattville 138 kV Ckt 1 | Regional Reliability | ITP | 2015-06-02 | 2014-06-01 | 2013-02-20 | 2013 ITPNT | 10241314 | 2013 | 11876785 | 10241314 | 8535104 | COMPLETE | 515242 | BLUEBELL 138 | 509758 | PRATTVILLE | Rebuild 9.0-mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW. | 138 |  | 9
20096 | 936 | 11236 | AEP | TX/OK | Line - Valliant - NW Texarkana 345 kV | NORTHWEST TEXARKANA - VALLIANT 345KV CKT 1 | High Priority | HP | 2016-12-16 | 2014-10-01 | 2010-06-30 | Priority Projects | 185751250 | 2016 | 200033780 | 185751250 |  | COMPLETE | 510911 | VALLIANT 345KV | 508072 | NORTHWEST TEXARKANA 345KV | Build a new 76 mile 345 kV line from Valliant to NW Texarkana with at least 3000 A capacity. Upgrade the Valliant and NW Texarkana substations with the necessary breakers and terminal equipment. | 345 | 76.25
20104 | 947 | 11261 | AEP | OK | Line - Broken Arrow North South Tap - Oneta 138 kV Ckt 1 | BROKEN ARROW NORTH - SOUTH TAP - ONETA 138KV CKT 1 #2 | Transmission Service | TS | 2016-05-25 | 2015-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 6072000 | 2014 | 6869911 | 6072000 |  | COMPLETE | 509806 | ONETA 138KV | 509786 | BROKEN ARROW NORTH - SOUTH TAP | Rebuild 4.33 of 795 ACSR with 1590 ACSR. | 138 |  | 4.33
200404 | 1001 | 11315 | SPS | TX | Line - Randall - South Georgia and Osage Station 115 kV Line Re-termination | Randall County Interchange - South Georgia Interchange 115 kV Ckt 1 | Regional Reliability | TS | 2017-04-19 | 2016-06-01 | 2016-07-25 | SPP-2015-AG1-AFS-6 | 10316217 | 2016 | 11109437 | 13100684 |  | COMPLETE | 524364 | Randall County Interchange 115 kV | 524322 | South Georgia Interchange 115 kV | Construct approximately 2 miles of new 115 kV line from Randall Co. Interchange towards Osage Substation connecting to South Georgia line. Tie new 115 kV line into existing circuit V70 near Osage Substation. Reconfigure the 115 kV transmission lines around Osage Substation: remove circuit V04 termination from Osage Substation and remove circuit back to Manhattan Tap (remove 3- terminal condition); remove circuits V67 and V05 terminations from Osage Substation and tie them together around Osage Substation; leave only circuits V43 and T75 terminated at the Osage Substation. Add new 115 kV terminal at Randall Co. Interchange and rebuild Randall 115 kV bus to breaker and one-half design. Upgrade terminal equipment and reset relays at South Georgia Interchange. | 115 | 2
200214 | 1003 | 11317 | SPS | TX | XFR - Grassland 230/115 kV Transformer Ckt 1 | Grassland Interchange 230/115 kV Transformer Ckt 1 | Regional Reliability | ITP | 2016-02-19 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 3961322 | 2013 | 4593919 | 4013798 | 4013798 | COMPLETE | 526677 | Grassland Interchange 230 kV | 526676 | Grassland Interchange 115 kV | Upgrade Grassland 230/115 kV transformer Ckt 1 to 250 MVA. | 230/115
200256 | 1004 | 11318 | SPS | TX | XFR - Swisher 230/115 kV Ckt 1 | Swisher County Interchange 230/115 kV Ckt 1 Transformer | Regional Reliability | ITP | 2015-12-03 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 3183028 | 2014 | 3601304 | 2869670 | 2869670 | COMPLETE | 525213 | Swisher County Interchange 230 kV | 525212 | Swisher County Interchange 115 kV | Upgrade existing 230/115 kV transformer at Swisher to 250 MVA. | 230/115
20110 | 1021 | 11343 | OGE | OK | Line - Arcadia - Redbud 345 kV Ckt 3 | ARCADIA - REDBUD 345KV CKT 3 | Transmission Service | TS | 2019-06-28 | 2019-06-01 | 2010-08-25 | SPP-2008-AGP1-AFS-9 | 18000000 | 2014 | 20365348 | 18000000 |  | COMPLETE | 514908 | ARCADIA 345 | 514909 | REDBUD 345 | Add 3rd 345kV line from Arcadia to Redbud | 345 | 5
200214 | 1031 | 11355 | SPS | TX | XFR - Crosby Co. 115/69 kV Transformers Ckt 1 and Ckt 2 | Crosby County Interchange 115/69 kV Transformer Ckt 1 | Regional Reliability | ITP | 2015-05-01 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 2378798 | 2013 | 2758676 | 4197329 | 4204317 | COMPLETE | 525926 | Crosby County Interchange 115 kV | 525925 | Crosby County Interchange 69 kV | Upgrade Crosby County 115/69 kV transformer Ckt 1 to 84 MVA. | 115/69
200214 | 1031 | 11356 | SPS | TX | XFR - Crosby Co. 115/69 kV Transformers Ckt 1 and Ckt 2 | Crosby County Interchange 115/69 kV Transformer Ckt 2 | Regional Reliability | ITP | 2015-09-10 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 2301000 | 2013 | 2668455 | 1874922 | 1861774 | COMPLETE | 525926 | Crosby County Interchange 115 kV | 525925 | Crosby County Interchange 69 kV | Upgrade Crosby County 115/69 kV transformer Ckt 2 to 84 MVA. | 115/69
200166 | 1033 | 11358 | SPS | TX | Line - Randall - South Georgia 115 kV reconductor | Randall County Interchange - South Georgia Interchange 115 kV Ckt 1 # 2 | Regional Reliability | ITP | 2017-04-12 | 2017-06-01 | 2012-04-09 | 2012 ITPNT | 6300000 | 2014 | 7127872 | 4294271 |  | COMPLETE | 524364 | Randall County Interchange 115 kV | 524322 | South Georgia Interchange 115 kV | Reconductor 4.1 miles of 6.1-mile 115 kV line from Randall County to South Georgia. | 115 |  | 4.1
20130 | 1036 | 11372 | SPS | TX | Line - Soncy convert load to 115 kV | Soncy Tap 115 kV - New Soncy 115 kV | Regional Reliability | ITP | 2018-12-31 | 2015-06-01 | 2011-02-14 | 2010 STEP | 929500 | 2014 | 1051644 | 2087292 |  | IN SERVICE | 524252 | Soncy Tap 115 kV | 524254 | New Soncy 115 kV | Convert 1.04 miles of Z33 to 115 kV service by tapping the 115 kV line from Sunset Substation to Coulter Interchange at I-40 & Soncy Street. At Soncy Sub split the converted Z33 line off the 69 kV bus and terminate to a new 115/13.2 kV transformer to serve the Soncy distribution load. Install new 115/13.2 kV distribution transformer. Leave 69 kV underground cable to Lawrence Park to be fed by Y72 out of Coulter Interchange. | 115 |  |  | 1.04
200297 | 1139 | 11501 | SPS | TX | Line - Allen Sub - Lubbock South Interchange 115 kV Ckt 1 | Allen Substation - Lubbock South Interchange 115 kV Ckt 1 | Regional Reliability | TS | 2019-04-26 | 2019-06-01 | 2015-05-05 | SPP-2012-AG3-AFS-9 | 1164782 | 2015 | 1285701 | 650058 |  | IN SERVICE | 526268 | Lubbock South Interchange 115 kV | 526213 | Allen Sub 115 kV | Rebuild 6-mile 115 kV line from Lubbock South Interchange to Allen substation. | 115
200369 | 1142 | 11506 | SPS | TX | Line - Canyon East - Randall 115 kV Ckt 1 Rebuild | Canyon East Sub - Randall County Interchange 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2014-02-01 | 2016-02-12 | SPP-2011-AG3-AFS-11 | 12806065 | 2016 | 13790731 | 6825695 |  | DELAY - MITIGATION | 524364 | Randall County Interchange 115 kV | 524523 | Canyon East Sub 115 kV | Rebuild 13.5-mile 4/0 segment of 115 kV line from Canyon East Sub to Randall County Interchange. | 115 | 18.5
200262 | 1144 | 11508 | SPS | TX | XFR - Hitchland 230/115 kV Ckt 2 | Hitchland 230/115 kV Ckt 2 Transformer | Regional Reliability | TS | 2017-03-29 | 2019-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 4087144 | 2014 | 4624228 | 4525487 |  | COMPLETE | 523095 | Hitchland Interchange 230 kV | 523093 | Hitchland Interchange 115 kV | Add second 230/115 kV 250 MVA transformer at Hitchland. | 230/115
200359 | 1146 | 11509 | SPS | TX | XFR - Carlisle 230/115 kV Ckt 1 | Carlisle 230/115 kV Ckt 1 Transformer | Regional Reliability | TS | 2018-03-09 | 2015-10-01 | 2015-12-02 | SPP-2014-AG1-AFS-6 | 3853326 | 2016 | 4149611 | 3000000 | 3109347 | IN SERVICE | 526161 | Carlisle Interchange 230 kV | 526160 | Carlisle Interchange 115 kV | Upgrade 230/115 kV transformer at Carlisle. | 230/115
200214 | 1147 | 11512 | SPS | TX | Multi - Potter - Channing - Dallam 230 kV Conversion | Channing - Potter County 230 kV Ckt 1 | Regional Reliability | ITP | 2015-12-31 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1819440 | 2013 | 2109993 | 2512528 | 2512528 | COMPLETE | 523869 | Channing 230 kV | 523959 | Potter County Interchange 230 kV | Convert 26 miles of 115 kV line from Channing to Potter to 230 kV and upgrade necessary terminal equipment at Potter. | 230 |  |  | 52
200214 | 1147 | 11514 | SPS | TX | Multi - Potter - Channing - Dallam 230 kV Conversion | Channing - XIT 230 kV Ckt 1 | Regional Reliability | ITP | 2015-12-31 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 9166904 | 2013 | 10630798 | 871088 | 871088 | COMPLETE | 523869 | Channing 230 kV | 523229 | Dallam 230 kV | Convert 35 miles of 115 kV line from Channing to new XIT substation (near Dallam) to 230 kV. | 230 |  |  | 70
200214 | 1147 | 11515 | SPS | TX | Multi - Potter - Channing - Dallam 230 kV Conversion | XIT 230/115/13.2 kV Transformer Ckt 1 | Regional Reliability | ITP | 2015-12-31 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 3863195 | 2013 | 4480122 | 9865350 | 9865350 | COMPLETE | 523229 | Dallam 230 kV | 523228 | Dallam County Interchange 115 kV | Install 230/115 kV transformer at XIT substation. | 230/115
20017 | 30160 | 50168 | OGE | AR | XFR - Ft Smith 500/161 kV Ckt 3 | FT SMITH 500/161KV TRANSFORMER CKT 5 | Transmission Service | TS | 2017-11-10 | 2017-06-01 | 2009-01-16 | SPP-2006-AG3-AFS-11 | 25635637 | 2017 | 26933441 | 25635637 | 22598424 | COMPLETE | 515305 | FT SMITH 500 | 515300 | FT SMITH 161 | Convert Ft. Smith 161KV to 1-1/2 breaker design and install 3rd 500-161KV transformer bank. | 500/161
20080 | 30201 | 50208 | NPPD | NE | Device - Clarks 115 kV | CLARKS 115KV | Regional Reliability | ITP | 2018-06-01 | 2012-11-01 | 2010-02-08 | 2009 STEP | 700000 | 2014 | 791986 | 700000 |  | DELAY - MITIGATION | 640436 | Clarks |  |  | Add a 18 Mvar capacitor bank at Clarks substation 115 kV bus. | 115
20080 | 30203 | 50210 | NPPD | NE | Device - Oneill 115 kV | ONEILL 115KV | Regional Reliability | ITP | 2018-07-01 | 2012-11-01 | 2010-02-08 | 2009 STEP | 700000 | 2014 | 791986 | 1739903 | 1739903 | COMPLETE | 640305 | O'Neill |  |  | Add a second 18 Mvar capacitor bank at Oneill 115 kV substation for a total of 36 Mvar at this location. | 115
20122 | 30296 | 50334 | AEP | TX | Device - Winnsboro 138 kV | WINNSBORO 138KV | Regional Reliability | ITP | 2016-04-21 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1319675 | 1166400 |  | COMPLETE | 508317 | Winnsboro 138 kV |  |  | Install a new 28.8 MVAR capacitor bank at Winnsboro 138 kV substation. | 138
20122 | 30298 | 50336 | AEP | LA | Device - Logansport 138 kV | LOGANSPORT 138KV | Regional Reliability | ITP | 2016-09-10 | 2016-06-01 | 2011-02-14 | 2010 STEP | 1166400 | 2014 | 1319675 | 1731419 |  | COMPLETE | 509071 | LOGANSPORT 138KV |  |  | Install 28.8 MVAR capacitor bank at Logansport 138 kV substation. | 138
200282 | 30331 | 50378 | SPS | NM | Device - Eagle Creek 115 kV | Eagle Creek 115 kV Cap Bank | High Priority | HP | 2016-03-14 | 2015-06-01 | 2014-05-19 | HPILS | 1470325 | 2014 | 1663538 | 1416992 | 1416992 | COMPLETE | 527711 | Eagle Creek 115 kV |  |  | Install 14.4-Mvar capacitor bank at Eagle Creek 115 kV bus. | 115
200166 | 30351 | 50401 | SPS | TX | Device - Crosby 115 kV Capacitor | Crosby 115 kV #2 | Regional Reliability | ITP | 2015-11-04 | 2012-06-01 | 2012-04-09 | 2012 ITPNT | 985519 | 2012 | 1171472 | 1334087 | 1334087 | COMPLETE | 525926 | Crosby County Interchange 115 kV |  |  | Install 14.4 Mvar capacitor at Crosby 115 kV. | 115
200166 | 30356 | 50406 | SPS | TX | Multi - Cedar Lake Interchange 115 kV | Diamondback Interchange 115/69 kV Transformer Ckt 1 | Regional Reliability | ITP | 2015-08-14 | 2012-06-01 | 2012-04-09 | 2012 ITPNT | 5524876 | 2012 | 6567342 | 7399322 | 6981891 | COMPLETE | 527212 | Cedar Lake 115 kV | 527211 | Adair Tap 69 kV | Install new 115/69 kV transformer at new Diamondback Interchange near Cedar Lake. | 115/69 | 17.79
200166 | 30356 | 50407 | SPS | TX | Multi - Cedar Lake Interchange 115 kV | Sulphur Interchange - Diamondback Interchange 115 kV Ckt 1 | Regional Reliability | ITP | 2015-08-14 | 2012-06-01 | 2012-04-09 | 2012 ITPNT | 7699644 | 2012 | 9152457 | 9364821 | 9933961 | COMPLETE | 527262 | Sulphur Interchange 115 kV | 527212 | Cedar Lake 115 kV | Build 12 miles of new 115 kV line from Sulphur Interchange to Diamondback Interchange near Cedar Lake. | 115 | 12.5
200255 | 30361 | 50413 | AEP | OK | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345kV Ckt 1 (AEP) | Regional Reliability | ITP | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 65082311 | 2017 | 68377103 | 65082311 | 87396515 | COMPLETE | 700345 | Chisholm 345 kV | 515800 | Gracemont 345kv | Build new single circuit 345 kV line from new Chisholm substation to point of interconnection with Oklahoma Gas & Electric Co. (OGE) towards Gracemont. The approximate line length for the Chisholm - Gracemont 345 kV line is 100 miles, of which AEP will construct approximately 70 miles from Chisholm to the OGE interconnection point. | 345 | 72
200255 | 30361 | 50414 | AEP | OK | Multi - Chisholm - Gracemont 345 kV | Chisholm 345/230 kV Substation | Regional Reliability | ITP | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 17471695 | 2017 | 18356200 | 17471695 |  | COMPLETE | 700345 | Chisholm 345 kV | 700231 | Chisholm 230 kV | Construct new 345/230 kV Chisholm substation between existing 230 kV substations, Sweetwater and Elk City. Cut-in existing Sweetwater - Elk City 230 kV Ckt 1 line into new Chisholm substation and install any necessary 230 kV terminal equipment. Install new 345/230 675 MVA transformer at new Chisholm substation. | 345/230
200240 | 30361 | 50419 | OGE | OK | Multi - Chisholm - Gracemont 345 kV | Chisholm - Gracemont 345 kV Ckt 1 (OGE) | Regional Reliability | ITP | 2018-03-01 | 2018-03-01 | 2013-12-20 | 2012 ITP10 | 43853500 | 2017 | 46073583 | 37541440 | 35955045 | COMPLETE | 700345 | Chisholm 345 kV | 515800 | Gracemont 345kv | Build new 30-mile single circuit 345 kV line from the Gracemont substation to the interconnection point with American Electric Power, toward the new Chisholm substation. Install any necessary terminal equipment at Gracemont. | 345 | 30.16
200223 | 30364 | 50420 | OGE | OK | Multi - Woodward District EHV - Tatonga - Matthewson - Cimarron 345 kV | Tatonga - Woodward District EHV 345 kV Ckt 2 | Regional Reliability | ITP | 2018-02-01 | 2021-03-01 | 2013-05-23 | 2012 ITP10 | 59522400 | 2013 | 69027736 | 56778052 |  | COMPLETE | 515375 | Woodward EHV 345kv | 515407 | Tatonga 345kv | Build second circuit of new 49-mile 345 kV line from Woodward District EHV to Tatonga. | 345 | 49
200223 | 30364 | 50421 | OGE | OK | Multi - Woodward District EHV - Tatonga - Matthewson - Cimarron 345 kV | Matthewson - Tatonga 345 kV Ckt 2 | Regional Reliability | ITP | 2018-02-15 | 2021-03-01 | 2013-05-23 | 2012 ITP10 | 65785650 | 2013 | 76291185 | 52175034 |  | COMPLETE | 515407 | Tatonga 345kv | 515497 | MATHEWSON 345 | Build second circuit of new 61-mile 345 kV line from Tatonga to new Matthewson substation. | 345 | 61
200253 | 30374 | 50441 | NPPD | NE | Multi - Hoskins - Neligh 345 kV | Neligh 345/115 kV Substation | Regional Reliability | ITP | 2018-06-08 | 2016-06-01 | 2014-02-19 | 2014 ITPNT | 10082325 | 2017 | 10592743 | 10281412 | 10281412 | COMPLETE | 750013 | Neligh 345 kV | 640293 | Neligh 115 kV | Build new substation at Neligh. Install a new 345/115 kV transformer and all necessary 345 kV equipment at Neligh. | 345/115
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | ITP | 2021-05-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 139090440 | 2013 | 161302268 | 174319989 |  | DELAY - MITIGATION | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | ITP | 2021-05-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 11896383 | 2013 | 13796157 | 9936752 |  | DELAY - MITIGATION | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | ITP | 2021-05-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 146065000 | 2013 | 169390619 | 211189224 |  | DELAY - MITIGATION | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
200220 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | ITP | 2021-05-01 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 16324800 | 2013 | 18931763 | 13119129 |  | DELAY - MITIGATION | 640503 | Holt County 345 kV |  |  | Build new Holt County 345 kV substation tap on the Grand Island - Fort Thompson 345 kV line owned by WAPA. Install necessary terminal equipment at new substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200395 | 31068 | 50447 | SPS | TX | Multi - Tuco - Yoakum 345/230 kV Ckt 1 | Tuco - Yoakum 345 kV Ckt 1 | Regional Reliability | ITP |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 128473352 | 2016 | 138351748 | 124076024 |  | DELAY - MITIGATION | 525832 | TUCO Interchange 345 kV | 526462 |  | Construct new 107-mile 345 kV line from Tuco to Yoakum. Install any necessary 345 kV terminal equipment at Yoakum associated with new 345/230 kV transformer. | 345 | 107
210484 | 31068 | 50451 | SPS | TX | Multi - Tuco - Yoakum 345/230 kV Ckt 1 | Yoakum 345/230 kV Ckt 1 Transformer | Regional Reliability | HP | 2019-06-01 | 2017-06-01 | 2018-04-27 | HPILS | 5047344 | 2016 | 5435437 | 4703455 |  | IN SERVICE | 526462 |  | 526460 | Amoco Switching Station 230 kV (Amoco Slaughter) | Install new 345/230 kV 640 MVA transformer at Yoakum substation. Install any necessary 230 kV terminal equipment. | 345/230
210484 | 30376 | 50452 | SPS | NM | Multi - Hobbs - Yoakum 345/230 kV Ckt 1 | Hobbs 345/230 kV Ckt 1 Transformer | High Priority | HP | 2018-03-24 | 2018-06-01 | 2018-04-27 | HPILS | 16204449 | 2014 | 18333847 | 13759261 | 14113711 | IN SERVICE | 527896 | Hobbs Interchange 345 kV | 527894 | Hobbs Interchange 230 kV | Expand existing Hobbs substation to accommodate 345 kV terminals. Install 345/230 kV 638 MVA transformer at Hobbs. | 345/230
200190 | 805 | 50453 | SPS | TX | Multi - Bowers - Howard 115 kV Ckt 1 | Bowers - Howard 115 kV | Regional Reliability | TS | 2016-02-28 | 2013-06-01 | 2013-01-18 | DPA-2011-SEPTEMBER-095 | 30851077 | 2013 | 35777791 | 41063661 | 35910939 | COMPLETE | 523748 | Bowers Interchange 115 kV | 523797 | Howard 115 kV | Build new 38-mile 115 kV line from Bowers Interchange - Howard. At Bowers, install 115 kV breaker positions to serve the new transmission line, converting to a three-breaker ring configuration. | 115 | 33
200309 | 30376 | 50457 | SPS | NM/TX | Multi - Hobbs - Yoakum 345/230 kV Ckt 1 | Hobbs - Yoakum 345 kV Ckt 1 | High Priority | HP | 2020-06-01 | 2020-06-01 | 2014-12-03 | HPILS | 90628750 | 2014 | 102538112 | 75976192 |  | ON SCHEDULE < 4 | 526462 |  | 527896 | Hobbs Interchange 345 kV | Construct new 52-mile 345 kV line from Hobbs to Yoakum. | 345 | 52
| 30401 | 50492 | TBD | NE | Cass Co. - S.W. Omaha (aka S3454) 345 kV | Cass Co. - S.W. Omaha (aka S3454) 345 kV Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 33126800 |  | IDENTIFIED | 645740 | Sub 3740 | 645454 | Sub 3454 | Build new 28 miles 345 kV Cass Co. - S.W. Omaha (aka S3454) and associated terminal equipment | 345 | 28
| 30402 | 50493 | OPPD | NE | Xfr- S3459-S1209 345/161 transformer no. 2 | S3459 345/161 kV Transformer Ckt 2 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED | 645459 | Sub 3459 | 646209 | Sub 1209 | Install 2nd 345/161 kV 560 MVA S3459 transformer | 345/161
200190 | 30410 | 50503 | SPS | TX | Line - Bowers - Canadian 69 kV Rebuild | Bowers - Canadian 69 kV Rebuild | Regional Reliability | TS | 2015-07-01 | 2012-06-01 | 2013-01-18 | DPA-2011-SEPTEMBER-095 | 34999584 | 2013 | 40588787 | 31779309 | 31779309 | COMPLETE | 523747 | Bowers Interchange 69 kV | 523579 | Canadian Sub 69 kV | Rebuild 49-mile 69 kV line between Bowers and Canadian with 795 ACSR conductor. | 69 | 39 | 10
200262 | 30420 | 50513 | SPS | TX | Line - Bushland Interchange - Deaf Smith County Interchange 230 kV Ckt 1 | Bushland Interchange - Deaf Smith Co Interchange 230 kV Ckt 1 Terminal Upgrade | Regional Reliability | TS | 2017-12-15 | 2014-02-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 285176 | 2014 | 322650 | 261084 |  | COMPLETE | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Upgrade 800 Amp wave trap at both Bushland Interchange and Deaf Smith Interchange. | 230
200193 | 30422 | 50515 | SPS | TX | XFR - Deaf Smith County Interchange 230/115 kV transformer CKT 1 | Deaf Smith County Interchange 230/115 kV Transformer Ckt 1 #2 | Regional Reliability | TS | 2016-02-25 | 2012-06-01 | 2012-11-20 | SPP-2010-AGP1-AFS-8 | 4273633 | 2012 | 5080007 | 3428156 | 3428156 | COMPLETE | 524623 | Deaf Smith County Interchange 230 kV | 524622 | Deaf Smith County Interchange 115 kV | Upgrade Deaf Smith County Interchange 230/115 kV Ckt 1 transformer to 250 MVA. | 230/115
200214 | 30423 | 50516 | SPS | TX | XFR - Deaf Smith County Interchange 230/115 kV Ckt 2 | Deaf Smith County Interchange 230/115 kV Transformer Ckt 2 | Regional Reliability | ITP | 2016-05-12 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 4225233 | 2013 | 4899975 | 2778128 |  | COMPLETE | 524623 | Deaf Smith County Interchange 230 kV | 524622 | Deaf Smith County Interchange 115 kV | Upgrade Deaf Smith Interchange 230/115 kV transformer Ckt 2 to 250 MVA. | 230/115
200214 | 30424 | 50517 | SPS | TX/OK | Line - Ochiltree - Tri-County Cole 115 kV Ckt 1 | Ochiltree - Tri-County REC Cole 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2015-11-20 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 11332148 | 2013 | 13141817 | 13096041 | 13096041 | COMPLETE | 523154 | Ochilltree Interchange 115 kV | 523120 | Cole Interchange 115 kV | Rebuild 16.9-mile 115 kV line from Ochiltree to Tri-County REC Cole Ckt 1. | 115 | 17
200216 | 30436 | 50531 | AEP | TX | Line - New Gladewater - Perdue 138 kV | New Gladewater - Perdue 138 kV Ckt 1 | Regional Reliability | ITP | 2014-12-31 | 2016-06-01 | 2013-02-20 | 2013 ITPNT | 1000000 | 2013 | 1159693 | 1000000 |  | COMPLETE | 508560 | NEW GLADEWATER | 508351 | PERDUE 138KV | Replace 138 kV breaker at Perdue. | 138
200242 | 30437 | 50532 | WR | KS | Multi - Geary County 345/115 kV and Geary - Chapman 115 kV | Geary County 345/115 kV Substation | Regional Reliability | ITP | 2018-06-01 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 20530196 | 2014 | 23228032 | 23813276 | 2632133 | COMPLETE | 532767 | Geary County 345 kV | 533336 | Geary County 115 kV | Build new Geary County 345/115 kV substation south of Junction City where JEC - Summit 345 kV and McDowell Creek - Junction City #2 115 kV circuits separate. Install 345/115 kV 440 MVA transformer and 115 kV terminal equipment. | 345/115
200241 | 30438 | 50533 | GRDA | OK | Line - Kerr - 412 Sub 161 kV Ckt 1 | Kerr - 412 Sub 161 kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 161100 | 2014 | 182270 | 161100 | 207691 | COMPLETE | 512637 | 412SUB 161 | 512635 | KERR 161 | Replace 1200 Amp switch with a 2000 Amp switch at Kerr substation 161 kV bus. | 161
200242 | 30437 | 50534 | WR | KS | Multi - Geary County 345/115 kV and Geary - Chapman 115 kV | Chapman Junction - Geary County 115 kV Ckt 1 | Regional Reliability | ITP | 2018-12-13 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 27938225 | 2014 | 31609537 | 30873104 | 30873104 | COMPLETE | 533336 | Geary County 115 kV | 533362 | CHAPMAN 115 KV | Build new 15.1-mile 115kV line between the new Geary County substation and Chapman Tap. 10.4 miles of the line will be built as a 2nd circuit to the existing Summit - McDowell Creek 345 kV line. | 115 | 4.67 | 10.42
200241 | 30440 | 50535 | GRDA | OK | Line - 412 Sub - Kansas Tap 161 kV Ckt 1 | 412 Sub - Kansas Tap 161 kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2014-02-19 | 2014 ITPNT | 54500 | 2014 | 61662 | 294840 |  | COMPLETE | 512637 | 412SUB 161 | 512714 | KANSAS TAP 161 | Replace 1200 Amp switch with a 2000 Amp switch at Kansas Tap substation 161 kV bus. | 161
200384 | 30444 | 50539 | SPS | TX | Device - Cochran 115 kV Cap Bank | Cochran 115 kV Cap Bank | Regional Reliability | TS | 2018-12-20 | 2016-06-01 | 2016-04-20 | DPA-2013-JUN-342 | 1808805 | 2016 | 1947885 | 2442000 |  | IN SERVICE | 526361 | Cochran Interchange 115 kV |  |  | Install 28.8-MVAR capacitor bank at Cochran 115 kV (two 14.4-MVAR stages). | 115
200231 | 30449 | 50545 | AEP | LA | Line - Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Rock Hill - Springridge Pan-Harr REC 138 kV Ckt 1 | Regional Reliability | ITP | 2016-09-19 | 2014-06-01 | 2013-09-23 | 2013 ITPNT | 25060655 | 2013 | 29062677 | 25060655 |  | COMPLETE | 509083 | ROCK HILL 138 | 507757 | SPRINGRIDGE PAN-HARR REC | Rebuild 27.6-mile 138 kV line from Rock Hill to Springridge Pan-Harr REC with 1926.9 ACSR/TW conductor. | 138 | 27.6
200214 | 30451 | 50546 | SPS | NM | Line - Atoka - Eagle Creek 115 kV Ckt 1 | Atoka - Eagle Creek 115 kV Ckt 1 | Regional Reliability | ITP | 2018-12-31 | 2015-06-01 | 2013-02-20 | 2013 ITPNT | 20808304 | 2013 | 24131253 | 22500000 |  | IN SERVICE | 527786 | Atoka Interchange 115 kV | 527711 | Eagle Creek 115 kV | Build new 12-mile 115 kV line from Atoka to Eagle Creek and install necessary terminal equipment. | 115 | 22.1
200214 | 30466 | 50560 | SPS | NM | XFR - Potash Junction 115/69 kV Ckt 1 | Potash Junction 115/69 kV Transformer Ckt 1 | Regional Reliability | ITP | 2015-08-07 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 2127697 | 2013 | 2467476 | 2422732 | 2422732 | COMPLETE | 527962 | Potash Junction Interchange 115 kV | 527961 | Potash Junction Interchange 69 kV | Upgrade Potash Junction 115/69 kV transformer Ckt 1 to 84 MVA. | 115/69
200229 | 30469 | 50563 | SPS | NM | Multi - Kilgore Switch - South Portales - Market St. - Portales 115 kV | Kilgore Switch - South Portales 115 kV Ckt 1 | Regional Reliability | ITP | 2018-02-07 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 5136476 | 2013 | 5956737 | 4513245 | 4604052 | COMPLETE | 524935 | Zodiac Sub 115 kV | 524949 | S Portales 115 kV | Build new 5.3-mile 115 kV line from the switching station east of Kilgore substation to South Portales and install necessary terminal equipment. | 115 | 5.3
200229 | 30469 | 50564 | SPS | NM | Multi - Kilgore Switch - South Portales - Market St. - Portales 115 kV | Market St. - South Portales 115 kV Ckt 1 | Regional Reliability | ITP | 2018-07-11 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 6498682 | 2013 | 7536479 | 4656008 | 4850346 | COMPLETE | 524949 | S Portales 115 kV | 524950 | Market ST 115 kV | Build new 6-mile 115 kV line from South Portales to Market St. and install necessary terminal equipment. | 115 | 6
200229 | 30469 | 50565 | SPS | NM | Multi - Kilgore Switch - South Portales - Market St. - Portales 115 kV | Market St. - Portales 115 kV Ckt 1 | Regional Reliability | ITP | 2018-02-07 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 15394429 | 2013 | 17852818 | 14407777 | 15189905 | COMPLETE | 524950 | Market ST 115 kV | 524924 | Portales Interchange 115 kV | Build new 10.4-mile 115 kV line from Market St. to Portales and install necessary terminal equipment. | 115 | 10.4
200216 | 30473 | 50569 | AEP | AR | Line - Midland REC - North Huntington 69 kV | Midland REC - North Huntington 69 kV Ckt 1 | Regional Reliability | ITP | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 1829026 | 2013 | 2121109 | 1829026 | 11990487 | COMPLETE | 507196 | MIDLAND REC | 507188 | NORTH HUNTINGTON 69KV | Rebuild 4.0-mile 69 kV line from Midland REC to North Huntington with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, and jumpers at North Huntington. | 69 | 1.3
200216 | 30474 | 50570 | AEP | AR | Line - Midland - Midland REC 69 kV | Midland - Midland REC 69 kV Ckt 1 | Regional Reliability | ITP | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 5653353 | 2013 | 6556157 | 5653353 |  | COMPLETE | 507187 | MIDLAND | 507196 | MIDLAND REC | Rebuild 1.3-mile 69 kV line from Midland to Midland REC with 1233.6 ACSR/TW. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 4.3
200216 | 30475 | 50571 | AEP | AR | Line - Howe Interchange - Midland 69 kV | Howe Interchange - Midland 69 kV Ckt 1 | Regional Reliability | ITP | 2015-05-15 | 2013-06-01 | 2013-02-20 | 2013 ITPNT | 9145130 | 2013 | 10605547 | 9145130 |  | COMPLETE | 515259 | HOWE INT 69 | 507187 | MIDLAND | Rebuild 7.0-mile portion of the 69 kV line from Howe Interchange to Midland with 1233.6 ACSR/TW. The portion of line to be rebuilt is from the state line to Midland. Upgrade CT ratios, relay settings, switches, and station conductors at Midland. | 69 | 7
200207 | 30478 | 50574 | OPPD | NE | Line - 6815 Tap South in Ckt 623 - Sub 6815 T3 69 kV Ckt 1 | 6815 Tap South - Sub 6815 T3 69 kV Ckt 1 | Regional Reliability | ITP | 2015-03-13 | 2015-06-01 | 2013-02-20 | 2013 ITPNT | 260590 | 2013 | 302205 | 439561 | 439561 | CLOSED OUT | 647016 | 915 Tap in Ckt 623 | 647815 |  | Rebuild 0.7-mile 69 kV line from S6815 Tap South to Sub S6815 T2. | 69 |  | 0.71
210523 | 30484 | 50582 | WR | KS | Multi - Viola 345/138kV Transformer and 138 kV Lines to Clearwater and Gill | Viola 345/138 kV Transformer Ckt 1 | Regional Reliability | ITP | 2018-04-19 | 2018-06-01 | 2019-09-20 | 2013 ITPNT | 10144608 | 2019 | 10144608 | 10144608 | 10144608 | COMPLETE | 532798 | Viola 7 | 533075 | Viola 138kV | Install new 345/138 kV transformer at Viola substation. | 345/138
200228 | 30484 | 50583 | WR | KS | Multi - Viola 345/138kV Transformer and 138 kV Lines to Clearwater and Gill | Clearwater - Viola 138 kV Ckt 1 | Regional Reliability | ITP | 2018-11-16 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 23266941 | 2019 | 23266941 | 23266941 | 166939 | COMPLETE | 533075 | Viola 138kV | 533036 | CLEARWATER 138KV | Build new 21.8-mile 138 kV line from new Viola substation to Clearwater 138 kV substation. | 138 | 21.8
200228 | 30484 | 50584 | WR | KS | Multi - Viola 345/138kV Transformer and 138 kV Lines to Clearwater and Gill | Gill - Viola 138 kV Ckt 1 | Regional Reliability | ITP | 2018-11-16 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 18318471 | 2019 | 18318471 | 18318471 | 18318471 | COMPLETE | 533075 | Viola 138kV | 533045 | GILL ENERGY CENTER WEST 138 KV | Build new 27.9-mile 138 kV line from new Viola substation to Gill 138 kV substation. | 138 | 27.9
200200 | 30491 | 50600 | WFEC | OK | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | TS | 2017-03-01 | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 274847 | 735000 |  | COMPLETE | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69
200242 | 30437 | 50605 | WR | KS | Multi - Geary County 345/115 kV and Geary - Chapman 115 kV | Geary County 345 kV | Regional Reliability | ITP | 2018-05-17 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 16190561 | 2014 | 18318134 | 14381297 | 14381297 | COMPLETE | 532767 | Geary County 345 kV |  |  | Install 345 kV ring bus at the new Geary County substation. | 345
200231 | 30495 | 50607 | AEP | LA | Sub - Messick 500/230 kV | Layfield 500/230 kV Transformer Ckt 1 | Regional Reliability | ITP | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 30369537 | 2013 | 35219352 | 22851755 |  | COMPLETE | 999113 | Messick 500 kV | 999114 |  | Build Messick 500/230 kV substation. Connect to Carrol, Clarence, and Western Kraft 230 kV lines. Install 500/230 kV 675 MVA transformer. This upgrade is contingent upon approval from Cleco Power LLC. | 500/230
200400 | 30496 | 50609 | NPPD | NE | Multi - Bobcat Canyon 345/115 kV and Bobcat Canyon - Scottsbluff 115 kV | Bobcat Canyon - Scottsbluff 115 kV Ckt 1 | Regional Reliability | ITP | 2017-10-26 | 2014-06-01 | 2016-08-17 | 2014 ITPNT | 26027015 | 2016 | 28028248 | 21204480 | 21204480 | COMPLETE | 640530 | Stegall 115 kV | 640338 | Scottsbluff | Install new 22-mile 115 kV line from Bobcat Canyon to Scottsbluff and install any necessary terminal equipment. | 115 | 23
200228 | 30484 | 50612 | WR | KS | Multi - Viola 345/138kV Transformer and 138 kV Lines to Clearwater and Gill | Viola 345 kV Terminal Equipment | Regional Reliability | ITP | 2018-04-19 | 2018-06-01 | 2013-09-10 | 2013 ITPNT | 2393900 | 2019 | 2393900 | 2393900 | 2393900 | COMPLETE | 532798 | Viola 7 |  |  | Install 345 kV breakers at Viola substation. | 345
200231 | 30495 | 50615 | AEP | LA | Sub - Messick 500/230 kV | Layfield 500 kV Terminal Upgrades | Regional Reliability | ITP | 2016-04-29 | 2013-06-01 | 2013-09-23 | 2013 ITPNT | 21508234 | 2013 | 24942957 | 32212715 |  | COMPLETE | 999113 | Messick 500 kV |  |  | Install terminal equipment on 500 kV side of new Messick substation. Connect to Mt. Olive - Hartburg 500 kV line. This upgrade is contingent upon approval from Cleco Power LLC for Upgrade ID 50607. | 500
200234 | 30503 | 50628 | WFEC | OK | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | TS | 2017-03-01 | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 214548 | 0 |  | COMPLETE | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69
200369 | 30509 | 50636 | SPS | TX | Line - Canyon East Sub - Canyon West Sub 115 kV Ckt 1 | Canyon East Sub - Canyon West Sub 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2016-05-18 | 2014-02-01 | 2016-02-12 | SPP-2011-AG3-AFS-11 | 2694811 | 2016 | 2902017 | 5013917 | 5013917 | COMPLETE | 524523 | Canyon East Sub 115 kV | 524516 | Canyon West Sub 115 kV | Rebuild 3.73-mile 115 kV line from Canyon East Sub to Canyon West Sub. | 115 | 3.7
200262 | 30510 | 50637 | SPS | TX | Line - Mustang - Shell CO2 115 kV Ckt 1 | Mustang - Shell CO2 115 kV Ckt 1 | Transmission Service | TS | 2019-05-01 | 2015-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 15473119 | 2014 | 17506414 | 19100000 |  | IN SERVICE | 527146 | Mustang Interchange North Bus 115 kV | 527062 | Shell Co2 Gas Sub 115 kV | Construct new 7.7-mile 115 kV line from Mustang to Shell CO2. | 115 | 7.71
200410 | 30552 | 50690 | SPS | NM | Line - Oxy Permian Sub - West Bender Sub 115 kV Ckt 1 | Oxy Permian Sub - West Bender Sub 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2016-10-28 | 2018-06-01 | 2016-08-17 | 2014 ITPNT | 973674 | 2013 | 1129163 | 742000 |  | COMPLETE | 528575 | OXY Permian Sub 115 kV | 528449 | West Bender Sub 115 kV | Rebuild 0.5-mile 115 kV line from Oxy Permian Sub to West Bender Sub. | 115 |  | 0.5
200256 | 30555 | 50693 | SPS | NM | Quahada Switching Station 115 kV | Quahada Switching Station 115 kV | Regional Reliability | ITP | 2015-07-09 | 2015-06-01 | 2014-02-19 | 2014 ITPNT | 6943260 | 2014 | 7855661 | 7668328 | 7668328 | COMPLETE | 528394 | Quahada 115 kV |  |  | Install 4-breaker ring bus at Quahada to connect the 115 kV lines from Cunningham to PCA Interchange and Lea National to Maljamar. | 115 | 0.68
200296 | 30560 | 50698 | WR | KS | Line - Sumner County - Viola 138 kV Ckt 1 | Sumner County - Viola 138 kV Ckt 1 | Zonal Reliability | ITP | 2020-06-01 | 2019-06-01 | 2014-09-02 | 2014 ITPNT | 34432188 | 2019 | 34432188 | 34432188 |  | DELAY - MITIGATION | 532984 | SUMNER COUNTY 138 kV | 533075 | Viola 138kV | Build new 28-mile 138 kV line from Viola to Sumner County. | 138 | 28
200245 | 30563 | 50702 | WFEC | OK | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | ITP | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 570230 | 504000 |  | COMPLETE | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138
200309 | 30569 | 50708 | SPS | NM | Multi - Potash Junction - Road Runner 230/115 kV Ckt 1 | Potash Junction - Road Runner 230 kV Ckt 1 | High Priority | HP | 2015-10-27 | 2015-06-01 | 2014-12-03 | HPILS | 43096827 | 2014 | 48760104 | 48902600 |  | COMPLETE | 527965 |  | 528027 | Road Runner 345 kV | Construct new 40-mile 345 kV line operated at 230 kV from Potash Junction to Road Runner. | 230 | 40.4
200309 | 30569 | 50709 | SPS | NM | Multi - Potash Junction - Road Runner 230/115 kV Ckt 1 | Road Runner 230/115 kV Substation | High Priority | HP | 2015-10-27 | 2015-06-01 | 2014-12-03 | HPILS | 10576672 | 2014 | 11966534 | 11574381 | 59848300 | COMPLETE | 528027 | Road Runner 345 kV | 528025 | Road Runner 115 kV | Construct new 230 kV Road Runner substation, tapping the existing 115 kV line from Red Bluff to Agave Hills. Construct substation to accommodate future 345 kV line terminal from Potash Junction. Install new 230/115 kV 288 MVA transformer at new Road Runner substation. Install any necessary terminal equipment. | 230/115 | 1
200246 | 30573 | 50718 | AEP | LA | Line - Broadmoor - Fort Humbug 69 kV Ckt 1 | Broadmoor - Fort Humbug 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-06-21 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 6695986 | 2014 | 7575893 | 6695986 |  | COMPLETE | 507716 | BROADMOOR | 507730 | FORT HUMBUG 69KV | Rebuild 1.7-mile 69 kV line from Fort Humbug to Broadmoor with 1233.6 ACSR/TW conductor. Upgrade jumpers at Fort Humbug along with jumpers and bus at Broadmoor. | 69 |  | 1.7
200246 | 30574 | 50719 | AEP | TX | Line - Daingerfield - Jenkins Rec 69 kV Ckt 1 Rebuild | Daingerfield - Jenkins REC T 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-11-09 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 2819806 | 2014 | 3190352 | 2819806 |  | COMPLETE | 508288 | DAINGERFIELD | 508293 | JENKINS REC T | Rebuild 1.3-mile 69 kV line from Daingerfield to Jenkins REC T with 959.6 ACSR/TW conductor. | 69 |  | 1.3
200246 | 30575 | 50720 | AEP | TX | Line - Hallsville - Longview Heights 69 kV Ckt 1 | Hallsville - Longview Heights 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-03-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 8851677 | 2014 | 10014860 | 11571330 |  | COMPLETE | 508543 | HALLSVILLE | 508553 | LONGVIEW HEIGHTS 69KV | Rebuild 6.6-mile 69 kV line from Longview Heights to Hallsville with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Longview Heights. | 69 |  | 6.6
200246 | 30576 | 50721 | AEP | TX | Line - Hallsville - Marshall 69 kV Ckt 1 | Hallsville - Marshall 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-06-02 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 15248925 | 2014 | 17252760 | 19751448 |  | COMPLETE | 508556 | MARSHALL 69KV | 508543 | HALLSVILLE | Rebuild 11.2-mile 69 kV line from Hallsville to Marshall with 1233.6 ACSR/TW conductor. Upgrade jumpers, CT ratios, and relay settings at Marshall. | 69 |  | 11.2
200256 | 30577 | 50722 | SPS | NM | Line - Chavis - Price - CV Pines - Capitan 115 kV Ckt 1 | Chaves - Price 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-30 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 4701279 | 2014 | 5319066 | 5961279 | 11926147 | COMPLETE | 527482 | Chaves County Interchange 115 kV | 527543 | PRICE 3 115 kV | Rebuild 5-mile 69 kV line from Chaves to Price converting to 115 kV. Install any necessary terminal equipment at Chaves. | 115 | 5 |  | 5
200256 | 30577 | 50723 | SPS | NM | Line - Chavis - Price - CV Pines - Capitan 115 kV Ckt 1 | CV Pines - Price 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-30 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 4158668 | 2014 | 4705151 | 4319668 |  | COMPLETE | 527543 | PRICE 3 115 kV | 527542 | CV-PINES 3 115 kV | Rebuild 3-mile 69 kV line from CV Pines to Price converting to 115 kV. | 115 |  |  | 3
200256 | 30577 | 50724 | SPS | NM | Line - Chavis - Price - CV Pines - Capitan 115 kV Ckt 1 | Capitan - CV Pines 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-30 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 5415053 | 2014 | 6126635 | 4343227 | 1727131 | COMPLETE | 527542 | CV-PINES 3 115 kV | 527541 | Capitan 115 kV | Rebuild 5-mile 69 kV line from Capitan to CV Pines converting to 115 kV. | 115 | 5 |  | 5
200475 | 30580 | 50733 | WR | KS | Line - Crestview - Kenmar 69 kV | Kenmar - Northeast 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-11-07 | 2014-06-01 | 2018-02-21 | 2014 ITPNT | 5590592 | 2014 | 6325242 | 5531119 | 5246249 | COMPLETE | 533822 | NORTHEAST 69 KV | 533811 | KEN MAR 69 KV | Rebuild 1.74-mile 69 kV line from Kenmar to Northeast with single 1192 ACSR to achieve 124 MVA minimum ampacity. | 69 |  | 1.74
200242 | 30584 | 50739 | WR | KS | Line - Montgomery - Sedan 69 kV Ckt 1 | Elk Junction - Montgomery 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2017-12-28 | 2018-06-01 | 2014-02-19 | 2014 ITPNT | 16110343 | 2016 | 17349077 | 17074331 | 12634488 | COMPLETE | 533698 | MONTGOMERY 69 KV | 533690 | ELK JUNCTION 69 KV | Rebuild 9.7-mile 69 kV line from Elk Junction to Montgomery to achieve new emergency rating of 72 MVA. | 69 |  | 7.9
200242 | 30584 | 50740 | WR | KS | Line - Montgomery - Sedan 69 kV Ckt 1 | Elk Junction - Sedan 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-09-11 | 2018-06-01 | 2014-02-19 | 2014 ITPNT | 19015228 | 2016 | 20477321 | 17965350 |  | IN SERVICE | 533690 | ELK JUNCTION 69 KV | 533544 | CANEY VALLEY NO. 5 SEDAN 69 KV | Rebuild 18.8-mile 69 kV line from Elk Junction to Sedan to achieve new emergency rating of 72 MVA. | 69 |  | 19
200320 | 30588 | 50745 | OPPD | NE | Multi - Fremont - S991 E 161/69 kV Ckt 1 | Fremont 161/69 kV Transformer Ckt 1 | Regional Reliability | ITP | 2019-04-30 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 1952654 | 2018 | 2001470 | 2075199 | 2075199 | CLOSED OUT | 646291 |  | 647291 |  | Install new 161/69 kV transformer at Fremont to accommodate a new 161 kV interconnection. | 161/69
200320 | 30588 | 50746 | OPPD | NE | Multi - Fremont - S991 E 161/69 kV Ckt 1 | Fremont - S991 E 69 kV Ckt 1 | Regional Reliability | ITP | 2019-04-30 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 4854430 | 2018 | 4975791 | 4254712 | 4254712 | CLOSED OUT | 647422 | Fremont Sub B | 647291 |  | Build new 3-mile 69 kV line from Fremont to new substation S991 E. | 161/69 | 3.5
200320 | 30588 | 50747 | OPPD | NE | Multi - Fremont - S991 E 161/69 kV Ckt 1 | S1226 161kV Ckt 1 | Regional Reliability | ITP | 2019-04-30 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 20690401 | 2018 | 21207661 | 20150325 | 20150325 | CLOSED OUT | 646226 | Sub 1226 | 646291 |  | Build new 17-mile 161 kV line from S1226 to new substation S1301. | 161 | 19.4
200258 | 30590 | 50748 | OPPD | NE | Multi - S906 - S912 69 kV | S906 - S924 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-06-01 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 1360327 | 2014 | 1539085 | 1143763 | 1143763 | CLOSED OUT | 647906 | Sub 906 South Bus | 647924 | Sub 924 | Rebuild 1.34-mile 69 kV line from S906 to S924 to achieve a new emergency rating of 143 MVA. | 69 |  | 1.34
200258 | 30590 | 50749 | OPPD | NE | Multi - S906 - S912 69 kV | S924 - S912 69 kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP | 2018-06-01 | 2019-06-01 | 2014-02-19 | 2014 ITPNT | 69679 | 2014 | 78835 | 128670 | 128670 | CLOSED OUT | 647912 | Sub 912 | 647924 | Sub 924 | Install terminal upgrades at S924 to increase emergency rating of S924 - S912 69 kV Ckt 1 to 99 MVA. | 69
200256 | 856 | 50754 | SPS | TX | Multi - Centre St. - Hereford NE 115 kV Ckt 1 and Centre St. and Hereford 115 kV Load Conversion | Hereford 115 kV Load Conversion | Regional Reliability | ITP | 2016-12-15 | 2014-06-01 | 2014-02-19 | 2014 ITPNT | 435146 | 2014 | 492328 | 727279 | 740694 | COMPLETE | 524606 | Hereford Interchange 115 kV |  |  | Convert distribution transformer high side at Hereford from 69 kV to 115 kV. | 115
200294 | 30596 | 50757 | NPPD | NE | Multi - Broken Bow Wind - Ord 115 kV Ckt 1 | Broken Bow Wind - Ord 115 kV Ckt 1 | Regional Reliability | ITP | 2018-03-01 | 2014-06-01 | 2014-08-26 | 2014 ITPNT | 28018664 | 2018 | 28719131 | 23583074 | 23583074 | COMPLETE | 640445 | Broken Bow Wind | 640308 | Ord | Build a new 35-mile 115 kV line from Ord to Broken Bow Wind and install necessary terminal equipment. | 115 | 42
200392 | 30597 | 50758 | OGE | OK | Multi - Knob Hill - Lane - Noel 138 kV Ckt 1 | Knob Hill - Lane - Noel 138 kV Ckt 1 | Regional Reliability | ITP | 2018-09-30 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4009000 | 2016 | 4317255 | 4647152 | 4367290 | COMPLETE | 514795 | KNOBHILL 138 | 514794 | KNOBHILL 69 | Build new Lane 138 kV substation adjacent to existing Knob Hill substation. Install a new 138 kV terminal at Knob Hill. Tie the Knob Hill and Lane substations together with one span of 138 kV line. Build new 1.5-mile 138 line from Lane to Noel. Install fiber optics on 138 kV circuit connecting Knob Hill to Lane to Noel. | 138 | 1.65
200361 | 30598 | 50759 | AEP | TX | Device - Letourneau 69 kV Cap Bank | Letourneau 69 kV Cap Bank | Regional Reliability | ITP | 2017-06-26 | 2017-06-01 | 2015-12-11 | 2016 ITPNT | 1409347 | 2016 | 1517713 | 1409347 |  | COMPLETE | 508536 | LETOURNEAU STEEL | 508594 | Letouteau W tap 69 kV | Install 16.2-MVAR 69 kV capacitor bank at Letourneau. | 69
200294 | 30596 | 50760 | NPPD | NE | Multi - Broken Bow Wind - Ord 115 kV Ckt 1 | North Loup - Ord 115 kV Ckt 1 | Regional Reliability | ITP | 2018-06-01 | 2014-06-01 | 2014-08-26 | 2014 ITPNT | 516009 | 2018 | 528909 | 548029 | 548029 | COMPLETE | 640284 | North Loup | 640308 | Ord | Increase line clearance on 115 kV line from North Loup to Ord to 100 degree C. Upgrade disconnect switches, CTs, and jumpers at North Loup. | 115
200255 | 30361 | 50768 | AEP | OK | Multi - Chisholm - Gracemont 345 kV | Chisholm 230 kV | Regional Reliability | ITP | 2017-12-07 | 2018-03-01 | 2014-02-06 | 2012 ITP10 | 1270623 | 2017 | 1334948 | 1270623 |  | COMPLETE | 700345 | Chisholm 345 kV |  |  | Install approximately 2 miles of 230 kV transmission line for a cut-in to existing 230 kV line from Sweetwater to Elk City, creating termination points at new Chisholm substation. | 230 | 2
| 30599 | 50769 | AEP | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | South Fayetteville 345/161 kV Transformer Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED |  |  |  |  | Install new 345/161 kV Transformer at South Fayetteville. | 345/161
| 30599 | 50770 | TBD | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | Chamber Springs - South Fayetteville 345 kV Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 21295800 |  | IDENTIFIED |  |  |  |  | Build new 345 kV line from Chamber Springs to South Fayetteville and associated terminal equipment. | 345 | 18
| 30600 | 50771 | GMO | MO | XFR - Maryville 345/161 kV | Maryville 345/161 kV Transformer Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED | 541197 | Maryville 345 kV | 300097 | Maryville | Install new 345/161 transformer at Maryville. | 345/161
| 30601 | 50772 | KCPL | KS | XFR - Nashua 345/161 kV | Nashua 345/161 kV Transformer Upgrade Ckt11 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED |  |  |  |  | Increase rating of Nashua transformer to 650/715 MVA. | 345/161
| 30602 | 50773 | TBD | NE | Line - Keystone - Red Willow 345 kV | Keystone - Red Willow 345 kV Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 130141000 |  | IDENTIFIED | 640252 | Keystone | 640325 | Red Willow | Build new 110 mile 345 kV line from Keystone to Red Willow and associated terminal equipment. | 345 | 110
| 30603 | 50774 | TBD | TX | Line - Tolk - Tuco 345 kV | Tolk - Tuco 345 kV Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 75718400 |  | IDENTIFIED | 525549 | Tolk Station 345 kV | 525832 | TUCO Interchange 345 kV | Build new 64 mile 345 kV line from Tolk to Tuco and associated terminal equipment. | 345 | 64
| 30604 | 50775 | SEPC | KS | XFR - 2nd Holcomb 345/115 kV | Holcomb 345/115 kV Transformer Ckt2 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED | 531449 | HOLCOMB | 531448 | HOLCOMB | Install 2nd 345/115 kV transformer at Holcomb. | 345/115
| 30605 | 50776 | TBD | KS | Line - Neosho - Wolf Creek 345 kV | Neosho - Wolf Creek 345 kV Ckt1 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 117126900 |  | IDENTIFIED | 532797 | WOLF CREEK 345 KV | 532793 | NEOSHO 345 KV | Build a new 86.4 mile 345kV line from Neosho to Wolf Creek rated at 1792 MVA | 345 | 86.4
| 30606 | 50777 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | Clinton - Truman 161 kV Ckt1 Reconductor | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 15701325 |  | IDENTIFIED | 300071 | Clinton | 505502 | Truman | Rebuild 29 mile 161 kV line from Clinton to Truman. | 161 |  | 29
| 30606 | 50778 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | North Warsaw - Truman 161 kV Ckt1 Reconductor | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 1082850 |  | IDENTIFIED | 505502 | Truman | 541314 | North Warsaw 161 | Rebuild 2 miles of 161 kV line from North Warsaw to Truman. | 161 |  | 2
| 30608 | 50779 | WR | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn 345/115 kV Transformer Ckt2 | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 12600000 |  | IDENTIFIED |  |  |  |  | Install new 345/115 kV transformer at Auburn. | 345/115
| 30608 | 50780 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Swissvale 345 kV Ckt1 Voltage Conversion | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 20112700 |  | IDENTIFIED |  |  |  |  | Convert 17 mile Auburn - Swissvale 230 kV line to a 345 kV line. | 345 |  |  | 17
| 30608 | 50781 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Jeffrey EC 345 kV Ckt1 Voltage Conversion | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 35493000 |  | IDENTIFIED |  |  |  |  | Convert the 30 mile Auburn - Jeffrey EC 230 kV to 345 kV. | 345 |  |  | 30
| 30607 | 50782 | OGE | OK | Sub - Muskogee/Pecan Creek 345 kV | Muskogee/Pecan Creek 345 kV Terminal Upgrades | ITP20 | ITP 20 |  | 2033-01-01 | [5 empty] | 34605675 |  | IDENTIFIED | 515224 | MUSKOGEE 345 | 515235 | PECAN CREEK 345 | Upgrade terminal equipment at Muskogee and Pecan Creek substations to increase Muskogee - Pecan Creek 345 kV Ckts 1 & 2 ratings to 1195/1195 MVA.
200256 | 30616 | 50794 | SPS | NM | Sub - Curry County 115 kV | Curry County Interchange 115 kV | Regional Reliability | ITP | 2018-05-07 | 2018-06-01 | 2014-02-19 | 2014 ITPNT | 813381 | 2014 | 920266 | 2965311 | 2831247 | COMPLETE | 524822 | Curry County Interchange 115 kV |  |  | Install two 115 kV breakers at Curry County Interchange to convert the high side of the Curry County distribution transformer to 115 kV. | 115
200310 | 30619 | 50802 | AEP | OK | Line - Darlington - Roman Nose 138 kV Ckt 1 | Darlington - Roman Nose 138 kV Ckt 1 (AEP) | High Priority | HP | 2017-06-29 | 2015-06-01 | 2014-12-02 | HPILS | 11652107 | 2014 | 13183289 | 11652107 | 11033623 | COMPLETE | 511559 |  | 514823 | ROMAN NOSE 138 | Construct AEP's portion of new 25-mile 138 kV line from Darlington to Roman Nose (OGE). | 138 | 14.25
200311 | 30622 | 50805 | OGE | OK | Multi - Knipe - SW Station - Linwood & Warwick Tap 138 kV Ckt 1 | SW Station - Warwick Tap 138 kV Ckt 1 | High Priority | HP | 2018-05-11 | 2018-06-01 | 2014-12-02 | HPILS | 12767120 | 2014 | 14444824 | 12767120 | 11352952 | COMPLETE | 515012 | SPRING VALLEY TAP 69 | 515047 | WARWICK 138 | Construct new 138 kV SW Station switching station. Construct new 13-mile 138 kV line from new SW Station switching station to Warwick Tap. | 138 | 14.22
200311 | 30622 | 50806 | OGE | OK | Multi - Knipe - SW Station - Linwood & Warwick Tap 138 kV Ckt 1 | Linwood - SW Station 138 kV Ckt 1 | High Priority | HP | 2018-05-11 | 2018-06-01 | 2014-12-02 | HPILS | 9899440 | 2014 | 11200308 | 9899440 | 8494353 | COMPLETE | 515401 | Pump Station 32 | 515012 | SPRING VALLEY TAP 69 | Construct new 18-mile 138 kV line from Linwood to new SW Station switching station. | 138 | 15.49
200311 | 30622 | 50807 | OGE | OK | Multi - Knipe - SW Station - Linwood & Warwick Tap 138 kV Ckt 1 | Knipe - SW Station 138 kV Ckt 1 | High Priority | HP | 2018-05-11 | 2018-06-01 | 2014-12-02 | HPILS | 8218020 | 2014 | 9297935 | 9128020 | 9409815 | COMPLETE | 515514 | Knipe 138 kV | 515012 | SPRING VALLEY TAP 69 | Construct new 5-mile 138 kV line from Knipe to new SW Station switching station. | 138 | 8.2
200309 | 30638 | 50819 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | China Draw - North Loving 345 kV Ckt 1 | High Priority | HP | 2018-05-30 | 2018-06-01 | 2014-12-03 | HPILS | 19255234 | 2014 | 21785530 | 19257479 | 20816118 | COMPLETE | 528185 |  | 528223 |  | Construct new 18.2-mile 345 kV line from North Loving to China Draw. | 345 | 18.2
200309 | 30638 | 50820 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | Kiowa - North Loving 345 kV Ckt 1 | High Priority | HP | 2018-05-21 | 2018-06-01 | 2014-12-03 | HPILS | 25716516 | 2014 | 29095877 | 24078943 | 25905391 | COMPLETE | 528185 |  | 527965 |  | Construct new 20.4-mile 345 kV line from new Kiowa substation to North Loving. | 345 | 20.4
200282 | 30824 | 50821 | SPS | NM | XFR - Potash Junction 230/115 kV Ckt 1 | Potash Junction 230/115 kV Ckt 1 | High Priority | HP | 2016-04-15 | 2015-06-01 | 2014-05-19 | HPILS | 3508346 | 2014 | 3969371 | 3782261 |  | COMPLETE | 527963 | Potash Junction Interchange 230 kV | 527962 | Potash Junction Interchange 115 kV | Upgrade 230/115 kV transformer at Potash Junction to 250 MVA. | 230/115
200309 | 30638 | 50849 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | China Draw 345/115 kV Ckt 1 Transformer | High Priority | HP | 2018-05-30 | 2018-06-01 | 2014-12-03 | HPILS | 4649045 | 2014 | 5259968 | 5305787 | 5434144 | COMPLETE | 528223 |  | 528222 | China Draw 115 kV | Install new 345/115 kV 448 MVA transformer at new China Draw substation. Install any necessary 115 kV terminal equipment and ring/breaker and a half 115 kV bus for 4 line or transformer terminals. | 345/115
200309 | 30638 | 50850 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | China Draw 345 kV Ckt 1 Terminal Upgrades | High Priority | HP | 2018-05-30 | 2018-06-01 | 2014-12-03 | HPILS | 4172734 | 2014 | 4721066 | 6369801 | 6110103 | COMPLETE | 528223 |  |  |  | Construct 345 kV ring bus, expandable to breaker and a half for 6 line or transformer terminals at China Draw. | 345
200309 | 30637 | 50851 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Ckt 1 | Kiowa 345 kV Substation | High Priority | HP | 2018-03-24 | 2018-06-01 | 2014-12-03 | HPILS | 10383515 | 2018 | 10643103 | 11984884 | 11806387 | COMPLETE | 527965 |  |  |  | Construct new Kiowa 345 kV substation adjacent to Potash Junction. 345 kV bus will be ring, expandable to minimum 6 line or transformer terminals. Install terminal equipment as needed. | 345
200309 | 30638 | 50852 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | North Loving 345/115 kV Ckt 1 Transformer | High Priority | HP | 2018-03-24 | 2018-06-01 | 2014-12-03 | HPILS | 5950217 | 2014 | 6732124 | 6646195 | 6814454 | COMPLETE | 528185 |  | 528186 |  | Install new 345/115 kV 448 MVA transformer at new North Loving substation. Install any necessary 115 kV terminal equipment. | 345/115
200309 | 30638 | 50854 | SPS | NM | Multi - Kiowa - North Loving - China Draw 345/115 kV Ckt 1 | North Loving 345 kV Terminal Upgrades | High Priority | HP | 2018-05-21 | 2018-06-01 | 2014-12-03 | HPILS | 7873653 | 2014 | 8908316 | 7690295 | 7318532 | COMPLETE | 528185 |  |  |  | Install 345 kV line terminals at North Loving substation for Kiowa and China Draw. Install any necessary 345 kV terminal equipment necessary to install 345/115 kV 448 MVA transformer at North Loving. | 345
200309 | 30639 | 50862 | SPS | NM | Multi - Potash Junction - Road Runner 345 kV Conv. and Transformers at Kiowa and Road Runner | Road Runner 345/115 kV Ckt 1 Transformer | High Priority | HP | 2018-04-27 | 2018-06-01 | 2014-12-03 | HPILS | 3989689 | 2014 | 4513967 | 6742788 | 6777778 | COMPLETE | 528027 | Road Runner 345 kV | 528025 | Road Runner 115 kV | Install new 345/115 kV 448 MVA transformer at new Road Runner substation. Install any necessary 115 kV terminal equipment. | 345/115
200309 | 30639 | 50863 | SPS | NM | Multi - Potash Junction - Road Runner 345 kV Conv. and Transformers at Kiowa and Road Runner | Road Runner 345 kV Substation Conversion | High Priority | HP | 2018-04-27 | 2018-06-01 | 2014-12-03 | HPILS | 11569711 | 2014 | 13090066 | 4804210 | 2626680 | COMPLETE | 528027 | Road Runner 345 kV |  |  | Convert 230 kV Road Runner substation to 345 kV. Install any necessary 345 kV terminal equipment. | 345
200371 | 30666 | 50864 | SPS | NM | Device - China Draw and Road Runner 115 kV SVC | China Draw 115 kV SVC | Regional Reliability | ITP | 2016-06-08 | 2015-04-01 | 2016-02-12 | 2015 ITPNT | 25925187 | 2015 | 28616556 | 25925187 |  | COMPLETE | 528220 |  |  |  | Install new SVC at China Draw 115 kV substation with effective range of -50/+200 MVAR. | 115
200309 | 30639 | 50868 | SPS | NM | Multi - Potash Junction - Road Runner 345 kV Conv. and Transformers at Kiowa and Road Runner | Kiowa 345/115 kV Ckt 1 Transformer | High Priority | HP | 2018-04-27 | 2018-06-01 | 2014-12-03 | HPILS | 5443140 | 2014 | 6158413 | 5887848 | 6133123 | COMPLETE | 527965 |  |  |  | Install 345/115 kV 448 MVA transformer at Kiowa substation. | 345/115
200282 | 30675 | 50869 | SPS | NM | Multi - China Draw - Yeso Hills 115 kV | China Draw - Yeso Hills 115 kV Ckt 1 | High Priority | HP |  | 2018-06-01 | 2014-05-19 | HPILS | 14583586 | 2014 | 16499989 | 3095884 |  | DELAY - MITIGATION | 528222 | China Draw 115 kV | 528246 |  | Construct new 18.4-mile 115 kV line from China Draw to new Yeso Hills substation. | 115 | 18.4
200309 | 30717 | 50870 | SPS | NM | Line - Hopi Sub - North Loving - China Draw 115 kV Ckt 1 | Hopi Sub - North Loving 115 kV Ckt 1 | High Priority | HP | 2015-05-25 | 2015-06-01 | 2014-12-03 | HPILS | 9980879 | 2014 | 11292448 | 11345995 | 10421028 | COMPLETE | 528226 |  | 528191 |  | Construct new 9.5-mile 115 kV line from Hopi Sub to North Loving 115 kV. | 115 | 9.5
200309 | 30639 | 50871 | SPS | NM | Multi - Potash Junction - Road Runner 345 kV Conv. and Transformers at Kiowa and Road Runner | Kiowa - Potash Junction 345/115 kV Ckt 1 | High Priority | HP | 2018-04-27 | 2018-06-01 | 2014-12-03 | HPILS | 2176451 | 2014 | 2462455 | 3018938 | 5136295 | COMPLETE | 527965 |  | 528027 | Road Runner 345 kV | Construct 1-mile of double circuit structures from the new Kiowa substation to Potash Junction. Construct Circuit 1 with 345 kV conductor and Circuit 2 with 115 kV conductor. | 345 | 2
200282 | 30756 | 50873 | SPS | NM | Multi - Battle Axe - Road Runner 115 kV | Battle Axe - Road Runner 115 kV Ckt 1 | High Priority | HP | 2015-11-12 | 2018-06-01 | 2014-05-19 | HPILS | 13816310 | 2014 | 15631887 | 8143031 |  | COMPLETE | 528040 |  | 528025 | Road Runner 115 kV | Construct new 18.9-mile 115 kV line from Road Runner to Battle Axe. | 115 | 18.9
200282 | 30672 | 50874 | SPS | NM | Multi - Dollarhide - Toboso Flats 115 kV | Dollarhide - Toboso Flats 115 kV Ckt 1 | High Priority | HP | 2018-06-01 | 2018-06-01 | 2014-05-19 | HPILS | 5062341 | 2014 | 5727574 | 5062341 |  | IN SERVICE | 528561 | Dollarhide Sub 115 kV | 528566 |  | Construct new 7.4-mile 115 kV line from new Toboso Flats substation to Dollarhide. | 115 | 7.4
200309 | 30637 | 50875 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Ckt 1 | Hobbs - Kiowa 345 kV Ckt 1 | High Priority | HP | 2018-03-24 | 2018-06-01 | 2014-12-03 | HPILS | 48383526 | 2018 | 49593114 | 47590258 | 52084447 | COMPLETE | 527965 |  | 527896 | Hobbs Interchange 345 kV | Construct new 47.2-mile 345 kV line from Kiowa to Hobbs. | 345 | 47.24
200282 | 30694 | 50877 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa 115 kV Substation | High Priority | HP | 2017-06-01 | 2018-06-01 | 2014-05-19 | HPILS | 996485 | 2014 | 1127431 | 1082345 |  | COMPLETE | 528240 |  |  |  | Construct new 115 kV Ponderosa substation. Install any necessary 115 kV terminal equipment. | 115
200474 | 30694 | 50879 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa Tap 115 kV Substation | High Priority | HP | 2017-06-01 | 2018-06-01 | 2018-02-27 | HPILS | 4174446 | 2014 | 4723002 | 616860 |  | COMPLETE | 528239 |  |  |  | Tap the existing 115 kV line from Ochoa to Whitten to construct new 115 kV Ponderosa Tap substation. Install any necessary 115 kV terminal equipment. | 115 | 0.2
200370 | 30649 | 50881 | SPS | NM | Multi - Andrews 230/115 kV Transformer and Andrews - NEF 115 kV Ckt 1 | Andrews 230/115 kV Ckt 1 Transformer | High Priority | HP | 2016-04-04 | 2015-06-01 | 2016-02-12 | HPILS | 10671660 | 2016 | 11492211 | 11500000 | 12154286 | COMPLETE | 528604 |  | 528601 |  | Install two 230/115 kV 167 MVA transformers at Andrews substation for a combined emergency rating of 334 MVA. Install any necessary terminal equipment. | 230/115 | 0.1
200282 | 30649 | 50882 | SPS | NM | Multi - Andrews 230/115 kV Transformer and Andrews - NEF 115 kV Ckt 1 | Andrews - NEF 115 kV Ckt 1 | High Priority | HP | 2016-04-04 | 2015-06-01 | 2014-05-19 | HPILS | 3523472 | 2014 | 3986485 | 3031564 | 3031564 | COMPLETE | 528602 |  | 528603 | National Enrichment Plant Sub 115 kV | Construct new 2.1-mile 115 kV line from Andrews to National Enrichment Facility (NEF). | 115 | 2.1
200309 | 30717 | 50883 | SPS | NM | Line - Hopi Sub - North Loving - China Draw 115 kV Ckt 1 | China Draw - North Loving 115 kV Ckt 1 | High Priority | HP | 2015-05-25 | 2015-06-01 | 2014-12-03 | HPILS | 13283227 | 2014 | 15028752 | 10291637 | 11070902 | COMPLETE | 528182 | North Loving 115 kV | 528222 | China Draw 115 kV | Construct new 19.7-mile 115 kV line from North Loving to China Draw. | 115 | 19.7
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | HP | 2021-05-01 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 10528885 | 9797157 |  | DELAY - MITIGATION | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
200395 | 30692 | 50920 | SPS | TX | XFR - Seminole 230/115 kV #1 and #2 | Seminole 230/115 kV #1 Transformer | Regional Reliability | ITP | 2019-11-14 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3621405 | 2016 | 3899857 | 2986806 |  | IN SERVICE | 527276 | Seminole Interchange 230 kV | 527275 | Seminole Interchange 115 kV | Replace first existing 230/115 transformer at Seminole. | 230/115
200395 | 30692 | 50921 | SPS | TX | XFR - Seminole 230/115 kV #1 and #2 | Seminole 230/115 kV #2 Transformer | Regional Reliability | ITP | 2019-05-14 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3621405 | 2016 | 3899857 | 3203043 |  | IN SERVICE | 527276 | Seminole Interchange 230 kV | 527275 | Seminole Interchange 115 kV | Replace second existing 230/115 transformer at Seminole. | 230/115
200421 | 30693 | 50922 | SPS | TX | XFR - Wolfforth 230/115 kV Ckt 1 Transformer | Wolfforth 230/115 kV Ckt 1 Transformer | Regional Reliability | TS |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG2-AFS-3 | 3510969 | 2017 | 3688712 | 3883014 |  | ON SCHEDULE < 4 | 526525 | Wolfforth Interchange 230 kV | 526524 | Wolfforth Interchange 115 kV | Replace 230/115 kV transformer at Wolfforth substation. | 230/115
200411 | 30694 | 50923 | SPS | NM | Multi - Ponderosa - Ponderosa Tap 115 kV | Ponderosa - Ponderosa Tap 115 kV Ckt 1 | High Priority | HP | 2017-06-01 | 2018-06-01 | 2016-08-17 | HPILS | 8030702 |  |  | 9170509 |  | COMPLETE | 528239 |  | 528240 |  | Construct new 9.3-mile 115 kV line from new Ponderosa substation to new Ponderosa Tap substation. | 115 | 9.3
200395 | 31067 | 50924 | SPS | NM | Sub - Livingston Ridge 115 kV Substation Conversion | Livingston Ridge 115 kV Substation Conversion | Regional Reliability | ITP | 2017-11-30 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 5283323 | 2016 | 5689561 | 5365000 |  | COMPLETE | 527953 |  |  |  | Convert Livingston Ridge from 69 kV to 115 kV. Install any necessary 115 kV terminal equipment. | 115
200309 | 30695 | 50925 | SPS | NM | Multi - Livingston Ridge - Sage Brush - Cardinal 115 kV | Sage Brush 115 kV Substation | High Priority | HP | 2016-12-16 | 2018-06-01 | 2014-12-03 | HPILS | 3822672 | 2014 | 4325002 | 2472695 |  | COMPLETE | 527955 |  |  |  | Construct new 115 kV Sage Brush substation with 3 ring bus configuration. Install any necessary 115 kV terminal equipment. | 115
200436 | 30695 | 50926 | SPS | NM | Multi - Livingston Ridge - Sage Brush - Cardinal 115 kV | Livingston Ridge - Sage Brush 115 kV Ckt 1 | High Priority | HP | 2017-11-30 | 2018-06-01 | 2017-02-22 | HPILS | 13187417 | 2016 | 14201406 | 11510000 |  | COMPLETE | 527953 |  | 527955 |  | Construct new 27-mile 115 kV line from Livingston Ridge to new Sage Brush substation. | 115 | 13.9
200411 | 30825 | 50931 | SPS | NM | Line - China Draw - Wood Draw 115 kV Ckt 1 | China Draw - Wood Draw 115 kV Ckt 1 | High Priority | HP | 2017-06-15 | 2018-06-01 | 2016-08-17 | HPILS | 13704501 | 2014 | 15505385 | 14200000 |  | COMPLETE | 528222 | China Draw 115 kV | 528228 |  | Construct new 14-mile 115 kV line from China Draw to Wood Draw. | 115 | 14
200420 | 30699 | 50943 | SPS | TX | Line - Northwest - Rolling Hills 115 kV Ckt 1 | Northwest - Rolling Hills 115 kV Rebuild Ckt 1 | Regional Reliability | TS |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 4514434 | 2017 | 4742977 | 4513933 |  | ON SCHEDULE < 4 | 524007 |  | 524106 | Northwest Interchange 115 kV | Rebuild 8.3-mile 115 kV line from Northwest to Rolling Hills. | 115 |  | 7.2
200309 | 30695 | 50951 | SPS | NM | Multi - Livingston Ridge - Sage Brush - Cardinal 115 kV | Cardinal 115 kV Substation | High Priority | HP | 2016-12-15 | 2018-06-01 | 2014-12-03 | HPILS | 6115613 | 2014 | 6919255 | 6025000 | 5687646 | COMPLETE | 528596 | National Enrichment Plant Tap 115 kV |  |  | Construct new 115 kV Cardinal substation. Install any necessary 115 kV terminal equipment. | 115 | 0.2
200360 | 30914 | 50952 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | IMC #1 Tap - Livingston Ridge 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-04-15 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 5700000 | 2018 | 5842500 | 4711908 |  | DELAY - MITIGATION | 528035 | I. M. C. #1 Sub Tap 115 kV (International Mineral Co) | 527953 |  | Rebuild 9.5-mile 115 kV line from Livingston Ridge to IMC #1 Tap. | 115 |  | 9.5 | 9.3
200365 | 30708 | 50954 | SPS | NM | Line - Ochoa - Ponderosa Tap 115 kV Ckt 1 Rebuild | Ochoa - Ponderosa Tap 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2018-06-01 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 7032376 | 2016 | 7573100 | 4541292 | 4190439 | COMPLETE | 528232 | Ochoa Sub 115 kV | 528239 |  | Rebuild 9.1-mile 115 kV line from Ochoa to Ponderosa Tap. | 115
200360 | 30914 | 50955 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Ponderosa Tap - Whitten 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-01-26 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 2280000 | 2018 | 2337000 | 2251591 |  | COMPLETE | 528239 |  | 528540 | Whitten Sub 115 kV | Reconductor 5.9-mile 115 kV line from Ponderosa Tap to Whitten. | 115 |  | 3.92
200360 | 30914 | 50957 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Intrepid West - Potash Junction 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2019-04-15 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 2455000 | 2018 | 2516375 | 1315000 |  | IN SERVICE | 527999 |  | 527962 | Potash Junction Interchange 115 kV | Rebuild 1.5-mile 115 kV line from Intrepid West Tap to Potash Junction. | 115 |  | 1.5
200360 | 30914 | 50958 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | IMC #1 Tap - Intrepid West 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-04-15 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 3121473 | 2018 | 3199510 | 2653417 |  | COMPLETE | 527999 |  | 528035 | I. M. C. #1 Sub Tap 115 kV (International Mineral Co) | Rebuild 3.9-mile 115 kV line from Intrepid West Tap to IMC #2. | 115 |  | 3.9
200436 | 30695 | 50967 | SPS | NM | Multi - Livingston Ridge - Sage Brush - Cardinal 115 kV | Cardinal - Sage Brush 115 kV Ckt 1 | High Priority | HP | 2016-12-15 | 2018-06-01 | 2017-02-22 | HPILS | 9244612 | 2014 | 10459430 | 8120000 | 8378836 | COMPLETE | 528596 | National Enrichment Plant Tap 115 kV | 527957 |  | Construct new 19-mile 115 kV line from to Cardinal to Sage Brush. | 115 | 17.5
200282 | 30756 | 50968 | SPS | NM | Multi - Battle Axe - Road Runner 115 kV | Battle Axe 115 kV Substation | High Priority | HP | 2015-12-04 | 2018-06-01 | 2014-05-19 | HPILS | 2964499 | 2014 | 3354059 | 3006810 |  | COMPLETE | 528040 |  |  |  | Construct new 115 kV Battle Axe substation. Install any necessary 115 kV terminal equipment. | 115
200282 | 30675 | 50988 | SPS | NM | Multi - China Draw - Yeso Hills 115 kV | Yeso Hills 115 kV Substation | High Priority | HP | 2023-12-30 | 2018-06-01 | 2014-05-19 | HPILS | 1046485 | 2014 | 1184002 | 1013907 |  | DELAY - MITIGATION | 528246 |  |  |  | Construct new 115 kV Yeso Hills substation. Install any necessary 115 kV terminal equipment. | 115
200306 | 30731 | 50990 | AEP | TX | Line - Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | Mt Pleasant - West Mt Pleasant 69 kV Ckt 1 Rebuild | Regional Reliability | TS | 2015-04-20 | 2015-06-01 | 2014-11-24 | DPA-2013-SEP-351 | 4715419 | 2015 | 5204940 | 7381799 |  | COMPLETE |  |  |  |  | Rebuild 2.75-mile 69 kV line from Mt. Pleasant to West Mt. Pleasant to achieve a new emergency rating of 84 MVA. | 69 |  | 2.72
200455 | 30755 | 50992 | SPS | TX | XFR - Tuco 230/115 kV Ckt 1 | Tuco 230/115 kV Ckt 1 Transformer | Transmission Service | ITP | 2017-09-30 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 3800415 | 2015 | 4194947 | 100303 |  | COMPLETE | 525830 | TUCO Interchange 230 kV | 525828 | TUCO Interchange 115 kV | Upgrade 230/115 kV transformer at Tuco to 273 MVA. | 230/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | HP | 2021-05-01 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1053115 | 913714 |  | DELAY - MITIGATION | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
200272 | 30747 | 51014 | AEP | OK | Line - Grady - Round Creek 138 kV Ckt 1 | Grady - Round Creek 138 kV Ckt 1 | High Priority | HP | 2015-11-05 | 2015-06-01 | 2014-05-19 | HPILS | 12132497 | 2014 | 13726807 | 12132497 |  | COMPLETE | 511560 |  | 511427 | RUSH SPRINGS NATURAL GAS | Construct new Round Creek box bay tap structure adjacent to the Rush Springs 138 kV substation. Construct new 6-mile 138 kV line from Grady to Round Creek. Install 3-breaker ring bus where hard tap to Round Creek intersects the Cornville to Duncan 138 kV transmission line. | 138
200272 | 30748 | 51015 | AEP | OK | Line - Grady - Phillips Gas 138 kV Ckt 1 and 2 | Grady - Phillips 138 kV Ckt 1 and 2 | High Priority | HP | 2014-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8318584 | 2014 | 9411714 | 8318584 |  | COMPLETE | 511514 | PHILLIPS | 511560 |  | Construct new 4-mile double circuit 138 kV line from the new 4-breaker ring bus station at Grady. Circuit 1 will terminate at Phillips Gas and Circuit 2 will terminate at Lindsey Water Flood. | 138 | 4
200272 | 30750 | 51017 | AEP | OK | Line - Stonewall - Wapanucka 138 kV Ckt 1 | Stonewall - Wapanucka 138 kV Ckt 1 | High Priority | HP | 2013-12-31 | 2015-06-01 | 2014-05-19 | HPILS | 8934149 | 2014 | 10108169 | 8934149 | 7210309 | COMPLETE | 521075 |  | 510949 |  | Construct new 6.4-mile 138 kV line from Stonewall to Wapanucka. | 138 | 6.4
200298 | 30761 | 51033 | AEP | LA | Line - Cedar Grove - South Shreveport 138 kV | Cedar Grove - South Shreveport 138 kV | Transmission Service | TS | 2020-06-01 | 2020-06-01 | 2014-09-30 | SPP-2010-AGP1-AFS-8 | 6566218 | 2014 | 7429073 | 6566218 |  | ON SCHEDULE < 4 | 507771 | CEDARGROVE | 507755 | SOUTH SHREVEPORT 138KV | Rebuild 2.3 miles of 138 kV 954 ACSR conductor with 1590 ACSR conductor from Cedar Grove to South Shreveport. Replace breaker, switches, and jumpers at South Shreveport. Replace switch at Cedar Grove. | 138
200339 | 30762 | 51034 | AEP | LA | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Ckt 1 Rebuild | Regional Reliability | TS | 2019-03-01 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 6629465 | 2015 | 7317689 | 9905114 |  | COMPLETE | 507723 | ELLERBE ROAD 69 kV | 507739 | LUCAS | Rebuild existing 3.2-mile 69 kV line from Ellerbe Road to Lucas. | 69 | 3.2
200339 | 30762 | 51035 | AEP | LA | Multi - Ellerbe Road - Lucas 69 kV | Ellerbe Road - Lucas 69 kV Terminal Upgrades | Regional Reliability | TS | 2019-02-27 | 2019-03-01 | 2015-03-17 | DPA-2013-MAR-296 | 652658 | 2015 | 720412 | 1144751 |  | COMPLETE | 507723 | ELLERBE ROAD 69 kV |  |  | Replace jumpers at 69 kV substations Ellerbe Road and Lucas. Replace relay panel at Ellerbe Road. Change relay setting at Lucas. | 69
200262 | 30766 | 51039 | SPS | TX | XFR - Yoakum County Interchange 230/115 kV Ckts 1 and 2 | Yoakum County Interchange 230/115 kV Ckt 1 Transformer | Transmission Service | TS | 2019-03-15 | 2019-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 3632101 | 2014 | 4109389 | 2285718 |  | DELAY - MITIGATION | 526935 | Yoakum County Interchange 230 kV | 526934 | Yoakum County Interchange 115 kV | Upgrade Yoakum County Interchange Ckt 1 230/115 kV transformer to 250 MVA. | 230/115
200272 | 30770 | 51047 | AEP | OK | Sub - Ellis 138 kV | Ellis 138 kV Substation | High Priority | HP | 2013-06-01 | 2015-06-01 | 2014-05-19 | HPILS | 4100000 | 2014 | 4638774 | 4100000 | 4086696 | COMPLETE | 511561 |  | 521001 | MOREWOOD SW | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation. | 138
200286 | 30771 | 51048 | MIDW | KS | Multi - Midwest Pump - Midwest Pump Tap 115 kV Ckt 1 | Midwest Pump Tap 115 kV Substation | High Priority | HP | 2016-07-02 | 2015-06-01 | 2014-05-19 | HPILS | 4477251 | 2014 | 5065598 | 4477251 |  | COMPLETE | 531263 |  |  |  | Tap existing 115 kV line from Kanarado (Sunflower) to Sharon Springs to construct new Midwest Pump Tap substation. | 115
200286 | 30771 | 51049 | MIDW | KS | Multi - Midwest Pump - Midwest Pump Tap 115 kV Ckt 1 | Midwest Pump - Midwest Pump Tap 115 kV Ckt 1 | High Priority | HP | 2016-07-02 | 2015-06-01 | 2014-05-19 | HPILS | 2443469 | 2014 | 2764561 | 2443469 |  | COMPLETE | 530692 |  | 531263 |  | Build new 5-mile 115 kV line from Midwest Pump to the new Midwest Pump Tap substation. | 115 | 6
200262 | 30766 | 51050 | SPS | TX | XFR - Yoakum County Interchange 230/115 kV Ckts 1 and 2 | Yoakum County Interchange 230/115 kV Ckt 2 Transformer | Regional Reliability | TS | 2019-05-31 | 2019-06-01 | 2014-04-09 | SPP-2011-AG3-AFS-11 | 3432506 | 2014 | 3883565 | 5500796 |  | IN SERVICE | 526935 | Yoakum County Interchange 230 kV | 526934 | Yoakum County Interchange 115 kV | Upgrade Yoakum County Interchange Ckt 2 230/115 kV transformer to 250 MVA. | 230/115
| 30786 | 51069 | NPPD |  | Sub - Dixon County 230kV | Dixon County 230kV Substation | Generation Interconnection | GI | 2018-10-01 | [6 empty] | 6404189 |  | IN SERVICE |  |  |  |  | 230kV Line Terminal including four (4) breaker substation addition | 230
| 30787 | 51070 | NPPD |  | Line - Twin Church - Dixon County 230kV Ckt 1 | Twin Church - Dixon County 230kV Line Upgrade | Generation Interconnection | GI | 2018-11-01 | [6 empty] | 61774 |  | IN SERVICE |  |  |  |  | Increase clearances to accommodate 320MVA facility rating | 230
200382 | 30809 | 51096 | AEP | OK | Line - Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Keystone Dam - Wekiwa 138 kV Ckt 1 Rebuild | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2016-04-12 | SPP-2014-AG1-AFS-6 | 4319501 | 2016 | 4651630 | 6445009 |  | ON SCHEDULE < 4 | 505610 | Keystone Dam | 509757 | WEKIWA 138KV | Rebuild 2.0-mile 69 kV line from Keystone Dam to Wekiwa to 138 kV operation. | 138 | 2 | 2 | 2
200395 | 30817 | 51109 | SPS | TX | Line - Canyon West - Dawn - Panda - Deaf Smith 115 kV Ckt 1 Rebuild | Canyon West - Dawn 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-02-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6519222 | 2018 | 6682203 | 8888824 | 3483013 | COMPLETE | 524516 | Canyon West Sub 115 kV | 524590 | Dawn Sub 115 kV | Rebuild 13.7-mile 115 kV line from Canyon West to Dawn. | 115 |  | 13.7
200395 | 30817 | 51110 | SPS | TX | Line - Canyon West - Dawn - Panda - Deaf Smith 115 kV Ckt 1 Rebuild | Dawn - Panda 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-04-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4212298 | 2018 | 4317605 | 2169390 | 1738575 | COMPLETE | 524590 | Dawn Sub 115 kV | 524597 | Panda Energy Substation, Hereford 115 kV | Rebuild 8.4-mile 115 kV line from Dawn to Panda. | 115 |  | 8.4
200395 | 30817 | 51111 | SPS | TX | Line - Canyon West - Dawn - Panda - Deaf Smith 115 kV Ckt 1 Rebuild | Deaf Smith - Panda 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-12-15 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2055714 | 2018 | 2107107 | 1343820 | 5289345 | DELAY - MITIGATION | 524622 | Deaf Smith County Interchange 115 kV | 524597 | Panda Energy Substation, Hereford 115 kV | Rebuild 3.5-mile 115 kV line from Deaf Smith to Panda. | 115 |  | 3.5
200297 | 30820 | 51112 | SPS | TX | Carlisle Interchange - Tuco Interchange 230 kV Ckt 1 | Carlisle Interchange - Tuco Interchange 230 kV Ckt 1 Terminal Upgrade | Transmission Service | TS | 2016-10-24 | 2015-10-01 | 2015-05-05 | SPP-2012-AG3-AFS-9 | 362250 | 2015 | 399856 | 289000 |  | COMPLETE | 525830 | TUCO Interchange 230 kV | 526161 | Carlisle Interchange 230 kV | Replace the wave trap at Carlisle substation. Replace the wave trap on the Carlisle line terminal at Tuco substation. | 230
200360 | 30914 | 51131 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Byrd Tap - Monument Tap 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-12-14 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 4000000 | 2018 | 4100000 | 3525000 | 3240716 | IN SERVICE | 528582 | Byrd Sub 115 kV | 528568 | Monument Tap 115 kV | Rebuild 3.8-mile 115 kV line from Monument Tap to Byrd Tap. | 115 | 4.6
200371 | 30666 | 51132 | SPS | NM | Device - China Draw and Road Runner 115 kV SVC | Road Runner 115 kV SVC | Regional Reliability | ITP | 2016-04-01 | 2015-04-01 | 2016-02-12 | 2015 ITPNT | 28918070 | 2015 | 31920138 | 28918070 |  | COMPLETE | 528025 | Road Runner 115 kV |  |  | Install new SVC at Road Runner 115 kV substation with effective range of -50/+200 MVAR. | 115
200330 | 30838 | 51133 | OPPD | NE | XFR - Sub 3459 345/161 kV Ckt 1 Transformer | Sub 3459 345/161 kV Transformer | Regional Reliability | ITP | 2018-06-01 | 2019-06-01 | 2015-02-18 | 2015 ITP10 | 6588939 | 2015 | 7272956 | 6588939 |  | COMPLETE | 645459 | Sub 3459 | 646209 | Sub 1209 | Install new 345/161 kV transformer at Sub 3459. Install any necessary 161 kV terminal equipment. | 345/161
200330 | 30838 | 51136 | OPPD | NE | XFR - Sub 3459 345/161 kV Ckt 1 Transformer | Sub 3459 345 kV Terminal Upgrades | Regional Reliability | ITP | 2018-06-01 | 2019-06-01 | 2015-02-18 | 2015 ITP10 | 3604757 | 2015 | 3978977 | 3604757 |  | COMPLETE | 645459 | Sub 3459 |  |  | Install any 345 kV terminal equipment required for new 345/161 kV transformer at Sub 3459. | 345
200395 | 30844 | 51140 | SPS | TX | Sub - Amoco - Sundown 230 kV Terminal Upgrades | Amoco - Sundown 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-14 | 2019-01-01 | 2016-05-17 | 2016 ITPNT | 1771222 | 2016 | 1907412 | 716717 |  | DELAY - MITIGATION | 526435 | Sundown Interchange 230 kV | 526460 | Amoco Switching Station 230 kV (Amoco Slaughter) | Upgrade switches and wave traps at Sundown and Amoco and increase the line clearance to increase the rating of the 230 kV line from Amoco to Sundown. | 230
200328 | 30850 | 51151 | KCPL | MO | Line - Iatan - Stranger 345 kV Ckt 1 Voltage Conversion | Iatan 345 kV Voltage Conversion | Economic | ITP | 2018-06-01 | 2019-01-01 | 2015-02-25 | 2015 ITP10 | 3005339 | 2019 | 3005339 | 3005339 | 1885731 | COMPLETE | 542982 | IATAN 345 KV |  |  | Install any terminal upgrades required at Iatan to convert existing 18.2-mile 161 kV line from Iatan to Stranger Creek to 345 kV operation. | 345 | 0.2 |  | 18
200336 | 30859 | 51163 | SPS | NM | Device - Plains Interchange 115 kV Cap Bank | Plains Interchange 115 kV Cap Bank | Regional Reliability | ITP | 2018-04-04 | 2019-06-01 | 2015-02-26 | 2015 ITP10 | 1217275 | 2015 | 1343644 | 1630000 | 1696418 | COMPLETE | 526928 | Lea County REC-Plains Interchange115 kV |  |  | Install one (1) 14.4-MVAR capacitor bank at the Plains Interchange 115 kV substation. | 115
200326 | 30866 | 51170 | SPS | TX | Sub - Amarillo South 230 kV Terminal Upgrades | Amarillo South 230 kV Terminal Upgrades | Regional Reliability | ITP | 2020-04-01 | 2020-04-01 | 2015-02-18 | 2015 ITPNT | 31198 | 2015 | 34437 | 31198 |  | ON SCHEDULE < 4 | 524415 | Amarillo South Interchange 230 kV | 525213 | Swisher County Interchange 230 kV | Replace wave trap at Amarillo South to increase the rating of the 230 kV line from Amarillo South to Swisher County. | 230
200314 | 30873 | 51187 | AEP | OK | Line - Southwestern Station - Carnegie 138kV Ckt 1 Rebuild | Southwestern Station - Carnegie 138 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-07-06 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 15821763 | 2015 | 17464266 | 9397311 | 8899000 | COMPLETE | 511477 | SOUTHWESTERN STATION 138KV | 511445 | CARNEGIE | Rebuild 16.5-mile 138 kV from Southwestern Station to Carnegie. | 138 |  | 16.52 | 138
200326 | 30875 | 51189 | SPS | NM | Line - PCA Interchange - Quahada 115 kV Ckt 1 Rebuild | PCA Interchange - Quahada 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-02-25 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 7264308 | 2015 | 8018437 | 9000000 |  | COMPLETE | 527930 | PCA Interchange 115 kV | 528394 | Quahada 115 kV | Rebuild 11.1-mile 115 kV line from PCA Interchange to Quahada. | 115 |  | 12.1
200318 | 30883 | 51200 | NPPD | NE | Multi - Bassett 115 kV | Bassett 115 kV Substation | Regional Reliability | ITP | 2018-06-01 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 5163000 | 2015 | 5698986 | 127220 | 127220 | COMPLETE | 640580 |  |  |  | Tap the existing 115 kV line from Ainsworth to Stuart to construct the new Bassett substation. | 115 | 0.1
200326 | 30888 | 51206 | SPS | TX | XFR - Lynn County 115/69 kV Ckt 1 Transformer | Lynn County 115/69 kV Ckt 1 Transformer | Regional Reliability | ITP | 2019-06-01 | 2019-06-01 | 2015-02-18 | 2015 ITPNT | 1699629 | 2015 | 1876072 | 2302251 |  | DELAY - MITIGATION | 526656 | Lynn County Interchange 115 kV | 526655 | Lynn County Interchange 69 kV | Replace 115/69 kV transformer at Lynn County substation. | 115/69
200406 | 30889 | 51207 | AEP | LA | Line - Linwood - South Shreveport 138kV Ckt 1 Rebuild | Linwood - South Shreveport 138 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-05-10 | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 5285437 | 2016 | 5691838 | 5919107 |  | COMPLETE | 507738 | LINWOOD | 507771 | CEDARGROVE | Rebuild the 2.4-mile 138kV line from Linwood to Cedar Grove to South Shreveport. Upgrade the jumpers at Linwood. | 138 |  | 2.42
200326 | 30894 | 51214 | SPS | TX | Device - Cargill 115 kV Cap Bank | Cargill 115 kV Cap Bank | Regional Reliability | ITP | 2018-12-31 | 2019-06-01 | 2015-02-18 | 2015 ITPNT | 1262485 | 2015 | 1393547 | 1670657 |  | IN SERVICE | 524648 | Cargill Sub 115 kV |  |  | Install one (1) 14.4-MVAR capacitor bank at Cargill 115 kV substation. | 115
200314 | 30895 | 51215 | AEP | LA | Line - Brooks Street - Edwards Street 69kV Ckt 1 Rebuild | Brooks Street - Edwards Street 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-12-20 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 4294228 | 2015 | 4740025 | 4294228 |  | COMPLETE | 507717 | BROOKS STREET | 507722 | EDWARDS STREET | Rebuild 0.8-mile 69 kV line from Brooks Street to Edwards Street. Upgrade jumpers at both substations. | 69 |  | 0.85
200343 | 30912 | 51235 | SPS | KS | Multi - Walkemeyer Tap - Walkemeyer 345/115 kV | Stevens Co. 345 kV Substation | Regional Reliability | ITP | 2018-06-08 | 2015-06-01 | 2015-08-13 | 2015 ITPNT | 13831957 | 2015 | 15267892 | 13340937 | 13433258 | COMPLETE | 531512 | Walkemeyer Tap 345 kV |  |  | Tap the existing 345 kV line from Finney to Hitchland to construct the new Stevens Co. substation. Install any necessary 345 kV terminal equipment. | 345 | 0.1
200343 | 30913 | 51237 | SPS | NM | Multi - RIAC 115 kV Voltage Conversion | RIAC 115 kV Voltage Conversion | Regional Reliability | ITP | 2018-11-30 | 2015-06-01 | 2015-08-13 | 2015 ITPNT | 4811635 | 2015 | 5311145 | 5169697 | 3932081 | IN SERVICE | 527552 | RIAC Subs 69 kV |  |  | Convert RIAC substation to 115 kV. Install a new 3-way 115 kV line switch tapping the 115 kV line from Brasher to Roswell Interchange. Remove the existing 69 kV transmission lines terminating at RIAC and rebuild the 1.5-mile 69 kV line from the north with a new 115 kV line to RIAC. Add a new 115 kV terminal at Roswell Interchange and build a new 0.1-mile line out of Roswell Interchange to connect to the Roswell City 115 kV circuit. | 115 | 0.1 | 1.5
200360 | 30914 | 51245 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | Cardinal - Targa 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2017-12-14 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 2435548 | 2018 | 2496437 | 1542794 | 1285381 | COMPLETE |  |  |  |  | Rebuild 3-mile 115 kV line from Cardinal to Targa. | 115 | 3
200360 | 30914 | 51250 | SPS | NM | Multi - Road Runner 115 kV Loop Rebuild | National Enrichment Plant - Targa 115 kV Ckt 1 | Regional Reliability | ITP | 2019-04-05 | 2015-06-01 | 2015-12-07 | 2015 ITPNT | 1874116 | 2018 | 1920969 | 1874116 |  | IN SERVICE | 528603 | National Enrichment Plant Sub 115 kV | 528540 | Whitten Sub 115 kV | Rebuild 4.3-mile 115 kV line from National Enrichment Plant to Targa. | 115 | 3
200326 | 30888 | 51270 | SPS | TX | XFR - Lynn County 115/69 kV Ckt 1 Transformer | Lynn County 115 kV Terminal Upgrades | Regional Reliability | ITP | 2019-06-01 | 2019-06-01 | 2015-02-18 | 2015 ITPNT | 19425 | 2015 | 21442 | 0 |  | IN SERVICE | 526656 | Lynn County Interchange 115 kV |  |  | Install 115 kV terminal equipment at Lynn County substation necessary to replace 115/69 kV transformer. | 115
200365 | 30918 | 51272 | SPS | NM | Line - Byrd Tap - Cooper Ranch - Oil Center - Lea Road 115 kV Ckt 1 Rebuild | Cooper Ranch - Oil Center 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 3044258 | 2016 | 3278333 | 1750000 |  | ON SCHEDULE < 4 |  |  |  |  | Rebuild 3.5-mile 115 kV line from Cooper Ranch to Oil Center. | 115 |  | 2.6
200365 | 30918 | 51273 | SPS | NM | Line - Byrd Tap - Cooper Ranch - Oil Center - Lea Road 115 kV Ckt 1 Rebuild | Byrd Tap - Cooper Ranch 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 3261324 | 2016 | 3512089 | 3017295 |  | ON SCHEDULE < 4 |  |  |  |  | Rebuild 4.9-mile 115 kV line from Byrd Tap to Cooper Ranch. | 115 |  | 5.7
200318 | 30921 | 51276 | NPPD | NE | Line - Ainsworth - Ainsworth Wind 115 kV Ckt 1 Rebuild | Ainsworth - Ainsworth Wind 115 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2020-06-01 | 2020-06-01 | 2015-02-18 | 2015 ITPNT | 200000 | 2015 | 220763 | 698228 |  | ON SCHEDULE < 4 |  |  |  |  | Rebuild 7.1-mile 115 kV line from Ainsworth to Ainsworth Wind. | 115
200318 | 30883 | 51277 | NPPD | NE | Multi - Bassett 115 kV | Bassett 115 kV Cap Bank | Regional Reliability | ITP | 2018-06-01 | 2016-06-01 | 2015-02-18 | 2015 ITPNT | 902000 | 2015 | 995639 | 3831068 | 3831068 | COMPLETE |  |  |  |  | Install one(1) 9-MVAR capacitor bank at the new Bassett 115 kV substation. | 115
200337 | 30850 | 51283 | GMO | MO | Line - Iatan - Stranger 345 kV Ckt 1 Voltage Conversion | Iatan - Stranger Creek 345 kV Ckt 1 Voltage Conversion (GMO) | Economic | ITP | 2018-06-01 | 2019-01-01 | 2015-02-25 | 2015 ITP10 | 6582841 | 2019 | 6582841 | 6582841 | 7688424 | COMPLETE | 541350 | Iatan 161 | 541231 | Stranger 161 KV | Convert GMO's portion of the existing 18.2-mile 161 kV line from Iatan to Stranger Creek to 345 kV operation. | 345
200338 | 30850 | 51284 | WR | KS | Line - Iatan - Stranger 345 kV Ckt 1 Voltage Conversion | Iatan - Stranger Creek 345 kV Ckt 1 Voltage Conversion (WR) | Economic | ITP | 2018-06-01 | 2019-01-01 | 2015-02-25 | 2015 ITP10 | 21977566 | 2019 | 21977566 | 21977566 | 21830047 | COMPLETE | 541350 | Iatan 161 | 541231 | Stranger 161 KV | Convert WR's portion of the existing 18.2-mile 161 kV line from Iatan to Stranger Creek to 345 kV operation. Install any necessary terminal equipment at Stranger Creek. | 345 |  |  | 10.83
| 30934 | 51292 | NPPD |  | Line - Hoskins - Dixon County 230kV Ckt 1 | Hoskins - Dixon County 230kV Line Upgrade | Generation Interconnection | GI | 2018-11-01 | [6 empty] | 308869 |  | IN SERVICE |  |  |  |  | Increase clearances on Hoskins - Dixon County 230kV line to accommodate 320MVA facility rating to address loading issues | 230
| 30943 | 51306 | BEPC | ND | Multi - AVS - Charlie Creek 345 kV | AVS - Charlie Creek 345 kV Ckt 2 | Regional Reliability | ITP | 2016-01-01 | 2017-12-01 |  | IS Integration Study | 96000000 | 2014 | 108615188 | 65407395 | 78253619 | COMPLETE | 659101 | ANTELOPE VALLEY | 659183 | CHARLIE CREEK | Construct new 70-mile 345 kV line from AVS to Charlie Creek. | 345 | 66.4
| 30943 | 51307 | BEPC | ND | Multi - AVS - Charlie Creek 345 kV | AVS 345 kV Substation | Regional Reliability | ITP | 2016-06-01 | 2017-12-01 |  | IS Integration Study | 3000000 | 2014 | 3394225 | 6121210 | 7612451 | COMPLETE | 659101 | ANTELOPE VALLEY |  |  | Construct new 345 kV AVS switching station to accommodate new 345 kV line from Charlie Creek. | 345
| 30943 | 51308 | BEPC | ND | Multi - AVS - Charlie Creek 345 kV | Charlie Creek 345 kV Substation | Regional Reliability | ITP | 2016-01-01 | 2017-12-01 |  | IS Integration Study | 9000000 | 2014 | 10182674 | 11268556 | 6577852 | COMPLETE | 659183 | CHARLIE CREEK |  |  | Expand Charlie Creek 345 kV substation to accommodate new 345 kV line from AVS. | 345
| 30944 | 51310 | BEPC | ND | Multi - Charlie Creek - Judson - Williston 345/230 kV | Charlie Creek - Judson 345 kV Ckt 1 | Regional Reliability | ITP | 2016-01-01 | 2017-12-01 |  | IS Integration Study | 103000000 | 2014 | 116535046 | 71704347 | 71158911 | COMPLETE | 659183 | CHARLIE CREEK | 659333 | JUDSON | Constuct new 75-mile 345 kV line from Charlie Creek to new Judson substation. | 345 | 73.7
| 30944 | 51311 | BEPC | ND | Multi - Charlie Creek - Judson - Williston 345/230 kV | Judson 345/230 kV Substation | Regional Reliability | ITP | 2015-12-22 | 2017-12-01 |  | IS Integration Study | 19000000 | 2014 | 21496756 | 24758086 | 16400623 | COMPLETE | 659333 | JUDSON |  |  | Construct new 345 kV Judson substation adjacent to the existing 230 kV Williston substation. | 345
| 30944 | 51312 | BEPC | ND | Multi - Charlie Creek - Judson - Williston 345/230 kV | Judson - Williston 230 kV Ckt 1 | Regional Reliability | ITP | 2016-01-01 | 2017-12-01 |  | IS Integration Study | 2400000 | 2014 | 2715380 | 3159903 | 7612451 | COMPLETE | 659333 | JUDSON | 652400 | WILLISTON | Construct 2-mile 230 kV DC line from new Judson substation to Williston. | 230 | 2
| 30945 | 51314 | BEPC | ND | Multi - Judson - Tande - Neset 345/230 kV | Judson - Tande 345 kV Ckt 1 | Regional Reliability | ITP | 2017-11-11 | 2017-12-01 |  | IS Integration Study | 86000000 | 2014 | 97301106 | 66207772 |  | COMPLETE | 659333 | JUDSON | 659336 | TANDE | Construct new 58-mile 345 kV line from Judson to Tande. | 345 | 61.2
| 30945 | 51315 | BEPC | ND | Multi - Judson - Tande - Neset 345/230 kV | Tande 345/230 kV Substation | Regional Reliability | ITP | 2017-10-31 | 2017-12-01 |  | IS Integration Study | 18000000 | 2014 | 20365348 | 18000000 |  | COMPLETE | 659336 | TANDE |  |  | Construct new 345 kV Tande substation adjacent to the existing 230 kV Neset substation. Install new 345/230 kV transformer at Tande. | 345
| 30945 | 51316 | BEPC | ND | Multi - Judson - Tande - Neset 345/230 kV | Neset - Tande 230 kV Ckt 1 | Regional Reliability | ITP | 2016-01-01 | 2017-12-01 |  | IS Integration Study | 3000000 | 2014 | 3394225 | 364982 |  | COMPLETE | 659138 | Neset 230 kV Bus | 659336 | TANDE | Install new 2-mile 230 kV line from Neset to new Tande substation. | 230 | 1
| 30945 | 51317 | BEPC | ND | Multi - Judson - Tande - Neset 345/230 kV | Neset 230 kV Terminal Upgrades | Regional Reliability | ITP | 2017-10-31 | 2017-12-01 |  | IS Integration Study | 4000000 | 2014 | 4525633 | 4000000 |  | COMPLETE | 659138 | Neset 230 kV Bus |  |  | Install any necessary terminal upgrades at Neset 230 kV to accommodate new 230 kV line from new Tande substation. | 230
| 30946 | 51318 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule - Witten 230 kV Ckt 1 | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration Study | 31500000 | 2014 | 35639359 | 31500000 |  | DELAY - MITIGATION | 659312 | Lower Brule | 659310 | Witten | Construct new 65-mile 230 kV line from Lower Brule to Witten. | 230
| 30946 | 51319 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule 230 kV Substation | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration Study | 4500000 | 2014 | 5091337 | 4500000 |  | DELAY - MITIGATION | 659312 | Lower Brule |  |  | Install any necessary terminal upgrades at Lower Brule 230 kV to accommodate new 230 kV line from Witten. | 230
| 30946 | 51320 | BEPC | SD | Multi - Lower Brule - Witten 230 kV | Lower Brule - Witten 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-01-01 | 2016-12-01 |  | IS Integration Study | 2000000 | 2014 | 2262816 | 2000000 |  | DELAY - MITIGATION | 659312 | Lower Brule | 659310 | Witten | Install communication facilities associated with the new 230 kV line from Lower Brule to Witten. | 230
200376 | 30953 | 51333 | SEPC | KS | Device - Lane Scott 115 kV Cap Bank | Lane Scott 115 kV Cap Bank | Regional Reliability | TS | 2019-09-19 | 2017-06-01 | 2016-07-12 | DPA-2015-MARCH-494 | 3852342 | 2016 | 4148551 | 4068523 |  | IN SERVICE |  |  |  |  | Install 12-MVAR capacitor bank at Lane Scott 115 kV. | 115
| 30955 | 51335 | OGE |  | SUB - Otter 138kV - rebuild and add terminal for GEN-2014-064 | Otter 138kV - rebuild and add terminal for GEN-2014-064 NU | Generation Interconnection | GI | 2018-10-15 | [6 empty] | 2807651 |  | COMPLETE |  |  |  |  | Install four (4) 138 kV, 2000 Amp breakers, line relaying, disconnect switches, and associated equipment.
| 30959 | 51338 | WR |  | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 NU) | Generation Interconnection | GI | [7 empty] | 11924807 |  | ON SCHEDULE < 4 |  |  |  |  | Install three (3) 345 kV breakers, six (6) 345 kV 3000 Amp switches, two (2) 345 kV 3000 Amp motor-operated switches, six (6) 345 kV CCVTs, four (4) 345 kV wave traps, new redundant primary relaying, two (2) 345 kV full tension dead-end structures, and all associated site, yard, cable, grounding and conduit work into a new Transmission Owner GEN-2014-001 Point of Interconnection substation.; Site for Transmission Owner Substation: Site parcel to be approved by Transmission Owner, such approval to not be unreasonably withheld.; Allowance for Funds Used During Construction (AFUDC) and Contingency; Emporia Substation – Relay change-out work; Wichita Substation – Relay change-out work; New Transmission Owner Substation – Inspection costs during Construction for Option to Build (assumes using Transmission Owner preferred contractors); Wichita – Emporia Energy Center 345 kV Ckt 1: Install two (2) three-pole steel dead-end and turning structures plus associated foundations, equipment, and labor to tap and loop the Wichita – Emporia Energy Center 345 kV Ckt 1 into new Transmission Owner 345kV substation. The estimated facilities and associated costs assume that the interconnection substation is adjacent to the existing 345kV line easement.; Allowance for Funds Used During Construction (AFUDC) and Contingency
| 30956 | 51339 | NPPD |  | Multi - GEN-2013-032 Interconnection Work | Antelope 115kV - Add terminal for GEN-2013-032 | Generation Interconnection | GI | 2017-05-01 | [6 empty] | 2868775 |  | IN SERVICE |  |  |  |  | Install two (2) 115 kV circuit breakers and associated switches, structures, and associated equipment. Add one (1) 115 kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities; Replace one (1) 115 kV circuit breaker due to short circuit over-duty.
| 30960 | 51341 | OGE |  | SUB - Beaver County 345kV - Add 345kV terminal for GEN-2013-030 | Beaver County Substation - Add 345kV terminal for GEN-2013-030 | Generation Interconnection | GI | 2019-10-28 | [6 empty] | 4842217 |  | COMPLETE |  |  |  |  | Beaver County 345 kV: Convert from ring bus to breaker–and-a-half configuration by installing additional rung to the existing bus layout and install five (5) 345 kV, 3000 Amp breakers, line relaying, disconnect switches, and associated equipment.
200384 | 30971 | 51358 | SPS | TX | Line - Cochran - Whiteface Tap 69 kV Ckt 1 Rebuild | Cochran - Whiteface Tap 69 kV Ckt 1 Rebuild | Regional Reliability | TS | 2018-12-20 | 2016-06-01 | 2016-04-20 | DPA-2013-JUN-342 | 2254282 | 2016 | 2427615 | 2250325 |  | IN SERVICE |  |  |  |  | Rebuild 4.5-mile 69 kV line from Cochran to Whiteface Tap to 115 kV standards (operated at 69 kV). | 69
| 30959 | 51360 | WR |  | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | GI | [7 empty] | 2602316 |  | ON SCHEDULE < 4 |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
| 30955 | 51362 | OGE |  | SUB - Otter 138kV - rebuild and add terminal for GEN-2014-064 | Otter 138kV - rebuild and add terminal for GEN-2014-064 TOIF | Generation Interconnection | GI | 2018-10-15 | [6 empty] | 410000 |  | COMPLETE |  |  |  |  | Add one (1) 138 kV line terminal including dead-end structure, line switch, line relaying, revenue metering, CTs, PTs, and associated equipment.
| 30975 | 51368 | SEPC |  | Sub - Buckner 345kV GEN-2010-045 Addition | Buckner 345kV Substation GEN-2010-045 Addition (TOIF) | Generation Interconnection | GI | [7 empty] | 4000000 |  | ON SCHEDULE < 4 |  |  |  |  | At the Buckner Substation: Add structural steel, switches, and all associated terminal equipment required for the 345 kV transmission line.; Add all equipment for 345 kV metering.; Add one (1) 345 kV breaker and one (1) 345 kV reactor.
| 30975 | 51369 | SEPC |  | Sub - Buckner 345kV GEN-2010-045 Addition | Buckner 345kV Substation GEN-2010-045 Addition (NU) | Generation Interconnection | GI | [7 empty] | 8200000 |  | ON SCHEDULE < 4 |  |  |  |  | Buckner Substation: Add a third 345kV breaker and a half leg to the ring bus.; Add two (2) 345 kV breakers and all associated network equipment needed for the 345 kV line terminal.; Spearville Substation: Replace terminal equipment on Buckner circuit.
200365 | 30987 | 51406 | SPS | NM | Line - Cunningham - Monument Tap 115 kV Ckt 1 Rebuild | Cunningham - Monument Tap 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 5129356 | 2016 | 5523755 | 4709561 |  | ON SCHEDULE < 4 | 527864 | Cunningham Station 115 kV | 528568 | Monument Tap 115 kV | Rebuild 6.5-mile 115 kV line from Cunningham to Monument Tap. | 115
200365 | 30918 | 51407 | SPS | NM | Line - Byrd Tap - Cooper Ranch - Oil Center - Lea Road 115 kV Ckt 1 Rebuild | Lea Road - Oil Center 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 3630770 | 2016 | 3909942 | 2654060 |  | DELAY - MITIGATION | 528505 | Lea Road Sub 115 kV | 528552 | Oil Center Sub 115 kV (DCP) | Rebuild 3.1-mile 115 kV line from Lea Road to Oil Center. | 115 |  | 4.25
200366 | 30988 | 51408 | SPS | NM | Sub - Eddy Co. 230 kV Bus Tie | Eddy Co. 230 kV Bus Tie | Transmission Service | TS |  | 2017-10-01 | 2016-01-12 | SPP-2013-AG3-AFS-6 | 10425309 | 2016 | 11226918 | 20720534 |  | DELAY - MITIGATION | 527800 | Eddy County Interchange 230 kV |  |  | Reconfigure 230 kV bus tie at Eddy Co. substation to convert to a double bus and breaker scheme. | 230 | 0.2
200365 | 30989 | 51409 | SPS | NM | Sub - Potash Junction 230 kV Terminal Upgrade | Potash Junction 230 kV Terminal Upgrade | Regional Reliability | TS | 2018-06-01 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 63251 | 2016 | 68114 | 63251 |  | COMPLETE | 527963 | Potash Junction Interchange 230 kV |  |  | Replace wavetrap at Potash Junction 230 kV substation. | 230
200365 | 30990 | 51410 | SPS | NM | Line - Jal - Teague 115 kV Ckt 1 Rebuild | Jal - Teague 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 6640592 | 2016 | 7151191 | 215414 | 127531 | COMPLETE | 528547 | South Jal Sub 115 kV | 528526 | Teague Sub 115 kV | Rebuild 10.3-mile 115 kV line from Jal to Teague. | 115
200365 | 30991 | 51411 | SPS | NM | Line - National Enrichment Plant - Teague 115 kV Ckt 1 Rebuild | National Enrichment Plant - Teague 115 kV Ckt 1 Rebuild | Regional Reliability | TS | 2018-12-15 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 4915370 | 2016 | 5293316 | 500000 |  | IN SERVICE | 528596 | National Enrichment Plant Tap 115 kV | 528526 | Teague Sub 115 kV | Rebuild 6.8-mile 115 kV line from National Enrichment Plant to Teague. | 115
200397 | 30995 | 51430 | WFEC | OK | Device - Harrisburg 69 kV Cap Bank | Harrisburg 69 kV Cap Bank | Regional Reliability | ITP | 2017-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 450000 | 2016 | 484601 | 450000 |  | RE-EVALUATION | 520933 | HARRISBURG |  |  | Install new 15-MVAR cap bank at Harrisburg 69 kV. | 69
200395 | 30996 | 51431 | SPS | TX | Sub - Hobbs - Yoakum Tap 230 kV Substation and Transformer | Hobbs - Yoakum Tap 230 kV Substation | Regional Reliability | ITP | 2019-12-15 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 9710319 | 2016 | 10456951 | 11459054 |  | DELAY - MITIGATION | 527894 | Hobbs Interchange 230 kV | 526935 | Yoakum County Interchange 230 kV | Tap the existing 230 kV line from Hobbs to Yoakum and the existing 115 kV line from Allred Tap to Waits. Terminate all four end points into new substation. | 230/115 | 0.6
200395 | 30996 | 51432 | SPS | TX | Sub - Hobbs - Yoakum Tap 230 kV Substation and Transformer | Hobbs - Yoakum Tap 230/115 kV Transformer | Regional Reliability | ITP | 2019-12-15 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3020218 | 2016 | 3252444 | 3328962 | 12696625 | DELAY - MITIGATION | 527894 | Hobbs Interchange 230 kV | 526935 | Yoakum County Interchange 230 kV | Install 230/115 kV transformer at new Hobbs - Yoakum Tap substation. | 230/115 | 0.6
200386 | 30997 | 51433 | AEP | OK | Device - Sayre 138 kV Cap Bank | Sayre 138 kV Cap Bank | Regional Reliability | ITP | 2018-12-19 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 758441 | 2016 | 816758 | 1997360 |  | COMPLETE | 511504 | SAYRE |  |  | Install new 14.4-MVAR capacitor bank at Sayre 138 kV. | 138
200395 | 30999 | 51436 | SPS | TX | Sub - Potter Co. - Harrington 230 kV Terminal Upgrades | Potter Co. - Harrington 230 kV Terminal Upgrades | Regional Reliability | ITP | 2019-06-01 | 2019-06-01 | 2016-05-17 | 2016 ITPNT | 914347 | 2016 | 984652 | 920343 |  | IN SERVICE | 523959 | Potter County Interchange 230 kV | 523979 | Harrington Station East Bus 230 kV | Upgrade terminal equipment at both Potter Co. and Harrington 230 kV substations. | 230
200395 | 31001 | 51438 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Agave Red Hills - Road Runner 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2017-03-20 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 443866 | 2016 | 477996 | 443866 |  | COMPLETE | 528230 |  | 528025 | Road Runner 115 kV | Construct new 115 kV line from Agave Red Hills to Road Runner. | 115 | 0.8
200395 | 31001 | 51439 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Ochoa - Road Runner 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2017-03-20 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 519061 | 2016 | 558971 | 321590 | 2449206 | COMPLETE | 528232 | Ochoa Sub 115 kV | 528025 | Road Runner 115 kV | Construct new 115 kV line from Ochoa to Road Runner. | 115 | 0.8
200395 | 31001 | 51440 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Custer Mountain - Road Runner 115 kV Ckt 1 New Line | Regional Reliability | ITP | 2017-04-28 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 759610 | 2016 | 818017 | 759610 |  | COMPLETE | 528239 |  | 528025 | Road Runner 115 kV | Add new 1-mile segment to existing 115 kV line from Custer Mountain to Ochoa, re-terminating at Road Runner. | 115 | 11
200395 | 31001 | 51441 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Road Runner 115 kV Terminal Upgrades | Regional Reliability | ITP | 2017-03-28 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 4580864 | 2016 | 4933089 | 4580864 | 1137605 | COMPLETE | 528025 | Road Runner 115 kV |  |  | Install any terminal upgrades needed to accommodate new line terminals for Ochoa, Agave Red Hills, and Custer Mountain. | 115
200395 | 31001 | 51442 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Ochoa 115 kV Terminal Upgrades | Regional Reliability | ITP | 2017-03-28 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 25280 | 2016 | 27224 | 119406 | 289533 | COMPLETE | 528232 | Ochoa Sub 115 kV |  |  | Install any terminal upgrades needed to accommodate new line terminal from Road Runner. | 115
200395 | 31001 | 51443 | SPS | NM | Line - Road Runner - Agave Red Hills/Ochoa/Custer Mountain 115 kV New Line | Agave Red Hills 115 kV Terminal Upgrades | Regional Reliability | ITP | 2017-03-28 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 25280 | 2016 | 27224 | 25280 |  | COMPLETE | 528230 |  |  |  | Install any terminal upgrades needed to accommodate new line terminal from Road Runner. | 115
200392 | 31002 | 51444 | OGE | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (OGE) | Regional Reliability | ITP | 2019-08-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 750000 | 2016 | 807668 | 700000 |  | DELAY - MITIGATION | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 138 kV line from Lincoln to Meeker. The total estimated length of the Lincoln to Meeker line is 12 miles.OGE and Western Farmers Electric Cooperative shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138
200397 | 31002 | 51445 | WFEC | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | ITP | 2019-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6461344 | 6000000 | 2157636 | COMPLETE | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
200386 | 31003 | 51446 | AEP | OK | Sub - Northeastern Station 138 kV Terminal Upgrades | Northeastern Station 138 kV Terminal Upgrades | Regional Reliability | ITP | 2016-10-05 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 518011 | 2016 | 557841 | 518011 |  | COMPLETE | 510396 | NORTHEAST STATION 138KV |  |  | Install terminal upgrades at Northeastern station 138 kV substation on terminal for 138 kV line to Oolagah. | 138
200386 | 31005 | 51448 | AEP | OK | Sub - Elk City 138 kV Move Load | Elk City 138 kV Move Load | Regional Reliability | ITP | 2018-05-25 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2904911 | 2016 | 3128271 | 2904911 |  | COMPLETE | 511458 | ELK CITY 138 | 511459 | ELK CITY 69 | Move load from 69 kV bus to 138 kV bus at Elk City. | 138
210496 | 31007 | 51450 | SPS | TX | XFR - Sundown 230/115 kV Transformer | Sundown 230/115 kV Transformer | Regional Reliability | ITP | 2020-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT |  |  |  | 6698537 |  | DELAY - MITIGATION | 526435 | Sundown Interchange 230 kV | 526434 | Sundown Interchange 115 kV | Upgrade the existing 230/115 kV transformer at Sundown and replace any terminal equipment required to meet the full rating of the new transformer. | 230/115
200395 | 31008 | 51452 | SPS | NM | Multi - Artesia County 115 kV | Artesia Country Club Tap 115 kV Line Tap | Regional Reliability | ITP |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 336134 | 2016 | 361980 | 378619 |  | DELAY - MITIGATION | 527711 | Eagle Creek 115 kV | 527786 | Atoka Interchange 115 kV | Tap the 115 kV line from Atoka to Eagle Creek and install 3-way switch at tap point. | 115
200395 | 31008 | 51453 | SPS | NM | Multi - Artesia County 115 kV | Artesia Country Club - Artesia Country Club Tap 115 kV Ckt 1 New Line | Regional Reliability | ITP |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3092796 | 2016 | 3330603 | 2106736 | 278513 | DELAY - MITIGATION |  |  |  |  | Construct new 115 kV line from Artesia County Club to Artesia County Club Tap. | 115 | 3
200406 | 31009 | 51454 | AEP | OK | Line - Duncan - Tosco 69 kV Ckt 1 Rebuild | Duncan - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-05-04 | 2018-06-01 | 2016-08-17 | 2016 ITPNT | 5974766 | 2016 | 6434170 | 5974766 | 8591402 | COMPLETE | 511452 | DUNCAN 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Duncan to Tosco. Replace wave trap at Duncan. | 69 | 3.86 | 3.86 | 69
| 31014 | 51467 | NPPD |  | Sub - Friend 115kV Substation - GEN-2014-039 Addition | Friend 115kV Substation - GEN-2014-039 Addition (TOIF) | Generation Interconnection | GI | 2017-10-15 | [6 empty] | 875000 |  | ON SCHEDULE < 4 |  |  |  |  | Install 115kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, and associated and miscellaneous material.; One (1) 115 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Friend 115 kV substation.
| 31014 | 51468 | NPPD |  | Sub - Friend 115kV Substation - GEN-2014-039 Addition | Friend 115kV Substation - GEN-2014-039 Addition | Generation Interconnection | GI | 2017-10-15 | [6 empty] | 4300000 |  | ON SCHEDULE < 4 |  |  |  |  | Expand the substation to a ring bus configuration. Work to include the installation of three (3) 115kV circuit breakers, disconnect switches, associated bus, supports, relay panels, and all associated and miscellaneous equipment.
| 31018 | 51474 | OGE |  | Sub - Minco 345kV GEN-2014-056 & GEN-2015-057 Addition | Minco 345kV Substation GEN-2014-056 Addition (TOIF) | Generation Interconnection | GI | 2018-10-15 | [6 empty] | 10500 | 10139 | COMPLETE |  |  |  |  | Work for relaying and relay verification.
200407 | 31021 | 51478 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Mustang - Seminole 115 kV Ckt 1 New Line | Regional Reliability | ITP |  | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 15007492 | 2016 | 16161427 | 11419764 |  | DELAY - MITIGATION | 527146 | Mustang Interchange North Bus 115 kV | 527275 | Seminole Interchange 115 kV | Construct new 115 kV line from Mustang to Seminole. | 115 | 19.7
200407 | 31021 | 51479 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Mustang 115 kV Terminal Upgrades | Regional Reliability | ITP |  | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 2712194 | 2016 | 2920736 | 3404512 |  | DELAY - MITIGATION | 527146 | Mustang Interchange North Bus 115 kV |  |  | Install terminal upgrades at Mustang 115 kV substation needed to accommodate termination of new line from Seminole. | 115 | 19.7
200407 | 31021 | 51480 | SPS | TX | Line - Mustang - Seminole 115 kV Ckt 1 New Line | Seminole 115 kV Terminal Upgrades | Regional Reliability | ITP |  | 2017-06-01 | 2016-08-17 | 2016 ITPNT | 2016340 | 2016 | 2171378 | 2502793 |  | DELAY - MITIGATION | 527275 | Seminole Interchange 115 kV |  |  | Install terminal upgrades at Seminole 115 kV substation needed to accommodate termination of new line from Mustang. | 115 | 19.7
200395 | 31022 | 51481 | SPS | TX | Line - Canyon East Tap - Randall 115 kV Ckt 1 Rebuild | Canyon East Tap - Randall 115 kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4804292 | 2016 | 5173697 | 2908059 |  | DELAY - MITIGATION | 524523 | Canyon East Sub 115 kV | 524364 | Randall County Interchange 115 kV | Rebuild 3-mile segment of 115 kV line from Canyon East Tap to Randall. | 115
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | ITP | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4307563 | 4000000 |  | DELAY - MITIGATION | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2440234 | 2266000 |  | RE-EVALUATION | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
200417 | 31031 | 51503 | BEPC | ND | Multi - Kummer Ridge - Roundup 345 kV New Line and Patent Gate and Roundup 345/115 kV Substations | Roundup 345/115 kV Transformer | Regional Reliability | ITP | 2016-09-01 | 2017-06-01 | 2016-12-28 | 2016 ITPNT | 6662000 | 2016 | 7174245 | 6662000 | 3448356 | COMPLETE |  |  |  |  | Install new 345/115 kV transformer at Roundup. | 345/115
200417 | 31031 | 51504 | BEPC | ND | Multi - Kummer Ridge - Roundup 345 kV New Line and Patent Gate and Roundup 345/115 kV Substations | Patent Gate 345/115 kV Transformer | Regional Reliability | ITP | 2016-09-01 | 2017-06-01 | 2016-12-28 | 2016 ITPNT | 6122000 | 2016 | 6592724 | 6662000 |  | COMPLETE |  |  |  |  | Install new 345/115 kV transformer at Patent Gate. | 345/115
200388 | 31032 | 51506 | BEPC | ND | Multi - Plaza 115 kV Substation and Blaisdell - Plaza 115 kV New Line | Plaza 115 kV Substation | Regional Reliability | ITP | 2018-02-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4110395 | 2016 | 4426446 | 3918000 |  | COMPLETE |  |  |  |  | Tap the 115 kV line from Makoti to Parshall to create new Plaza substation. | 115
200388 | 31032 | 51507 | BEPC | ND | Multi - Plaza 115 kV Substation and Blaisdell - Plaza 115 kV New Line | Blaisdell - Plaza 115 kV New Line | Regional Reliability | ITP | 2018-02-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15272151 | 2016 | 16446436 | 14841308 |  | COMPLETE |  |  |  |  | Constuct new 115 kV line from Blaisdell to new Plaza substation. | 115 | 36
200388 | 31032 | 51508 | BEPC | ND | Multi - Plaza 115 kV Substation and Blaisdell - Plaza 115 kV New Line | Plaza 115 kV Cap Bank | Regional Reliability | ITP | 2018-02-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 820000 | 2016 | 883050 | 283000 |  | COMPLETE |  |  |  |  | Install new 15-MVAR cap bank at new Plaza substation. | 115
200388 | 31033 | 51509 | BEPC | ND | Line - Berthold - Southwest Minot 115 kV Ckt 1 Reconductor | Berthold - Southwest Minot 115 kV Ckt 1 Reconductor | Regional Reliability | ITP | 2017-10-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3731074 | 2016 | 4017959 | 2876720 |  | COMPLETE |  |  |  |  | Reconductor 115 kV line from Berthold to Southwest Minot. | 115 |  | 26.44
200393 | 31038 | 51521 | OPPD | NE | Device - S964 69 kV Cap Bank | S964 69 kV Cap Bank | Regional Reliability | ITP | 2020-06-01 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 722660 | 2016 | 778226 | 722660 |  | ON SCHEDULE < 4 | 647964 | Sub 964 |  |  | Install new 10-MVAR capacitor bank at S964 69 kV. | 69
200406 | 31039 | 51524 | AEP | OK | Line - Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Comanche Tap - Tosco 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2016-12-19 | 2020-06-01 | 2016-08-17 | 2016 ITPNT | 4365864 | 2016 | 4701558 | 4365864 |  | COMPLETE | 511498 | COMANCHE TAP 69KV | 511457 | TOSCO 69KV | Rebuild 69 kV line from Comanche Tap to Tosco. | 69 | 3.2 | 3.2 | 69
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | ITP | 2019-09-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 592290 | 550000 |  | DELAY - MITIGATION | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | ITP | 2019-09-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3230672 | 3600000 |  | DELAY - MITIGATION |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
200418 | 31042 | 51528 | OGE | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 345 kV Substation | Regional Reliability | ITP | 2019-04-17 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 7700661 | 2017 | 8090507 | 13758800 | 14566861 | COMPLETE | 515375 | Woodward EHV 345kv | 539801 | Thistle 345kV | Tap the double-circuit 345 kV line from Woodward to Thistle to construct and interconnect the new DeGrasse substation. Install any 345 kV substation facilities needed for the new 345/138 kV transformer. | 345 | 0.38
200418 | 31042 | 51529 | OGE | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 345/138 kV Transformer | Regional Reliability | ITP | 2019-04-17 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 3600000 | 2017 | 3782250 | 3281064 | 7607868 | COMPLETE |  |  |  |  | Install new 345/138 kV transformer at the new DeGrasse substation. | 345/138
200418 | 31042 | 51530 | OGE | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse - Knob Hill 138 kV New Line | Regional Reliability | ITP | 2019-04-17 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 8383000 | 2017 | 8807389 | 7155975 | 7536594 | COMPLETE |  |  | 514795 | KNOBHILL 138 | Construct new 138 kV line from the new DeGrasse substation to Knob Hill. | 138 | 12.36
200419 | 31042 | 51531 | WFEC | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | ITP | 2020-07-01 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1470875 | 5700000 |  | RE-EVALUATION | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
200417 | 31031 | 51543 | BEPC | ND | Multi - Kummer Ridge - Roundup 345 kV New Line and Patent Gate and Roundup 345/115 kV Substations | Patent Gate 345 kV Substation | Regional Reliability | ITP | 2016-09-01 | 2017-06-01 | 2016-12-28 | 2016 ITPNT | 30000000 | 2016 | 32306719 | 30000000 |  | COMPLETE |  |  |  |  | Tap the 345 kV line from Charlie Creek to Jusdon to construct the new Patent Gate substation. Install any necessary 345 kV terminal upgrades needed for new 345/115 kV transformer at the new Patent Gate substation. | 345
200417 | 31031 | 51544 | BEPC | ND | Multi - Kummer Ridge - Roundup 345 kV New Line and Patent Gate and Roundup 345/115 kV Substations | Roundup 345 kV Substation | Regional Reliability | ITP | 2016-09-01 | 2017-06-01 | 2016-12-28 | 2016 ITPNT | 27100000 | 2016 | 29183736 | 27100000 | 16887418 | COMPLETE |  |  |  |  | Tap the 345 kV line from Antelope Valley Station to Charlie Creek to construct the new Roundup substation. Install any necessary 345 kV terminal upgrades needed for new 345/115 kV transformer at the new Roundup substation. | 345
200395 | 31051 | 51549 | SPS | TX | Sub - Terry Co. - Wolfforth 115 kV Terminal Upgrades | Terry Co. - Wolfforth 115 kV Terminal Upgrades | Regional Reliability | ITP | 2018-06-01 | 2020-04-01 | 2016-05-17 | 2016 ITPNT | 1461643 | 2016 | 1574030 | 1461643 |  | COMPLETE | 526736 | Terry County Interchange 115 kV | 526524 | Wolfforth Interchange 115 kV | Upgrade terminal equipment at Terry Co. and Wolfforth to increase the rating of the 115 kV line from Terry Co. to Wolfforth. | 115
200386 | 31057 | 51558 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - McAlester 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 13512897 | 2016 | 14551912 | 11805970 |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510899 | McALESTER 69KV | Rebuild 9.9-mile 69 kV line from Army Ammo to McAlester. | 69
200386 | 31057 | 51559 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Army Ammo - Savanna - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 15146464 | 2016 | 16311085 | 15595092 |  | DELAY - MITIGATION | 510912 | ARMY AMMUNITION DEPOT | 510885 | PITTSBURG 69KV | Rebuild 9.6-mile 69 kV line from Army Ammo to Savanna to Pittsburg. | 69
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | ITP | 2019-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668582 | 2016 | 23334693 | 21981548 |  | DELAY - MITIGATION | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
200386 | 31058 | 51561 | AEP | OK | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Fort Towson - Kiamichi Pump Tap 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-12-21 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 11778983 | 2016 | 12684677 | 11778983 |  | COMPLETE | 510876 | KIAMICHI PUMP TAP | 510917 | FORT TOWSON | Rebuild 9.0-mile 69 kV line from Fort Towson to Kiamichi Pump Tap. | 69
200386 | 31058 | 51562 | AEP | OK | Line - Fort Towson - Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Kiamichi Pump Tap - Valliant 69 kV Ckt 1 Rebuild | Regional Reliability | ITP | 2018-12-21 | 2018-06-01 | 2016-05-17 | 2016 ITPNT | 7699929 | 2016 | 8291982 | 7699929 |  | COMPLETE | 510876 | KIAMICHI PUMP TAP | 510910 | VALLIANT 69KV | Rebuild 4.8-mile portion of 69 kV line from Kiamichi Pump Tap to Valliant. | 69
200420 | 31061 | 51565 | SPS | NM | Line - Livingston Ridge - Wipp 115 kV Ckt 1 Rebuild | Livingston Ridge - Wipp 115 kV Ckt 1 Rebuild | Regional Reliability | TS |  | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 264157 | 2017 | 277530 | 1002000 |  | DELAY - MITIGATION | 527952 | Livingston Ridge Sub 69 kV | 528009 | WIPP Sub 115 kV | Rebuild 2.8-mile 115 kV line from Livingston Ridge to Wipp. | 115
200420 | 31063 | 51567 | SPS | NM | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 806194 | 890000 |  | ON SCHEDULE < 4 | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
200418 | 31042 | 51569 | OGE | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (OGE) | Regional Reliability | ITP | 2019-04-17 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 7723383 | 2017 | 8114379 | 4562495 |  | COMPLETE | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. OGE and Western Farmers Electric Cooperative shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138
200399 | 30496 | 51570 | BEPC | NE | Multi - Bobcat Canyon 345/115 kV and Bobcat Canyon - Scottsbluff 115 kV | Stegall 345 kV Terminal Upgrades | Regional Reliability | ITP | 2017-06-01 | 2014-06-01 | 2016-08-17 | 2014 ITPNT |  |  |  | 2499727 |  | COMPLETE | 659135 | STEGALL 345 kV |  |  | Install 345 kV breaker, terminal equipment, and dead end structure at the Stegall substation. | 345
| 30786 | 51577 | NPPD |  | Sub - Dixon County 230kV | Dixon County 230kV Substation (TOIF) | Generation Interconnection | GI | 2018-11-01 | [6 empty] | 501197 |  | IN SERVICE |  |  |  |  | Dixon County 230kV Substation Addition: Build 230kV Substation addition on the Twin Church – Hoskins 230kV to accommodate new 230kV interconnection. Includes: 230kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities to the new Transmission Owner substation. | 230
| 30937 | 51602 | SPS |  | SUB - TUCO 230kV Switching Station GEN-2012-020 Addition | TUCO 230kV Switching Station GEN-2012-020 Addition (TOIF) | Generation Interconnection | GI | 2018-12-14 | [6 empty] | 260000 |  | ON SCHEDULE < 4 |  |  |  |  | TUCO 230kV Switching Station: Communications; Revenue Metering; 230kV Line arrestors.
| 30960 | 51609 | OGE |  | SUB - Beaver County 345kV - Add 345kV terminal for GEN-2013-030 | Beaver County Substation - Add 345kV terminal for GEN-2013-030 (TOIF) | Generation Interconnection | GI | 2019-10-28 | [6 empty] | 1099958 |  | COMPLETE |  |  |  |  | Beaver County 345 kV: Add one (1) 345 kV line terminal including dead-end structure, substation steel, substation bus, interconnection metering, line switch and associated equipment. No additional Right-of-Way is included in this cost.
| 30956 | 51610 | NPPD |  | Multi - GEN-2013-032 Interconnection Work | Antelope 115kV - Add terminal for GEN-2013-032 (TOIF) | Generation Interconnection | GI | 2018-10-03 | [6 empty] | 873106 |  | IN SERVICE |  |  |  |  | Add one (1) 115 kV dead-end tower, arresters, line switch, revenue meter and other line relaying equipment necessary to interconnect the Interconnection Customer Interconnection Facilities to the new Transmission Owner substation.
| 31075 | 51614 | KCPL |  | Sub - Tap Centerville-Marmaton 161kV GEN-2015-016 Addition | Tap Centerville-Marmaton 161kV GEN-2015-016 Addition (NU) | Generation Interconnection | GI | 2018-06-01 | [6 empty] | 5361925 |  | IN SERVICE |  |  |  |  | Transmission Owner’s new 161 kV Interconnection Switch Station: Construct a new ring bus switch station on the 161 kV transmission line between Centerville and Marmaton.; Transmission Owner’s Centerville-Marmaton 161 kV transmission line: Transmission Owner will install two (2) new dead-end towers in the line and terminate transmission line to dead-ends in the Transmission Owner Switch Station.; Transmission Owner Switch Station: Install microwave communications for system protection, voice communication, and data telemetry. Commercial phone lines will not be utilized for communications.; Centerville Substation – Install new relays and relay panels.; Allowance Funds Used During Construction and contingency for all Transmission Owner construction.
200444 | 31079 | 51623 | SPS | TX | Sub - Tuco - Stanton 115 kV Terminal Upgrades | Tuco - Stanton 115 kV Terminal Upgrades | Economic | ITP | 2018-12-31 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 283963 | 2017 | 298339 | 0 |  | DELAY - MITIGATION | 525828 | TUCO Interchange 115 kV | 526076 | Stanton Sub 115 kV | Upgrade any necessary terminal equipment at Stanton and/or Tuco to increase the rating of the 115 kV line between the two substations. | 115
200444 | 31080 | 51624 | SPS | TX | Sub - Stanton - Indiana 115 kV Terminal Upgrades | Stanton - Indiana 115 kV Terminal Upgrades | Economic | ITP |  | 2017-01-01 | 2017-02-22 | 2017 ITP10 |  |  |  | 0 |  | DELAY - MITIGATION | 526076 | Stanton Sub 115 kV | 526146 | Indiana Sub 115 kV | Upgrade any necessary terminal equipment at Indiana and/or Stanton to increase the rating of the 115 kV line between the two substations. | 115
200444 | 31081 | 51625 | SPS | TX | Sub - Indiana - SP-Erskine 115 kV Terminal Upgrades | Indiana - SP-Erskine 115 kV Terminal Upgrades | Economic | ITP | 2020-02-28 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 1133153 | 2017 | 1190519 | 1178153 |  | DELAY - MITIGATION | 526146 | Indiana Sub 115 kV | 526109 | South Plains REC-Erskine 115 kV | Upgrade any necessary terminal equipment at Indiana and/or SP-Erskine to increase the rating of the 115 kV line between the two substations. | 115
200467 | 31082 | 51626 | WR | KS | Sub - Butler - Altoona 138 kV Terminal Upgrades | Butler - Altoona 138 kV Terminal Upgrades | Economic | ITP | 2018-09-21 | 2017-01-01 | 2017-11-14 | 2017 ITP10 | 247332 | 2017 | 259853 | 274649 | 274649 | COMPLETE | 532987 | BUTLER 138 KV | 533001 | ALTOONA 138 KV | Upgrade any necessary terminal equipment at Altoona and Butler substations to increase the rating of the 138 kV line. | 138
200430 | 31083 | 51628 | WR | KS | Sub - Neosho - Riverton 161 kV Terminal Upgrades | Neosho 161 kV Terminal Upgrades | Economic | ITP | 2018-12-07 | 2017-01-01 | 2017-02-21 | 2017 ITP10 | 137488 | 2017 | 144448 | 107669 |  | COMPLETE | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Upgrade any necessary terminal equipment at Neosho to increase the rating of the 161 kV line between Neosho substation and Riverton substation. | 161
200428 | 31085 | 51630 | KCPL | MO | Device - Northeast - Charlotte - Crosstown 161 kV Reactor | Northeast - Charlotte - Crosstown 161 kV Reactor | Economic | ITP | 2018-03-01 | 2018-01-01 | 2017-02-22 | 2017 ITP10 | 500000 | 2017 | 525313 | 204681 | 204681 | COMPLETE | 542985 | NORTHEAST 161 KV | 542990 | CROSSTOWN 161 KV | Install new 2-ohm line reactor at Northeast substation on the 161 kV line from Northeast to Charlotte to Crosstown. | 161
200458 | 31086 | 51631 | WR | KS | Line - DePaul - Girard Jct - Franklin - Frontenac 69 kV | DePaul - Girard Jct 69 kV | Regional Reliability | TS | 2018-11-15 | 2018-12-31 | 2017-06-23 | DPA-2016-March-596 | 2908572 | 2017 | 3055818 | 5672324 |  | IN SERVICE |  |  |  |  | 1.71 miles of the existing DePaul-Girard Jct. 69 kV line will be rebuilt with single 1192.5 Bunting ACSR. | 69 | 1.71
200458 | 31086 | 51632 | WR | KS | Line - DePaul - Girard Jct - Franklin - Frontenac 69 kV | Franklin - Frontenac 69 kV | Regional Reliability | TS | 2018-11-15 | 2018-12-31 | 2017-06-23 | DPA-2016-March-596 | 9287542 | 2017 | 9757724 | 8875465 |  | IN SERVICE |  |  |  |  | Two new 3.43 mile circuits of 69 kV line will be constructed with a single 1192.5 Bunting ACSR from Franklin substation to the point on the DePaul-Girard Jct. 69 kV line where the rebuild ends. | 69 | 3.43
200429 | 31127 | 51730 | MIDW | KS | Line - Knoll - Post Rock 230 kV New Line Ckt 2 | Knoll - Post Rock 230 kV New Line Ckt 2 | Economic | ITP | 2018-11-11 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 475463 | 2017 | 499533 | 790927 |  | COMPLETE | 530558 | KNOLL 230 KV | 530584 | POST ROCK 230 KV | Build a new second 0.5-mile 230 kV line from Knoll to Post Rock. | 230 | 0.68
200431 | 31131 | 51738 | AEP | AR/OK | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (AEP) | Economic | ITP | 2019-05-31 | 2017-01-01 | 2017-02-21 | 2017 ITP10 | 4780000 | 2017 | 5021988 | 4780000 |  | COMPLETE | 506948 | SILOAM SPRINGS | 512643 | SILOAM CITY 161 | Rebuild 2.1-mile 161 kV line from Siloam Springs (AEP) - Siloam Springs City (GRDA) and upgrade terminal equipment at Siloam Springs. | 161
200432 | 31131 | 51739 | GRDA | OK | Line - Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild | Siloam Springs - Siloam Springs City 161 kV Ckt 1 Rebuild (GRDA) | Economic | ITP | 2019-05-31 | 2017-01-01 | 2017-02-21 | 2017 ITP10 | 312400 | 2017 | 328215 | 440000 | 330549 | COMPLETE | 506948 | SILOAM SPRINGS | 512643 | SILOAM CITY 161 | Upgrade terminal equipment at Siloam Springs City (GRDA) to increase the rating of the line between Siloam Springs (AEP) and Siloam Springs City (GRDA)substations. | 161
210506 | 31139 | 51757 | KCPL | MO | Line - Crosstown - Blue Valley 161 kV New Line | Crosstown 161 kV Terminal Upgrades | Regional Reliability | ITP | 2023-06-30 | 2020-06-01 | 2018-12-11 | 2018 ITPNT |  |  |  | 1120000 |  | DELAY - MITIGATION WINDOW | 542990 | CROSSTOWN 161 KV | 543000 | BLUE VALLEY 161 KV | Install any necessary terminal upgrades at Crosstown to accommodate new 161 kV line from Blue Valley. | 161
210506 | 31139 | 51758 | KCPL | MO | Line - Crosstown - Blue Valley 161 kV New Line | Blue Valley 161 kV Terminal Upgrades | Regional Reliability | ITP | 2023-06-30 | 2020-06-01 | 2018-12-11 | 2018 ITPNT |  |  |  | 1400000 |  | DELAY - MITIGATION WINDOW | 542990 | CROSSTOWN 161 KV | 543000 | BLUE VALLEY 161 KV | Install any necessary terminal upgrades at Blue Valley to accommodate new 161 kV line from Crosstown. | 161
210506 | 31139 | 51759 | KCPL | MO | Line - Crosstown - Blue Valley 161 kV New Line | Blue Valley - Crosstown 161kV Ckt1 | Regional Reliability | ITP | 2023-06-30 | 2020-06-01 | 2018-12-11 | 2018 ITPNT |  |  |  | 18711000 |  | DELAY - MITIGATION WINDOW | 542990 | CROSSTOWN 161 KV | 543000 | BLUE VALLEY 161 KV | New 5.64 mile 161 kV line from Blue Valley to Crosstown. | 161 | 6
200433 | 31144 | 51764 | WFEC | OK | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | ITP | 2020-12-01 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 105063 | 0 |  | DELAY - MITIGATION | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
| 31147 | 51766 | SPS |  | Sub - Tap Tolk - Yoakum 230kV (Needmore) - GEN-2013-027 Addition | Tap Tolk - Yoakum 230kV (Needmore) - GEN-2013-027 Addition (TOIF) | Generation Interconnection | GI | 2018-10-26 | [6 empty] | 300000 |  | COMPLETE |  |  |  |  | Construct one (1) 230 kV line terminal including line switches, dead end structure, communications, revenue metering, line arresters and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer's Generating Facility.
| 31147 | 51767 | SPS |  | Sub - Tap Tolk - Yoakum 230kV (Needmore) - GEN-2013-027 Addition | Tap Tolk - Yoakum 230kV (Needmore) - GEN-2013-027 Addition (NU) | Generation Interconnection | GI | 2018-10-26 | [6 empty] | 6398806 |  | COMPLETE |  |  |  |  | Construct 230 kV, three breaker ring bus substation with line terminals for transmission lines to Tolk Station 230 kV and Yoakum 230 kV. The remaining line terminal to interconnect the Generating Facility is apportioned by Appendix A, Item 1.(b). Transmission Owner's new substation to include three (3) 3000A circuit breakers, disconnect switches, line relaying, and all associated and miscellaneous equipment. Also includes approximately twenty acres of land for siting the new substation.; Loop Tolk - Yoakum 230kV line into new three breaker ring-bus substation for GEN-2013-027. Includes all new line structures, foundations, conductors, insulators and all other associated work and materials.
200434 | 31150 | 51774 | OGE | OK | Sub - Lula - Tupelo Tap 138 kV Terminal Upgrades | Lula- Tupelo Tap 138 kV Terminal Upgrades | Economic | ITP | 2019-01-18 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 305000 | 2017 | 320441 | 305000 | 168028 | COMPLETE | 515192 | LULA 138 | 521071 | TUPELO TAP | Upgrade terminal equipment at Lula to increase the rating of the line between the Lula substation and Tupelo Tap substation. | 138
200429 | 31127 | 51815 | MIDW | KS | Line - Knoll - Post Rock 230 kV New Line Ckt 2 | Knoll Sub 230 kV Terminal | Economic | ITP | 2018-11-11 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 1903595 | 2017 | 1999964 | 1938416 |  | COMPLETE |  |  | 530558 | KNOLL 230 KV | Add a 230 kV line terminal to the existing substation. | 230
200429 | 31127 | 51816 | MIDW | KS | Line - Knoll - Post Rock 230 kV New Line Ckt 2 | Post Rock Sub 230 kV Terminal | Economic | ITP | 2018-11-11 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 1493227 | 2017 | 1568822 | 1743688 |  | COMPLETE |  |  | 530584 | POST ROCK 230 KV | Add a 230 kV line terminal to the existing substation. | 230
200457 | 31175 | 51818 | SPS | TX | Line - Cox Interchange - Hale Co Interchange 115 kV Rebuild | Cox Interchange - Hale Co Interchange 115 kV Ckt 1 | Regional Reliability | TS |  | 2021-06-01 | 2017-05-15 | SPP-2016-AG1-AFS-3 | 13355250 | 2017 | 14031360 | 10562326 |  | DELAY - MITIGATION |  |  |  |  | Rebuild 19.88 miles of 115 kV transmission line from Cox Interchange to Hale Co Interchange. | 115 |  | 19.7
200457 | 31176 | 51819 | SPS | TX | Sub - Hockley County Interchange 115 kV Terminal Upgrades | Hockley County Interchange 115 kV Terminal Upgrades | Regional Reliability | TS |  | 2021-06-01 | 2017-05-15 | SPP-2016-AG1-AFS-3 | 228066 | 2017 | 239612 | 137534 |  | ON SCHEDULE < 4 |  |  |  |  | Replace wave trap at Hockley County Interchange to increase the line capacity for Hockley County Interchange - Lamb County Interchange 115 kV Ckt 1. | 115
200423 | 31183 | 51826 | OGE | OK | Sub - Muskogee 161 kV Terminal Upgrades | Hancock - Muskogee 161 kV Ckt 1 Terminal Upgrades | Regional Reliability | TS | 2018-07-10 | 2021-06-01 | 2017-01-12 | SPP-2016-AG1-AFS-1 | 37638 | 2017 | 39543 | 60913 | 60913 | COMPLETE |  |  |  |  | Replace wavetrap at Muskogee. | 161
200446 | 31186 | 51831 | AEP | TX/AR | Device - IPC 138 kV Cap Bank | IPC 138 kV Cap Bank | Regional Reliability | ITP | 2018-12-13 | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 1298048 | 2017 | 1363762 | 1917591 |  | COMPLETE |  |  |  |  | Install 28.8-MVAR capacitor bank at IPC 138 kV | 138
200455 | 41188 | 61834 | SPS | TX | Sub - Hale County 115 kV | Hale County 115 kV Terminal Upgrades | Regional Reliability | ITP | 2020-12-31 | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 766323 | 2017 | 805118 | 54858 | 49956 | DELAY - MITIGATION | 525454 | Hale Co Interchange 115 kV |  |  | Install terminal upgrades at both breaker terminals of the line on the 115 kV circuit V72 (Hale County - Kress Interchange) at Hale County. | 115
200444 | 41189 | 61836 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Martin - Pantex North 115 kV Terminal Upgrades | Economic | ITP | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 340814 | 324392 |  | COMPLETE | 523928 | Martin Sub 115 kV | 523938 | Pantex North Sub 115 kV | Upgrade any necessary terminal equipment at Martin and/or Pantex North to increase the rating of the 115 kV line between the two substations. | 115
200444 | 41189 | 61837 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Pantex South - Highland Tap 115 kV Terminal Upgrades | Economic | ITP | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 340814 | 324392 |  | COMPLETE | 523945 | Pantex South Sub 115 kV | 523931 | Highland Park Tap 115 kV | Upgrade any necessary terminal equipment at Pantex South and/or Highland Tap to increase the rating of the 115 kV line between the two substations. | 115
200455 | 41192 | 61840 | SPS | TX | Sub - Coulter 115 kV | Coulter 115 kV Terminal Upgrades | Regional Reliability | ITP |  | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 286869 | 2017 | 301392 | 270000 |  | DELAY - MITIGATION | 524306 | Coulter Interchange 115 kV |  |  | Install terminal upgrades on the 115 kV circuit W71 (Coulter - Puckett) at Coulter Substation. | 115
200455 | 41194 | 61844 | SPS | TX | Sub - Plant X - Sundown 230 kV | Plant X 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 217734 | 2017 | 228757 | 0 |  | DELAY - MITIGATION | 525481 | Plant X Station 230 kV |  |  | Install terminal upgradeson the 230 kV circuit K46 (Plant X - Sundown) at Plant X. | 230
200455 | 41194 | 61845 | SPS | TX | Sub - Plant X - Sundown 230 kV | Sundown 230 kV Terminal Upgrades | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 360540 | 2017 | 378792 | 360540 |  | DELAY - MITIGATION | 526435 | Sundown Interchange 230 kV |  |  | Install terminal upgrades on the 230 kV circuit K46 (Plant X - Sundown) at Sundown. | 230
210496 | 41197 | 61850 | SPS | TX | Terry County - LG Clauene 115 kV Terminal Upgrades | Terry County - LG Clauene 115 kV Terminal Upgrades | Regional Reliability | ITP |  | 2019-06-01 | 2018-08-17 | 2018 ITPNT |  |  |  | 466483 |  | DELAY - MITIGATION | 526491 | Lyntegar REC-Clauene 115 kV |  |  | Replace terminal equipment on the Clauene-Terry (circuit V55) line and address any line clearance concerns to meet or exceed the line's conductor rating. | 115
200455 | 41198 | 61852 | SPS | OK | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 103633 | 98639 |  | DELAY - MITIGATION | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
200455 | 41198 | 61853 | SPS | OK | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | ITP | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 113919 | 108430 |  | DELAY - MITIGATION | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
200476 | 41200 | 61856 | WAPA | ND | Sub - Williston 115 kV | Williston 115 kV Terminal Upgrades | Regional Reliability | ITP | 2017-11-20 | 2018-06-01 | 2018-02-21 | 2017 ITPNT | 5000 | 2017 | 5253 | 5000 |  | COMPLETE | 652421 | WILISTON |  |  | Install 115 kV terminal upgrades needed at Williston to increase the rating of the Williston - Judson line. | 115
200446 | 41202 | 61858 | AEP | OK | Line - Tulsa Southeast - E.61st 138 kV Rebuild | Tulsa Southeast - E.61st 138 kV Rebuild | Regional Reliability | ITP | 2019-12-20 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 6014381 | 2017 | 6318859 | 7238795 |  | DELAY - MITIGATION | 509811 | TULSA SOUTHEAST 138KV | 509831 | EAST 61st STREET | Rebuild Tulsa Southeast - E.61st 3.5-mile 138 kV line. | 138 | 1.8
200448 | 41209 | 61869 | EDE | MO | Line - Line -– Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Nichols – Republic North 69 kV Reconductor | Regional Reliability | ITP | 2018-04-13 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 4050000 | 2017 | 4255031 | 4050000 |  | COMPLETE | 547542 | SUB 170 - NICHOLS ST. | 547576 | SUB 345 - REPUBLIC NORTHEAST | Reconductor 9.7-mile 69 line from Nichols to Republic North. | 69 |  | 10
200448 | 41209 | 61870 | EDE | MO | Line - Line -– Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Republic Hines Street - Republic North 69 kV Reconductor | Regional Reliability | ITP | 2018-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 1450000 | 2017 | 1523406 | 1450000 |  | COMPLETE | 547443 | SUB 451 - REPUBLIC HINES STREET | 547576 | SUB 345 - REPUBLIC NORTHEAST | Reconductor 3.9-mile 69 kV line from Republic Hines Street to Republic North. | 69 |  | 3.5
200448 | 41209 | 61871 | EDE | MO | Line - Line -– Republic East – Republic Hines Street – Republic North – Nichols 69 kV Reconductor | Republic East - Republic Hines Street 69 kV Reconductor | Regional Reliability | ITP | 2018-06-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 800000 | 2017 | 840500 | 800000 |  | Complete | 547443 | SUB 451 - REPUBLIC HINES STREET | 547580 | SUB 359 - REPUBLIC EAST | Reconductor 1.3-mile 69 kV line from Republic East to Republic Hines Street. | 69 |  | 1.6
200462 | 41223 | 61894 | CPEC | ND | Line - New East Ruthville - SW Minot 115 kV New Line | East Ruthville - SW Minot 115 kV New Line | Regional Reliability | ITP | 2019-12-31 | 2018-06-01 | 2017-08-02 | 2017 ITPNT | 20746000 | 2017 | 21796266 | 20746000 |  | DELAY - MITIGATION | 655655 |  | 655657 |  | Construct new 24-mile 115 kV line from East Ruthville to SW Minot. | 115 | 23.8
200462 | 41223 | 61895 | CPEC | ND | Line - New East Ruthville - SW Minot 115 kV New Line | East Ruthville - SW Minot 115 kV line Terminal Upgrades | Regional Reliability | ITP | 2019-12-31 | 2018-06-01 | 2017-08-02 | 2017 ITPNT | 1035000 | 2017 | 1087397 | 1035000 |  | DELAY - MITIGATION | 655655 |  | 655657 |  | Install terminal upgrades needed for East Ruthville - SW Minot 24-mile 115 kV line. | 115
200452 | 51236 | 71926 | WAPA | SD | Multi - Roberts County - Sisseton 115kV | Roberts County 115 kV Substation | Regional Reliability | ITP | 2019-01-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 4300000 | 2017 | 4517688 | 3957000 |  | DELAY - MITIGATION | 655454 |  |  |  | Build new 115 kV substation at Roberts County between the Forman and Summit substations. | 115
200452 | 51236 | 71927 | WAPA | SD | Multi - Roberts County - Sisseton 115kV | XFR - Roberts County 115/69 kV Transformer | Regional Reliability | ITP | 2019-09-30 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 1200000 | 2017 | 1260750 | 1200000 |  | DELAY - MITIGATION | 655361 |  | 655454 |  | New 115/69 kV transformer at Roberts County. Install necessary 69 kV terminal equipment at Roberts County substation. | 115
| 51239 | 71933 | NPPD |  | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 4700000 |  | ON SCHEDULE < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
| 51239 | 71934 | NPPD |  | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | GI | 2020-11-01 | [6 empty] | 5900000 |  | ON SCHEDULE < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
| 51240 | 71935 | NPPD |  | Sub - Hoskins 345kV - GEN-2015-007 Addition | Hoskins 345kV - GEN-2015-007 Addition (TOIF) | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 16700000 |  | ON SCHEDULE < 4 | 640226 | Hoskins 345 kV |  |  | Hoskins 345 kV Substation - Install 345 kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformer and potential transformer and associated and miscellaneous material.; One (1) approximately sixteen (16) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Hoskins 345 kV substation.
| 51240 | 71936 | NPPD |  | Sub - Hoskins 345kV - GEN-2015-007 Addition | Hoskins 345kV - GEN-2015-007 Addition (NU) | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 4600000 |  | ON SCHEDULE < 4 | 640226 | Hoskins 345 kV |  |  | Hoskins 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
| 51240 | 71937 | TBD |  | Sub - Hoskins 345kV - GEN-2015-007 Addition | Hoskins 345kV - GEN-2015-007 Addition (MISO) | Generation Interconnection | GI | 2019-10-01 | [6 empty] | 50000 |  | ON SCHEDULE < 4 | 635200 | Raun | 645451 | Sub 3451 (Ft Cal) | Replace wave trap at Raun (MidAmerican Energy Company) – Replace one (1) wave trap at Raun and adjust relay settings. This will increase MidAmerican Energy Company’s rating of its section of the Raun – Ft Calhoun line to above 1107 MVA for a new rating of 1195 MVA. | 345
200450 | 51236 | 71938 | EREC | SD | Multi - Roberts County - Sisseton 115kV | Roberts County - Sisseton 69 kV New Line | Regional Reliability | ITP | 2019-09-30 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 603000 | 2017 | 633527 | 560800 |  | DELAY - MITIGATION | 655361 |  | 655303 |  | Construct new 1.5-mile 69 kV line from Sisseton to the new Roberts County substation being constructed by Western Area Power Administration (refer to NTC No. 200452, Network Upgrade ID No. 71926). | 69 | 1.9
| 51241 | 71939 | SEPC |  | Sub - Johnson Corner 115kV - GEN-2015-021 Addition | Johnson Corner 115kV - GEN-2015-021 Addition (TOIF) | Generation Interconnection | GI | 2020-03-01 | [6 empty] | 894061 |  | ON SCHEDULE < 4 | 531424 | JOHNSON CORNER 115 |  |  | 115 kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, one (1) 2000A circuit breaker, communications, control panel replacement, disconnect switches, revenue metering, and line arrestor, substation bus, and associated equipment. |  | 0.05
| 30781 | 71940 | NPPD |  | Sub - Rosemont 115kV Substation GEN-2008-123N Addition | Rosemont 115kV Substation GEN-2008-123N Addition (TOIF) | Generation Interconnection | GI | 2017-11-01 | [6 empty] | 1880000 |  | ON SCHEDULE < 4 |  |  |  |  | Rosemont 115 kV substation addition on the Pauline – Guide Rock 115 kV line to accommodate new 115 kV interconnection - Add 115kV dead-end tower, arresters, line equipment, metering, and associated equipment to terminate the 115kV line to the generating facility.; One (1) 115 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's new 115 kV Rosemont Substation.
| 51242 | 71941 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (TOIF) | Generation Interconnection | GI | 2020-02-28 | [6 empty] | 216180 |  | ON SCHEDULE < 4 |  |  |  |  | Add a single 115kV line termination, dead end structure, one (1) 115kV disconnect switch with ground blades, and line relaying. No additional Right-of-Way is included in this cost.
| 51242 | 71942 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (SANU) | Generation Interconnection | GI | 2020-02-28 | [6 empty] | 7109676 |  | ON SCHEDULE < 4 |  |  |  |  | Construct new 115 kV switchyard in a three breaker ring bus configuration. Construction to include the addition of three (3) 115 kV power circuit breakers, four (4) 115 kV disconnect switches, two (2) 115 kV disconnect switches with ground blades, instrument transformers, associated control and protection equipment, control building, high voltage bus, transmission line take-off structures, and conductor.
| 51242 | 71943 | WAPA |  | Multi - Sulphur 115kV - GEN-2014-001IS Addition | Sulphur 115kV - GEN-2014-001IS Addition (NU) | Generation Interconnection | GI | 2020-02-28 | [6 empty] | 8529876 |  | ON SCHEDULE < 4 |  |  |  |  | Maurine-Newell-Elk Creek-Rapid City 115 kV Transmission Lines - Replace thirty-five (35) 115 kV transmission structures.; Newell Substation - Replacement of the 115 kV strain bus, circuit switchers, and jumpers.; Elk Creek Substation - Replacement of the 115 kV strain bus, jumpers. Reset relays.; Rapid City Substation - Replacement of the main and transfer 115 kV buses, transfer bay, and transmission line bay (to Dry Creek).
200446 | 41233 | 71945 | AEP | OK | Line - Broken Arrow North - Lynn Lane East 138 kV Ckt 1 | Broken Arrow North - Lynn Lane East 138 kV Ckt 1 Reconductor | Regional Reliability | ITP | 2019-03-19 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 5714095 | 2017 | 6003371 | 5714095 |  | COMPLETE | 509786 | BROKEN ARROW NORTH - SOUTH TAP | 509804 | LYNN LANE TAP | Reconductor Broken Arrow - Lynn Lane East 7.2-mile 138 kV line | 138 |  | 7.13
200455 | 51246 | 71949 | SPS | TX | Sub - Nichols - 230 kV | Nichols 230 kV Terminal Upgrades | Regional Reliability | ITP |  | 2018-12-01 | 2017-05-12 | 2017 ITPNT | 490000 | 2017 | 514806 | 271060 |  | DELAY - MITIGATION WINDOW | 524044 | Nichols Station 230 kV | 524415 | Amarillo South Interchange 230 kV | Install terminal upgrades on the Nichols - Amarillo 230 kV circuit at Nichols. | 230
| 51247 | 71951 | OGE |  | Sub - Cleo Corner 138kV GEN-2015-048 Addition | Cleo Corner 138kV GEN-2015-048 Addition (TOIF) | Generation Interconnection | GI | 2019-06-14 | [6 empty] | 410000 |  | RE-EVALUATION |  |  |  |  | Transmission Owner’s Cleo Corner 138kV Substation: Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51247 | 71952 | OGE |  | Sub - Cleo Corner 138kV GEN-2015-048 Addition | Cleo Corner 138kV GEN-2015-048 Addition (NU) | Generation Interconnection | GI | 2019-06-14 | [6 empty] | 2558000 |  | RE-EVALUATION |  |  |  |  | Transmission Owner’s Cleo Corner 138kV Substation: Construct four (4) 2000 continuous ampacity breakers, control panel replacement, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Reroute transmission line to the south to open up the north terminal.
| 51248 | 71953 | OGE |  | Line - Cleo Corner – Cleo Plant Tap 138kV Ckt 1 | Cleo Corner - Cleo Plant Tap 138kV Ckt 1 | Generation Interconnection | GI | 2019-06-14 | [6 empty] | 61890 |  | RE-EVALUATION |  |  |  |  | Cleo Corner – Cleo Plant Tap 138kV Circuit #1: Change current transformers tap setting and testing.
200469 | 51249 | 71954 | KPP | KS | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | TS |  | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3690000 | 3600000 |  | ON SCHEDULE < 4 |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow.
200466 | 51249 | 71955 | WR | KS | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-2 | 7831427 | 2017 | 8227893 | 7131646 |  | ON SCHEDULE < 4 |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1
200466 | 51252 | 71958 | WR | KS | XFR - Creswell 138/69/13.2 kV Transformers | Creswell (CRSW TX-1) 138/69/13.2 kV Transformer Ckt 1 | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-2 | 3486230 | 2017 | 3662720 | 3249656 |  | ON SCHEDULE < 4 |  |  |  |  | Upgrade Creswell (CRSW TX-1) 138/69/13.2 kV transformer to 150/165 MVA. | 138/69
200466 | 51252 | 71959 | WR | KS | XFR - Creswell 138/69/13.2 kV Transformers | Creswell (CRSW TX-2) 138/69/13.2 kV Transformer Ckt 2 | Regional Reliability | TS | 2021-06-01 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-2 | 3621491 | 2017 | 3804829 | 3201470 |  | ON SCHEDULE < 4 |  |  |  |  | Upgrade Creswell (CRSW TX-2) 138/69/13.2 kV transformer to 150/165 MVA. | 138/69
210536 | 41199 | 71960 | SPS | TX | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | ITP |  | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9495447 | 1665947 |  | NTC - COMMITMENT WINDOW | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
200454 | 51253 | 71961 | NIPCO | IA | Sub - L-10 Southern 69 kV Terminal Upgrades | L-10 Southern 69 kV Terminal Upgrades | Regional Reliability | ITP | 2019-07-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 710000 | 2017 | 745944 | 769995 |  | COMPLETE |  |  |  |  | Install 69 kV breakers needed to close in the L-10 Southern to North Oakland 69 kV line | 69
200454 | 51253 | 71962 | NIPCO | IA | Sub - L-10 Southern 69 kV Terminal Upgrades | J16 69 kV Substation | Regional Reliability | ITP | 2019-07-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 1220000 | 2017 | 1281763 | 1507856 |  | COMPLETE |  |  |  |  | Build new 69 kV switching station to replace the K-116 switch | 69
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | TS | 2021-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 13010210 | 12692888 |  | DELAY - MITIGATION |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment.z | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5309148 | 5179657 |  | DELAY - MITIGATION |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5309148 | 5179657 |  | DELAY - MITIGATION |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
200477 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 11553014 | 11271233 |  | DELAY - MITIGATION |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
200477 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1305344 | 1273506 |  | DELAY - MITIGATION |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | TS | 2023-01-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 3795848 | 3703266 |  | DELAY - MITIGATION |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
200470 | 51260 | 71976 | CBPC | IA | Device - Prestage Family 69 kV Cap Bank | Prestage Family 69 kV Cap Bank | Regional Reliability | TS | 2018-09-01 | 2018-08-01 | 2018-01-19 | DPA-2017-March-735 | 1017500 | 2018 | 1042938 | 1017500 |  | COMPLETE |  |  |  |  | Add two new 9.6 MVAR capacitor banks (19.2 MVAR total) at the new Prestage Family 69 kV station | 69 | 1.5
| 51261 | 71980 | NPPD |  | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere 115kV Substation GEN-2015-087 Addition (TOIF) | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 300000 |  | RE-EVALUATION |  |  |  |  | Transmission Owner’s Belvidere 115kV Substation: Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; 115kV Transmission Line: One (1) approximately two-and-a-half (2.5) mile 115 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Belvidere 115 kV substation. | 115
| 51261 | 71981 | NPPD |  | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere 115kV Substation GEN-2015-087 Addition (NU) | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 5300000 |  | RE-EVALUATION |  |  |  |  | Transmission Owner’s Belvidere 115kV Substation: Construct new substation and three (3) line terminals, three (3) 2000 continuous ampacity breakers, cut in transmission line and re-terminate, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 115
| 51261 | 71982 | NPPD |  | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 1700000 |  | RE-EVALUATION |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115
| 51261 | 71983 | NPPD |  | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generation Interconnection | GI | 2019-11-01 | [6 empty] | 900000 |  | RE-EVALUATION | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115
| 51262 | 71984 | NPPD |  | Sub - Tobias 345kV Substation GEN-2015-088 Addition | Tobias 345kV Substation GEN-2015-088 Addition (TOIF) | Generation Interconnection | GI | 2019-01-01 | [6 empty] | 700000 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Tobias 345kV Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, protection, controls, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; 345kV Transmission Line: One (1) approximately two-and-a-half (2.5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Tobias 345 kV substation. | 345/345
| 51262 | 71985 | NPPD |  | Sub - Tobias 345kV Substation GEN-2015-088 Addition | Tobias 345kV Substation GEN-2015-088 Addition (NU) | Generation Interconnection | GI | 2019-01-01 | [6 empty] | 11700000 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Tobias 345kV Substation: Construct new substation and three (3) line terminals, five (5) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. | 345/345
| 51276 | 72002 | WR |  | Sub - Union Ridge 230kV GEN-2015-069 Addition | Union Ridge 230kV GEN-2015-069 Addition (TOIF) | Generation Interconnection | GI | 2018-09-24 | [6 empty] | 1523191 | 1523191 | COMPLETE |  |  |  |  | Transmission Owner’s Union Ridge 230 kV Substation: Construct one (1) 345 kV (230kV operating) line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; Allowance for Funds Used During Construction (AFUDC); Contingency
| 51276 | 72003 | WR |  | Sub - Union Ridge 230kV GEN-2015-069 Addition | Union Ridge 230kV GEN-2015-069 Addition (NU) | Generation Interconnection | GI | 2018-11-02 | [6 empty] | 584188 | 584188 | COMPLETE |  |  |  |  | Transmission Owner’s Union Ridge 230 kV Substation: Construct one (1) 345kV (230kV operating) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. The following are included in this cost estimate: Allowance for Funds Used During Construction (AFUDC), Contingency
200483 | 51277 | 72004 | OPPD | OK | Line - S1255 - S1260 161 kV | S1255 - S1260 161 kV Ckt 1 New Line | Regional Reliability | TS | 2020-01-01 | 2020-01-01 | 2018-02-27 | DPA-2017-May-746 | 14770262 | 2018 | 15139519 | 9435262 |  | ON SCHEDULE < 4 | 646255 | Sub 1255 | 646260 |  | Build new 5.3-mile 161 kV line from S1255 to S1260. | 161 | 5.9
210487 | 51278 | 72005 | CPEC | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | North Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | SP | 2020-12-31 | 2018-11-01 | 2018-08-17 | SUS-002 CPEC North Bismarck Breaker |  |  |  | 0 |  | DELAY - MITIGATION | 655644 |  | 655646 |  | Sponsored Upgrade - CPEC is changing the operational status of the 115 kV breaker 262 within the North Bismarck substation from a "normally open" device to a "normally closed" device. This change in configuration results in a 115 kV loop between WAPA's Bismarck and Ward 230 kV substations. | 115
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | SP | 2023-01-31 | 2024-06-01 | 2018-08-17 | SUS-002 CPEC North Bismarck Breaker |  |  |  | 90000 |  | DELAY - MITIGATION | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
200482 | 51280 | 72011 | WFEC | NE | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | TS | 2022-06-01 | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 512500 | 500000 |  | DELAY - MITIGATION | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
200482 | 51281 | 72012 | WFEC | OK | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | TS | 2022-06-01 | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1025000 | 1000000 |  | DELAY - MITIGATION | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
210483 | 51282 | 72013 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | TS | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2050000 | 2000000 |  | COMPLETE |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
210483 | 51282 | 72014 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | TS | 2019-07-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | DELAY - MITIGATION | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
210483 | 51282 | 72015 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2019-10-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8148750 | 7950000 |  | DELAY - MITIGATION | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
210483 | 51282 | 72016 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2019-12-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 6750000 | 2018 | 6918750 | 6750000 |  | DELAY - MITIGATION | 521016 | OKEENE | 521090 | WATONGA SW | Convert 13.5 mile 69 kV line from Okeene - Watonga SW to 138 kV. | 138 |  | 13.5 | 13.5
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-03-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 8610000 | 8400000 |  | DELAY - MITIGATION | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-10-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1281250 | 1250000 |  | DELAY - MITIGATION | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-03-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 4663750 | 4550000 |  | DELAY - MITIGATION | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | TS | 2020-10-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4100000 | 4000000 |  | DELAY - MITIGATION | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-03-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 5791250 | 5650000 |  | DELAY - MITIGATION | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-03-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4100000 | 3250000 |  | DELAY - MITIGATION | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-03-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4100000 | 10650000 |  | DELAY - MITIGATION | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
210483 | 51282 | 72025 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-03-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 10916250 | 1050000 |  | DELAY - MITIGATION | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
210483 | 51282 | 72026 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-12-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1076250 | 5000000 |  | DELAY - MITIGATION | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-03-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5125000 | 5300000 |  | DELAY - MITIGATION | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
210483 | 51282 | 72029 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW - Park Community 138 kV Ckt 1 New Line | Regional Reliability | TS | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4500000 | 2018 | 4612500 | 4500000 |  | COMPLETE |  |  |  |  | Construct new 9.0 mile 138 kV line from Kingfisher SW - Park Community. | 138 | 9
210483 | 51282 | 72030 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | TS | 2019-10-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4100000 | 4000000 |  | DELAY - MITIGATION |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | TS | 2020-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4356250 | 4250000 |  | DELAY - MITIGATION WINDOW | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 51283 | 72032 | WR |  | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | GI | 2020-12-01 | [6 empty] | 841431 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51283 | 72033 | WR |  | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | GI | 2020-12-01 | [6 empty] | 13362472 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
| 51283 | 72034 | OGE |  | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | GI | 2019-09-16 | [6 empty] | 20000 |  | ON SCHEDULE < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
210493 | 51285 | 72037 | CUS | MO | Multi - Brookline 345kV | Brookline 345kV Reactor | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3471864 | 2018 | 3558661 | 3471864 |  | DELAY - MITIGATION | 549984 | Brookline 345 |  |  | Install new 50 MVAR reactor at Brookline 345kV. | 345
210493 | 51285 | 72038 | CUS | MO | Multi - Brookline 345kV | Brookline 345kV Substation Expansion | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 794411 | 2018 | 814271 | 794411 |  | DELAY - MITIGATION | 549984 | Brookline 345 |  |  | Brookline 345kV Substation expansion to accommodate new 50MVAR reactor. | 345
210495 | 51292 | 72047 | KCPL | KS | Sub - Brookridge - Overland Park 161kV Terminal Upgrades | Brookridge - Overland Park 161kV Terminal Upgrades | Regional Reliability | ITP | 2019-10-07 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 745000 | 2018 | 763625 | 745000 |  | COMPLETE | 543033 | BROOKRIDGE 161 KV | 543047 | OVERLAND PARK 161 KV | Upgrade terminal equipment on both sides of the Brookridge to Overland Park 161 kV line. | 161
210495 | 51294 | 72049 | KCPL | KS | Sub - Olathe - Switzer 161kV Ckt1 Terminal Upgrades | Olathe - Switzer 161kV Ckt1 | Regional Reliability | ITP | 2020-02-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 1088000 | 2018 | 1115200 | 1088000 |  | DELAY - MITIGATION | 543036 | OLATHE 161 KV | 543045 | SWITZER 161 KV | Replace terminal equipment on the Olathe - Switzer 161 kV branch from at Switzer | 161
210492 | 51295 | 72050 | BEPC | MT | Line - Lewis - Richland 115kV Ckt 1 | Lewis - Richland 115kV Ckt 1 (BEPC) | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT |  |  |  | 5000 |  | DELAY - MITIGATION WINDOW | 652451 | RICHLAND | 661056 | Lewis & Clark | Adjust CT taps on Lewis to Richland to 1200/5. | 115
210497 | 51295 | 72052 | WAPA | MT | Line - Lewis - Richland 115kV Ckt 1 | Lewis - Richland 115kV Ckt 1 (WAPA) | Regional Reliability | ITP | 2019-06-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 100000 | 2019 | 100000 | 136000 |  | DELAY - MITIGATION WIINDOW | 652451 | RICHLAND | 661056 | Lewis & Clark | Reconductor 0.1 miles of 115 kV line from Lewis to Richland and replace structures as needed. | 115 |  | 0.1
210491 | 51300 | 72066 | AEP | AR | Multi - Fig Five - VBI 69kV | Fig Five - VBI North 69kV Ckt 1 | Regional Reliability | ITP | 2019-04-11 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3357600 | 2018 | 3441540 | 3357600 |  | COMPLETE | 504185 | Figure Five | 504032 | VBI NORTH | Rebuild 4.2 miles of 69 kV line from Fig Five to VBI. | 69
210490 | 51300 | 72067 | AECC | AR | Multi - Fig Five - VBI 69kV | Fig 5 - VBI North 69 kV Ckt 1 #2 | Regional Reliability | ITP | 2019-05-16 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 51200 | 2018 | 52480 | 52100 | 32996 | COMPLETE | 504032 | VBI NORTH |  |  | Upgrade terminal equipment for Fig Five - VBI 69 kV line at VBI North. | 69
210498 | 51305 | 72076 | WR | KS | XFR - Lawrence Hill 230/115kV | Lawrence Hill 230/115kV Transformer | Regional Reliability | ITP | 2020-06-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 5781164 | 2018 | 5925693 | 5781164 |  | DELAY - MITIGATION | 532853 | LAWRENCE HILL 230 KV | 533250 | LAWRENCE HILL 115 KV | Replace the 230/115 kV transformer at Lawrence Hill. | 230
210496 | 51316 | 72095 | SPS | TX | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | ITP |  | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 238776 | 674000 |  | ON SCHEDULE < 4 | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-12-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 10250000 | 10000000 |  | DELAY - MITIGATION | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2021-03-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7072500 | 6900000 |  | DELAY - MITIGATION | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
210489 | 51327 | 82113 | WFEC | OK | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-01-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 7790000 | 7600000 |  | DELAY - MITIGATION |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
210489 | 51327 | 82114 | WFEC | OK | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-01-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 307500 | 300000 |  | DELAY - MITIGATION | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | TS | 2020-12-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6457500 | 6300000 |  | DELAY - MITIGATION | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 51328 | 82116 | WR |  | Sub - Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection | Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection (TOIF) | Generation Interconnection | GI | 2019-11-05 | [6 empty] | 1179325 |  | IN SERVICE | 532768 | EMPORIA ENERGY CENTER |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.; Allowance for Funds Used During Construction (AFUDC)
| 51328 | 82117 | WR |  | Sub - Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection | Emporia Energy Center 345 kV Substation GEN-2015-073 Interconnection (NU) | Generation Interconnection | GI | 2019-11-05 | [6 empty] | 1037608 |  | IN SERVICE | 532768 | EMPORIA ENERGY CENTER |  |  | Construct One (1) 345 kV 3000 continuous ampacity breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. The following are included in this cost estimate: Allowance for Funds Used During Construction (AFUDC)
210494 | 51330 | 82123 | EREC | SD | Multi - Lakeview County 69kV | Lakeview 69 kV Substation #3 | Regional Reliability | ITP | 2020-02-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 3732000 | 2018 | 3825300 | 3732000 |  | DELAY - MITIGATION |  |  |  |  | Build new Lakeview 69 kV Substation to replace existing motor-operated switch | 69
210494 | 51330 | 82124 | EREC | SD | Multi - Lakeview County 69kV | Lakeview 69 kV Capacitor Bank | Regional Reliability | ITP | 2020-02-01 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 1740000 | 2018 | 1783500 | 1740000 |  | DELAY - MITIGATION |  |  |  |  | New 14.4 MVAR (7.2 x 2) capacitor bank at the new Lakeview 69 kV Substation | 69
210499 | 51331 | 82125 | GHP | MO | Line - Nixa Downtown - Nixa Espy | Nixa Downtown - Nixa Espy Ckt1 | Regional Reliability | ITP | 2019-12-31 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 1402000 | 2018 | 1437050 | 3384026 |  | DELAY - MITIGATION |  |  |  |  | Reconductor 1.25 miles of 69 kV line from Nixa Downtown - Nixa Espy | 69
| 51332 | 82126 | OGE |  | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | GI | 2020-09-16 | [6 empty] | 1099958 |  | ON SCHEDULE < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51332 | 82127 | OGE |  | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | GI | 2020-09-16 | [6 empty] | 1025042 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
| 51333 | 82128 | OGE |  | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 1099958 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51333 | 82129 | OGE |  | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 9213042 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 51335 | 82132 | NPPD |  | Sub - Belden 115 kV Substation GEN-2015-076 Interconnection | Belden 115 kV Substation GEN-2015-076 Interconnection (TOIF) | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 300000 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Belden Substation: Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51335 | 82133 | NPPD |  | Sub - Belden 115 kV Substation GEN-2015-076 Interconnection | Belden 115 kV Substation GEN-2015-076 Interconnection (NU) | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 2900000 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Belden 115 kV Substation: Construct two (2) 2000 continuous ampacity breakers, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 51338 | 82134 | WAPA |  | Line - Gavins Point - Yankton Junction 115 kV | Gavins Point - Yankton Junction 115 kV | Generation Interconnection | GI | 2020-10-01 | [6 empty] | 1401596 |  | ON SCHEDULE < 4 |  |  |  |  | Western Area Power Administration (“WAPA”)/NorthWestern Energy Gavins Point – Yankton Junction 115 kV1: Rebuild approximately four (4) miles of 115 kV and replace associated terminal equipment.
| 51336 | 82135 | SPS |  | Sub - Lost Draw 115 kV Substation GEN-2015-014 Interconnection | Lost Draw 115 kV Substation GEN-2015-014 Interconnection (TOIF) | Generation Interconnection | GI | 2018-10-05 | [6 empty] | 371000 |  | COMPLETE |  |  |  |  | Transmission Owner’s Lost Draw 115kV Switching Station: Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, 115kV line arresters and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. Communications: It is Interconnection Customer’s responsibility to provide both the data circuit and dial up telephone circuits, per Section 1.13 of the Transmission Owner’s GEN-2015-014 Facility Study, 115KV Line Arresters and Appendix C, Item 3(d) of this Agreement.
| 51336 | 82136 | SPS |  | Sub - Lost Draw 115 kV Substation GEN-2015-014 Interconnection | Lost Draw 115 kV Substation GEN-2015-014 Interconnection (NU) | Generation Interconnection | GI | 2018-10-05 | [6 empty] | 5750184 |  | COMPLETE |  |  |  |  | Transmission Owner Interconnection Substation - Acquire five (5) acres of land for constructing a new substation, tapping, looping in, and re-terminating Cochran – Lehman 115kV transmission circuit, construct a new three (3) breaker ring 115kV bus, two (2) line terminals, three (3) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and associated equipment. Transmission Owner Lost Draw 115kV Switching Station: Construct two (2) line terminals, and tap, loop-in, and re-terminate Lehman – Cochran 115kV transmission circuit into the new Lost Draw Switching Station. Construct and install new line structures, foundations, conductors, insulators, switches, and all other associated work and materials. • Approximately 5 acres of land • Tap V-36 into and out of Lost Draw from Cochran to Lehman • Communication Equipment (DFR, RTU and other related items)
| 51337 | 82137 | AEP |  | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (TOIF) | Generation Interconnection | GI | 2019-12-31 | [6 empty] | 700000 |  | ON SCHEDULE < 4 |  |  |  |  | Install station A-frame dead-end structure and disconnect switch at the POI for the 138 kV transmission line from the Generating Facility; • Install Capacitive Voltage Transformer (“CVT”) and revenue metering including 138 kV Current Transformers (“CTs”) and Potential Transformers (“PTs”) at the POI on the transmission line from the Generating Facility; • Install a 138 kV span from the POI to the Point of Change of Ownership at Interconnection Customer’s dead-end structure outside the Tuskahoma fence. Transmission Owner will own the hardware required to suspend the span; • Transmission Owner will provide a serial port on the RTU at Tuskahoma switching station for Interconnection Customer to access real-time data from the meter; • Transmission Owner will provide Interconnection Customer with access to interval data (historical MV90) from the meter recorder using a telephone line, or some other networked means of contacting the meter, which will be provided by Interconnection Customer; • Install entrance duct at the POI to accommodate Optical Ground Wire (“OPGW”) from the Interconnection Customer’s step-up substation, adequate space in the POI control building to accommodate Interconnection Customer’s fiber and splice termination equipment, and associated equipment; and • Install RTU, SDR rack, PMU and DME panels to be located at the Generating Facility step-up substation.
| 51337 | 82138 | AEP |  | Sub - Tuskahoma 138 kV Substation GEN-2016-028 Interconnection | Tuskahoma 138 kV Substation GEN-2016-028 Interconnection (NU) | Generation Interconnection | GI | 2019-12-31 | [6 empty] | 8700000 |  | ON SCHEDULE < 4 |  |  |  |  | Construct the 138 kV Tuskahoma switching station including a three breaker ring bus constructed on a four breaker footprint. The Tuskahoma switching station will be located on property acceptable to Transmission Owner in the vicinity of structure 50/8 (GPS: 34.582, -95.317) of the existing Lone Oak – Broken Bow Southwestern Public Power Administration’s (“SWPA”) 138 kV line. The Tuskahoma switching station will have line terminals for transmission lines to Lone Oak, Broken Bow and the Generating Facility. The substation will include three (3) 3,000 Amp circuit breakers, disconnect switches, line relaying, monitoring equipment (DME, SDR and PMU's on both transmission lines), and all associated and miscellaneous equipment. Install turning structures and loop the existing Lone Oak – Broken Bow (SWPA) transmission line in and out of the new Tuskahoma switching station. • Replace relay panels at Transmission Owner’s Lone Oak substation. • Engineering support, project oversight and construction supervision of Transmission Owner's Interconnection Facilities and Stand Alone Network Upgrades constructed by Interconnection Customer.
210512 | 51339 | 82139 | OGE | OK | Line - Kildare - White Eagle 138 kV | Kildare - White Eagle 138 kV Ckt 1 Rebuild | Sponsored Upgrade | SP | 2019-10-29 | 2019-06-01 | 2019-04-03 | SUS-004 |  |  |  | 7200000 |  | COMPLETE | 514760 | KILDARE4 138 | 514761 | WHITE EAGLE 138 | Rebuild 11.2 mile 138 kV line from Kildare - White Eagle and upgrade terminal equipment. | 138 |  | 11.22
210513 | 51340 | 82140 | CUS | MO | XFR - James River Power Station 161/69 kV Ckt 2 | James River Power Station 161/69 kV Ckt 2 Transformer | Sponsored Upgrade | SP | 2018-06-01 |  | 2019-04-26 | SUS-005 |  |  |  | 2883983 |  | COMPLETE | 549961 | James River 161 | 549903 | Phelps Avenue-Main Avenue Gas Turbine | Add second 161/69 kV transformer at James River Power Station. Split 69 kV bus and connections at James River Power Station. | 161/69
210496 | 61346 | 92151 | SPS | KS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | ITP | 2021-05-28 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 9069324 | 2018 | 9296057 | 9069324 |  | DELAY - MITIGATION |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
210496 | 61346 | 92152 | SPS | KS | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | ITP | 2021-05-28 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 5226730 | 2018 | 5357398 | 5226730 |  | DELAY - MITIGATION |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
210507 | 61347 | 92153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | TS | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 22000000 |  | DELAY - MITIGATION |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
210507 | 61347 | 92154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | TS | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 21133839 |  | ON SCHEDULE < 4 |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
210507 | 61347 | 102153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | TS | 2021-10-29 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 6506478 |  | DELAY - MITIGATION |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | TS | 2021-10-29 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 5916168 |  | ON SCHEDULE < 4 |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
210507 | 71347 | 102156 | SPS | NM | Line - Eddy County - Kiowa 345 kV New Line | Eddy County - Kiowa 345 kV Ckt 1 New Line | Regional Reliability | TS | 2020-11-15 | 2024-06-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 63613061 |  | ON SCHEDULE < 4 | 527802 | Eddy County Interchange 345 kV | 527965 |  | Build new 34 mile 345 kV line from Eddy County to Kiowa. | 345 | 34
210507 | 61347 | 102157 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | TS | 2021-10-29 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 4265177 |  | DELAY - MITIGATION |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
210507 | 61347 | 102158 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | TS | 2020-11-06 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 |  |  |  | 11410517 |  | DELAY - MITIGATION |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
210534 | 71348 | 102159 | OPPD | NE | Multi - S1361 | S3761 345 kV Substation | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 4610067 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Build a new 345 kV Substation at S3761 | 345/161
210534 | 71348 | 102160 | OPPD | NE | Multi - S1361 | S3761 - S3455 345 kV New Line | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 17036209 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  | 645455 | Sub 3455 | Build a new 4.5 mile S3761 - S3455 345 kV Line | 345 | 5.6
210534 | 71348 | 102161 | OPPD | NE | Multi - S1361 | S1361 161 kV Substation and 345/161 kV Transformer | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 9707827 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Build a new S1361 161 kV Substation with new 345/161 kV transformer | 161
210534 | 71348 | 102162 | OPPD | NE | Multi - S1361 | S1260 161/69 kV Transformer (161 kV) | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 1105064 |  | NTC-C PROJECT ESTIMATE WINDOW | 646260 |  |  |  | 161 kV bus work associated with new S1260 161/69 kV Transformer | 161/69
210534 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 3647471 |  | NTC - COMMITMENT WINDOW | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
210534 | 71348 | 102165 | OPPD | NE | Multi - S1361 | S1259 - S1260 161 kV Rebuild | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 2107486 |  | NTC-C PROJECT ESTIMATE WINDOW | 646260 |  | 646259 | Sub 1259 | Rebuild 2.6 miles of S1259 - S1260 161 kV | 161 | 2.56
210534 | 71348 | 102166 | OPPD | NE | Multi - S1361 | S1255 161 kV Terminal Upgrades (new breakers) | Regional Reliability | TS | 2021-06-01 |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 654180 |  | NTC-C PROJECT ESTIMATE WINDOW | 646255 | Sub 1255 |  |  | Upgrade breakers at S1255 | 161
| 71349 | 102167 | WAPA |  | Sub - Granite Falls 115 kV Substation GEN-2016-036 Interconnection | Granite Falls 115 kV Substation GEN-2016-036 Interconnection (TOIF) | Generation Interconnection | GI | 2018-10-01 | [6 empty] | 1334000 |  | ON SCHEDULE < 4 | 652551 | GRANITE FALLS |  |  | Transmission Owner’s Granite Falls 115 kV Substation: Construct a 115-kV bay addition including, the installation of one 115-kV circuit breaker (JY28A/2862), two 115-kV disconnect switches (WY28A/2863, YY28B/2865), one 115-kV disconnect switch with ground blades (YY28A/2861, ZY28A/2860), one 115-kV CCVT (VY28A1), equipment supports, steel lattice beam and supports, 115-kV take-off/underground termination structure, control boards, communication equipment, and relays.
| 71350 | 102168 | OGE |  | SUB - Ranch Road 345kV Substation GEN-2015-034 Addition | Ranch Road 345kV Substation GEN-2015-034 Addition (TOIF) | Generation Interconnection | GI | 2020-05-29 | [6 empty] | 1099958 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Ranch Road 345kV Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 71350 | 102169 | OGE |  | SUB - Ranch Road 345kV Substation GEN-2015-034 Addition | Ranch Road 345kV Substation GEN-2015-034 Addition (NU) | Generation Interconnection | GI | 2020-05-29 | [6 empty] | 925042 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Ranch Road 345kV Substation: Construct one (1) 3000 continuous ampacity breakers, control panel replacement, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 71351 | 102170 | OGE |  | SUB - Johnston County 345kV Substation GEN-2015-036 Addition | Johnston County 345kV Substation GEN-2015-036 Addition (TOIF) | Generation Interconnection | GI | 2019-10-11 | [6 empty] | 892334 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Johnston County Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 71351 | 102171 | OGE |  | SUB - Johnston County 345kV Substation GEN-2015-036 Addition | Johnston County 345kV Substation GEN-2015-036 Addition (NU) | Generation Interconnection | GI | 2019-10-11 | [6 empty] | 1132666 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Johnston County Interconnection Substation: Construct one (1) 345 kV 3000 continuous ampacity breaker, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210505 | 71352 | 102172 | WFEC | OK | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | TS | 2019-12-01 | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 |  |  |  | 717209 |  | ON SCHEDULE < 4 |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
| 31018 | 112173 | OGE |  | Sub - Minco 345kV GEN-2014-056 & GEN-2015-057 Addition | Minco 345kV Substation GEN-2015-057 Addition (NU) | Generation Interconnection | GI | 2018-10-15 | [6 empty] | 10000 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Minco 345kV Substation: Update relay settings, electrical modeling, and records.
210525 | 81357 | 112180 | OPPD | NE | GEN-2016-115 Interconnection Costs | GEN-2016-115 Interconnection Costs (NU) (OPPD) | Generation Interconnection | GI | 2020-06-26 | 2020-06-26 | 2019-11-01 | DISIS-2016-002 |  |  |  | 7553 |  | NTC - COMMITMENT WINDOW |  |  |  |  | Interconnection upgrades and costs estimates needed to interconnect the following Interconnection Customer facility, GEN-2016-115 (300.0 MW/Wind), into the Point of Interconnection (POI) at Holt 345kV.
210511 | 81423 | 112253 | OGE | OK | GEN-2016-020 Interconnection Costs | GEN-2016-020 Interconnection Costs | Generation Interconnection | GI | 2019-11-01 |  | 2019-04-03 | DISIS-2016-001 |  |  |  | 10000 |  | ON SCHEDULE < 4 |  |  |  |  | GEN-2016-020 Interconnection Costs
| 81467 | 112297 | SEPC |  | Mingo 345 kV Substation | Mingo 345kV Substation GEN-2015-065 (TOIF) | Generation Interconnection | GI | 2019-05-30 | [6 empty] | 1314623 |  | COMPLETE |  |  |  |  | Mingo 345 kV Substation
| 81467 | 112298 | SEPC |  | Mingo 345 kV Substation | Mingo 345kV Substation GEN-2015-065 (NU) | Generation Interconnection | GI | 2019-05-30 | [6 empty] | 9596925 |  | COMPLETE |  |  |  |  | Mingo 345kV Substation (NU)
| 81467 | 112299 | SEPC |  | Mingo 345 kV Substation | Mingo Substation Relay GEN-2015-065 (NU) | Generation Interconnection | GI | [7 empty] | 15000 |  | ON SCHEDULE > 4 |  |  |  |  | Mingo Substation relay setting modification (NU
| 81467 | 112300 | SEPC |  | Mingo 345 kV Substation | Mingo 115kV Substation GEN-2015-064 (TOIF) | Generation Interconnection | GI | 2020-03-01 | [6 empty] | 911033 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Mingo 115kV Substation: Construct one (1) 115kV line terminal, line switches, dead end structure, line relaying,communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81467 | 112301 | SEPC |  | Mingo 345 kV Substation | Mingo 115kV Substation GEN-2015-064 (NU) | Generation Interconnection | GI | 2020-03-01 | [6 empty] | 4517777 |  | ON SCHEDULE < 4 |  |  |  |  | Transmission Owner’s Mingo 345kV Substation: Construct four (4) 115 kV 3000 continuous ampacity breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210534 | 71348 | 112357 | OPPD | NE | Multi - S1361 | S1260 161/69 kV Transformer (69 kV) | Regional Reliability | TS |  |  | 2019-11-13 | DPA-2018-February-841 |  |  |  | 1799221 |  | NTC - COMMITMENT WINDOW | 646260 |  |  |  | Add new S1260 161/69 kV Transformer and associated 69 kV bus work | 161/69
210540 | 81498 | 112358 | OGE | OK | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 271289 |  | NTC - COMMITMENT WINDOW | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
210540 | 81499 | 112359 | OGE | OK | Sub - Santa Fe 138 kV | Santa Fe 138 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 406935 |  | NTC - COMMITMENT WINDOW | 514926 | SANTA FE 138 |  |  | Replace 3 breakers at Santa Fe 138 kV with 40 kA breakers | 138
210544 | 81500 | 112360 | AEP |  | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 16288000 |  | NTC - COMMITMENT WINDOW | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 21 breakers at Riverside Station 138 kV with 80 kA breakers | 138
210544 | 81501 | 112361 | AEP |  | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 4421345 |  | NTC - COMMITMENT WINDOW | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138
210541 | 81504 | 112364 | SPS |  | Sub - Denver City Interchange 115 kV North | Denver City Interchange North 115 kV Breaker | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 552668 |  | NTC - COMMITMENT WINDOW | 527130 | Denver City Interchange N. 115 kV |  |  | Replace 1 breaker at Denver City Interchange North 115 kV with 40 kA breaker | 115
210541 | 81586 | 112365 | SPS |  | Sub - Denver City Interchange South 115 kV | Denver City Interchange South 115 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 1105336 |  | NTC - COMMITMENT WINDOW | 527136 | Denver City Interchange S. 115 kV |  |  | Replace 2 breakers at Denver City Interchange South 115 kV with 40 kA breakers | 115
210538 | 81505 | 112366 | NPPD | NE | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 2600000 |  | NTC - COMMITMENT WINDOW | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115
210538 | 81506 | 112367 | NPPD | NE | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 550000 |  | NTC - COMMITMENT WINDOW | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115
210538 | 81507 | 112368 | NPPD | NE | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 510000 |  | NTC - COMMITMENT WINDOW | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
210539 | 81508 | 112369 | KCPL | MO | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 254000 |  | NTC - COMMITMENT WINDOW | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161
210539 | 81509 | 112370 | KCPL | MO | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 440000 |  | NTC - COMMITMENT WINDOW | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161
210539 | 81510 | 112371 | KCPL | MO | Sub - Midtown 161 kV | Midtown 161 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 440000 |  | NTC - COMMITMENT WINDOW | 542996 | MIDTOWN 161 KV |  |  | Replace 2 breakers at Midtown 161 kV with 40 kA breakers | 161
210539 | 81511 | 112372 | KCPL | MO | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 880000 |  | NTC - COMMITMENT WINDOW | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 228500 |  | NTC - COMMITMENT WINDOW | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
210545 | 81514 | 112378 | WFEC | OK | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 52400 |  | NTC - COMMITMENT WINDOW | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
210545 | 81515 | 112379 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 822500 |  | NTC - COMMITMENT WINDOW | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
210545 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 128300 |  | NTC - COMMITMENT WINDOW | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
210542 | 81516 | 112381 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 6178207 |  | NTC - COMMITMENT WINDOW | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | : Rebuild 6.03 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 6
210542 | 81516 | 112382 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - Smittyville 115kV Ckt 1 | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 8839308 |  | NTC - COMMITMENT WINDOW | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Rebuild 7.99 miles of 115 kV line from Baileyville to Smittyville and upgrade any necessary terminal equipment at Baileyville and/or Smittyville to increase the summer emergency rating to 239 MVA | 115 | 8
210542 | 81516 | 112383 | WR | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Marshall County - Smittyville 115kV Ckt 1 | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 2618506 |  | NTC - COMMITMENT WINDOW | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Rebuild 2.17 miles of 115 kV line from Marshall County to Smittyville and upgrade any necessary terminal equipment at Marshall County and/or Smittyville to increase the summer emergency rating to 239 MVA | 115 | 2.2
210544 | 81520 | 112389 | AEP |  | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 6724237 |  | NTC - COMMITMENT WINDOW | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138 | 2
210544 | 81523 | 112393 | AEP |  | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 1307802 |  | NTC - COMMITMENT WINDOW | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138 |  | 1.5
210545 | 81525 | 112395 | WFEC | OK | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 400000 |  | NTC - COMMITMENT WINDOW | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69
210542 | 81526 | 112396 | WR | KS | Sub - Getty - Skelly 69kV | Getty East - Skelly 69kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 114821 |  | NTC - COMMITMENT WINDOW | 533592 | GETTY 69 KV | 533602 | SKELLY 69 KV | Upgrade any necessary terminal equipment at Getty East and/or Skelly to increase the summer emergency line rating to 108 MVA | 69
210540 | 81532 | 112402 | OGE | OK | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | ITP |  | 2022-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 16602 |  | NTC - COMMITMENT WINDOW | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 570000 |  | NTC - COMMITMENT WINDOW | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | ITP |  | 2021-04-01 | 2019-11-18 | 2019 ITP |  |  |  | 2800000 |  | NTC - COMMITMENT WINDOW | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
210541 | 81542 | 112425 | SPS |  | Sub - Amoco - Sundown 115 kV | Amoco - Sundown 115kV Terminal Upgrades | Economic | ITP |  | 2023-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 358281 |  | NTC - COMMITMENT WINDOW | 526434 | Sundown Interchange 115 kV | 526445 | Amoco Tap 115 kV | Upgrade any necessary terminal equipment at Sundown and/or Amoco Tap to increase the summer emergency rating to 175 MVA | 115
210542 | 81545 | 112428 | WR | KS | Sub - Lawrence Energy Center - Midland 115 kV | Lawrence Energy Center - Midland 115 kV Terminal Upgrades | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 30939 |  | NTC - COMMITMENT WINDOW | 533248 | LAWRENCE ENERGY CENTER UNIT 3 115 KV |  |  | Upgrade any necessary terminal equipment at Lawrence Energy Center and/or Midland to increase the summer emergency rating to 159 MVA | 115
210541 | 81548 | 112433 | SPS |  | Line - Hansford - Spearman 115kV | Hansford - Spearman 115 kV Rebuild | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 828359 |  | NTC - COMMITMENT WINDOW | 523186 | Spearman Interchange 115 kV | 523195 | Hansford County Switch Station 115 kV (POI: JD Wind #4 80MW) | Rebuild 1.2 miles of 115 kV line from Spearman to Hansford and replace structures at Hansford and/or Spearman as needed to increase the summer emergency rating to 233 MVA | 115
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 1000000 |  | NTC - COMMITMENT WINDOW |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138
210540 | 81556 | 112449 | OGE | OK | Multi - Cimarron - Northwest - Mathewson 345kV | Cimarron - Northwest 345kV Ckt 1 Terminal Upgrades | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 166504 |  | NTC - COMMITMENT WINDOW | 514880 | NORTHWEST 345 | 514901 | CIMARRON 345 | Upgrade any necessary terminal equipment at Northwest and/or Cimarron to increase the summer emergency rating to 1426 MVA | 345
210540 | 81556 | 112450 | OGE | OK | Multi - Cimarron - Northwest - Mathewson 345kV | Northwest - Mathewson 345 kV Terminal Upgrades | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 369869 |  | NTC - COMMITMENT WINDOW | 514880 | NORTHWEST 345 | 515497 | MATHEWSON 345 | Upgrade any necessary terminal equipment at Northwest and/or Mathewson to increase the summer emergency rating to 1792 MVA | 345
210543 | 81557 | 112451 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 462000 |  | NTC - COMMITMENT WINDOW | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115
210543 | 81557 | 112452 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 1633500 |  | NTC - COMMITMENT WINDOW | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115
210543 | 81557 | 112453 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | ITP |  | 2025-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 1556500 |  | NTC - COMMITMENT WINDOW | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115
210544 | 81561 | 112460 | AEP |  | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | ITP |  | 2026-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 733520 |  | NTC - COMMITMENT WINDOW | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138
210544 | 81571 | 112488 | AEP |  | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | ITP |  | 2021-06-01 | 2019-11-18 | 2019 ITP |  |  |  | 9155167 |  | NTC - COMMITMENT WINDOW | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 115/69
210544 | 81561 | 112502 | AEP |  | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | ITP |  | 2026-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 5383105 |  | NTC - COMMITMENT WINDOW |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06
210515 | 81581 | 112510 | SPS | NM | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | TS | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 |  |  |  | 3165684 | 7731949 | ON SCHEDULE > 4 | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line | 115 |  | 10.5
210515 | 81581 | 122510 | SPS | TX | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw Capacitor Bank | Regional Reliability | TS | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 |  |  |  | 3749224 |  | ON SCHEDULE > 4 | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
210531 | 81614 | 122570 | BEPC |  | Multi - Neset - Newtown 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | TS | 2019-06-01 |  | 2019-10-17 | DPA-2018-August-918 |  |  |  | 33023153 |  | NTC-C PROJECT ESTIMATE WINDOW | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 28
210532 | 81614 | 122571 | MWE |  | Multi - Neset - Newtown 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | TS | 2019-06-01 |  | 2019-10-17 | DPA-2018-August-918 |  |  |  | 17332093 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20
210531 | 81614 | 122572 | BEPC |  | Multi - Neset - Newtown 230 kV | Northshore 230/115 kV Transformer | Regional Reliability | TS | 2019-06-01 |  | 2019-10-17 | DPA-2018-August-918 |  |  |  | 5920939 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Build new 230/115 kV Transformer at Northshore substation | 230/115
210531 | 81614 | 122575 | BEPC |  | Multi - Neset - Newtown 230 kV | Northshore 230 kV Substation | Regional Reliability | TS | 2019-06-01 |  | 2019-10-17 | DPA-2018-August-918 |  |  |  | 8371948 |  | NTC-C PROJECT ESTIMATE WINDOW |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch | 230/115
210522 | 81616 | 122576 | NWE |  | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen City - Aberdeen Industrial Park 115 kV Ckt 1 New Line | Sponsored Upgrade | SP | 2019-12-31 |  | 2019-09-06 | SUS-006 |  |  |  | 3200009 |  | ON SCHEDULE < 4 |  |  |  |  | Build new 3.29 mile, 115 kV line from Aberdeen City - Aberdeen Industrial Park | 115 | 3.29
210545 | 81617 | 122577 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | ITP |  | 2021-01-01 | 2019-11-18 | 2019 ITP |  |  |  | 2850000 |  | NTC - COMMITMENT WINDOW | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont and upgrade any necessary equipment to increase the summer emergency rating to 478 MVA | 138 |  | 5.09
210527 | 81626 | 122593 | EREC |  | Multi - Wentworth 69 kV | Wentworth 69 kV Substation | Regional Reliability | TS | 2019-06-01 |  | 2019-10-17 | DPA-2018-January-821 |  |  |  | 2073095 |  | NTC - COMMITMENT WINDOW |  |  |  |  | Build new Wentworth 69 kV Substation to replace existing motor-operated switch | 69
210527 | 81626 | 122594 | EREC |  | Multi - Wentworth 69 kV | Wentworth 69 kV Capacitor Bank | Regional Reliability | TS | 2019-07-01 |  | 2019-10-17 | DPA-2018-January-821 |  |  |  | 600675 |  | NTC - COMMITMENT WINDOW |  |  |  |  | New 7.2 MVAR capacitor bank at the new Wentworth 69 kV Substation | 69
210545 | 81627 | 122597 | WFEC | OK | SUB - Marietta - Rocky Point 69 kV | Marietta 69 kV | Regional Reliability | ITP |  | 2021-12-01 | 2019-11-18 | 2019 ITP |  |  |  | 100000 |  | NTC - COMMITMENT WINDOW |  |  |  |  | Install any necessary protection equipment at Marietta to change the operational status from normally open to normally closed | 69
210522 | 81616 | 122599 | NWE |  | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | SP | 2021-12-31 |  | 2019-09-06 | SUS-006 |  |  |  | 552668 |  | ON SCHEDULE < 4 |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115
| 81547 | 112509 | WR | KS | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek - Blackberry 345kV Terminal Equipment | Economic | ITP |  | 2026-01-01 |  | 2019 ITP |  |  |  | 10056365 |  | IDENTIFIED |  |  |  |  | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | 345
| 81547 | 122598 | TBD | KS | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | ITP |  | 2026-01-01 |  | 2019 ITP |  |  |  | 142601178 |  | IDENTIFIED |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
| 81561 | 112458 | TBD | KS | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | ITP |  | 2026-01-01 |  | 2019 ITP |  |  |  | 77606498 |  | IDENTIFIED |  |  |  |  | Add a single 345kV line terminal to existing Sooner 345kV substation. Dead end structure, 3000A line switch, 3000A breaker, line relaying, metering CT's, CCVT's. | 345