## 2022 STEP Appendix 1
2022 STEP Appendix 1
COMPLETE |  |  |  | Complete and in-service
CLOSED OUT |  |  |  | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project
DELAY - MITIGATION WINDOW |  |  |  | Behind schedule, interim mitigation pending or project may change but time permits the implementation of project
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
RE-EVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
RFP ISSUED |  |  |  | Responses for competeitive upgrades are being submitted and/or reviewed
SUSPENDED |  |  |  | NTC/GIA suspended
NTC ID | PID | UID | Project Owner | State(s) | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200397 | 242 | 10308 | WFEC | OK | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-03-31 | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3757406.6808 | 4339358 | 4171494.22 | Delay - Mitigation | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
200397 | 844 | 11113 | WFEC | OK | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | 2020-12-31 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5215515.9052 | 4725000 | 643783.96 | Delay - Mitigation | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10
20080 | 30201 | 50208 | NPPD | NE | Device - Clarks 115 kV | CLARKS 115KV | Regional Reliability | 2018-06-01 | 2012-11-01 | 2010-02-08 | 2009 STEP | 700000 | 2014 | 772669.023 | 700000 |  | Closed Out | 640436 | Clarks |  |  | Add a 18 Mvar capacitor bank at Clarks substation 115 kV bus. | 115
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 214576055.8119 | 204236579 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 14385872.9756 | 13692681 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2025-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 244694447.7113 | 232903698 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
210618 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2025-12-31 | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 591425 | 577000 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
| 30401 | 50492 | TBD | NE | Cass Co. - S.W. Omaha (aka S3454) 345 kV | Cass Co. - S.W. Omaha (aka S3454) 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 33126800 |  | Identified | 645740 | Sub 3740 | 645454 | Sub 3454 | Build new 28 miles 345 kV Cass Co. - S.W. Omaha (aka S3454) and associated terminal equipment | 345
200200 | 30491 | 50600 | WFEC | OK | Device - Hazelton 69 kV | Hazelton 69 kV Capacitor | Regional Reliability | 2017-03-01 | 2013-01-01 | 2013-03-01 | DPA-2012-MAR-143-147 | 237000 | 2013 | 261603.6549 | 735000 |  | Re-evaluation | 520937 | HAZELTON |  |  | Install two 4.8 Mvar capacitors at Hazelton 69 kV for total of 9.6 Mvar. | 69
200234 | 30503 | 50628 | WFEC | OK | Device - Hazelton 69 kV #2 | Hazelton Capacitor 69 kV #2 | Regional Reliability | 2017-03-01 | 2017-06-01 | 2013-10-28 | DPA-2012-MAR-151-154-161-JUL-218-SEP-243 | 185004 | 2013 | 204209.7999 | 0 |  | Re-evaluation | 520937 | HAZELTON |  |  | Install new 69 kV 4.8-Mvar capacitor at Hazelton substation. | 69
200245 | 30563 | 50702 | WFEC | OK | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  | Re-evaluation | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138
| 30599 | 50769 | AEP | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | South Fayetteville 345/161 kV Transformer Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 12600000 |  | Identified |  |  |  |  | Install new 345/161 kV Transformer at South Fayetteville. | 345/161
| 30599 | 50770 | TBD | AR | Multi - South Fayetteville 345/161 kV Transformer & Chamber Springs - South Fayetteville 345 kV line | Chamber Springs - South Fayetteville 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 21295800 |  | Identified |  |  |  |  | Build new 345 kV line from Chamber Springs to South Fayetteville and associated terminal equipment. | 345 | 18
| 30600 | 50771 | EMW | MO | XFR - Maryville 345/161 kV | Maryville 345/161 kV Transformer Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 12600000 |  | Identified | 541197 | Maryville 345 kV | 300097 | Maryville | Install new 345/161 transformer at Maryville. | 345/161
| 30601 | 50772 | EM | KS | XFR - Nashua 345/161 kV | Nashua 345/161 kV Transformer Upgrade Ckt11 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 12600000 |  | Identified |  |  |  |  | Increase rating of Nashua transformer to 650/715 MVA. | 345/161
| 30602 | 50773 | TBD | NE | Line - Keystone - Red Willow 345 kV | Keystone - Red Willow 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 130141000 |  | Identified | 640252 | Keystone | 640325 | Red Willow | Build new 110 mile 345 kV line from Keystone to Red Willow and associated terminal equipment. | 345 | 110
| 30603 | 50774 | TBD | TX | Line - Tolk - Tuco 345 kV | Tolk - Tuco 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 75718400 |  | Identified | 525549 | Tolk Station 345 kV | 525832 | TUCO Interchange 345 kV | Build new 64 mile 345 kV line from Tolk to Tuco and associated terminal equipment. | 345 | 64
| 30604 | 50775 | SEPC | KS | XFR - 2nd Holcomb 345/115 kV | Holcomb 345/115 kV Transformer Ckt2 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 12600000 |  | Identified | 531449 | HOLCOMB | 531448 | HOLCOMB | Install 2nd 345/115 kV transformer at Holcomb. | 345/115
| 30605 | 50776 | TBD | KS | Line - Neosho - Wolf Creek 345 kV | Neosho - Wolf Creek 345 kV Ckt1 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 117126900 |  | Identified | 532797 | WOLF CREEK 345 KV | 532793 | NEOSHO 345 KV | Build a new 86.4 mile 345kV line from Neosho to Wolf Creek rated at 1792 MVA | 345 | 86.4
| 30606 | 50777 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | Clinton - Truman 161 kV Ckt1 Reconductor | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 15701325 |  | Identified | 300071 | Clinton | 505502 | Truman | Rebuild 29 mile 161 kV line from Clinton to Truman. | 161 |  | 29
| 30606 | 50778 | TBD | MO | Multi - Clinton - Truman - North Warsaw 161 kV Rebuild | North Warsaw - Truman 161 kV Ckt1 Reconductor | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 1082850 |  | Identified | 505502 | Truman | 541314 | North Warsaw 161 | Rebuild 2 miles of 161 kV line from North Warsaw to Truman. | 161 |  | 2
| 30607 | 50782 | OGE | OK | Sub - Muskogee/Pecan Creek 345 kV | Muskogee/Pecan Creek 345 kV Terminal Upgrades | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 34605675 |  | Identified | 515224 | MUSKOGEE 345 | 515235 | PECAN CREEK 345 | Upgrade terminal equipment at Muskogee and Pecan Creek substations to increase Muskogee - Pecan Creek 345 kV Ckts 1 & 2 ratings to 1195/1195 MVA.
| 30608 | 50779 | EKC | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn 345/115 kV Transformer Ckt2 | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 12600000 |  | Identified |  |  |  |  | Install new 345/115 kV transformer at Auburn. | 345/115
| 30608 | 50780 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Swissvale 345 kV Ckt1 Voltage Conversion | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 20112700 |  | Identified |  |  |  |  | Convert 17 mile Auburn - Swissvale 230 kV line to a 345 kV line. | 345 |  |  | 17
| 30608 | 50781 | TBD | KS | Multi - Jeffrey EC - Auburn - Swissvale 345 kV Conversion & Auburn 345/115 kV Transformer | Auburn - Jeffrey EC 345 kV Ckt1 Voltage Conversion | ITP20 |  | 2033-01-01 |  | 2013 ITP20 |  |  |  | 35493000 |  | Identified |  |  |  |  | Convert the 30 mile Auburn - Jeffrey EC 230 kV to 345 kV. | 345 |  |  | 30
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2025-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11338457.3874 | 9797157 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2025-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1134089.4193 | 913714 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
200326 | 30866 | 51170 | SPS | TX | Sub - Amarillo South 230 kV Terminal Upgrades | Amarillo South 230 kV Terminal Upgrades | Regional Reliability |  | 2020-04-01 | 2015-02-18 | 2015 ITPNT | 31198 | 2015 | 37084.618 | 0 |  | Re-evaluation | 524415 | Amarillo South Interchange 230 kV | 525213 | Swisher County Interchange 230 kV | Replace wave trap at Amarillo South to increase the rating of the 230 kV line from Amarillo South to Swisher County. | 230
| 30937 | 51602 | SPS | TX | SUB - TUCO 230kV Switching Station GEN-2012-020 Addition | TUCO 230kV Switching Station GEN-2012-020 Addition (TOIF) | Generation Interconnection | 2018-12-14 |  |  | GI STUDIES |  |  |  | 260000 |  | On Schedule < 4 |  |  |  |  | TUCO 230kV Switching Station: Communications; Revenue Metering; 230kV Line arrestors.
| 30959 | 51338 | EKC | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection | 2021-07-08 |  |  | GI STUDIES |  |  |  | 2098946 |  | Complete |  |  |  |  | Construct new terminal extension of the bus north to add another rung to the bus. Equipment includes two (2) 345kV breakers, four (4) 345kV switches, bus work, and all associated yard and conduit work.
| 30959 | 51360 | EKC | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | 2021-07-28 |  |  | GI STUDIES |  |  |  | 1674997 |  | In Service |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
200365 | 30989 | 51409 | SPS | NM | Sub - Potash Junction 230 kV Terminal Upgrade | Potash Junction 230 kV Terminal Upgrade | Regional Reliability | 2018-06-01 | 2018-06-01 | 2016-01-12 | SPP-2014-AG1-AFS-6 | 63251 | 2016 | 66453.0819 | 0 |  | Re-evaluation | 527963 | Potash Junction Interchange 230 kV |  |  | Replace wavetrap at Potash Junction 230 kV substation. | 230
200397 | 31002 | 51445 | WFEC | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | 2021-05-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6788449.26 | 7710000 |  | Delay - Mitigation | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability |  | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2627865.2897 | 2266000 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2022-04-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 637831.381 | 600000 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2022-04-01 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3479080.26 | 3600000 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
200419 | 31042 | 51531 | WFEC | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | 2024-12-01 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1583971.494 | 5700000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20716215 |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
200420 | 31063 | 51567 | SPS | NM | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | 2021-06-01 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | Complete | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2023-05-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4638773.68 | 4000000 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
200444 | 31079 | 51623 | SPS | TX | Sub - Tuco - Stanton 115 kV Terminal Upgrades | Tuco - Stanton 115 kV Terminal Upgrades | Economic | 2018-12-31 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 283963 | 2017 | 291062.075 | 0 |  | Re-evaluation | 525828 | TUCO Interchange 115 kV | 526076 | Stanton Sub 115 kV | Upgrade any necessary terminal equipment at Stanton and/or Tuco to increase the rating of the 115 kV line between the two substations. | 115
200433 | 31144 | 51764 | WFEC | OK | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | 2021-12-31 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 110381.289 | 410000 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
200444 | 41189 | 61836 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Martin - Pantex North 115 kV Terminal Upgrades | Economic | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 332501.8 | 0 |  | Re-evaluation | 523928 | Martin Sub 115 kV | 523938 | Pantex North Sub 115 kV | Upgrade any necessary terminal equipment at Martin and/or Pantex North to increase the rating of the 115 kV line between the two substations. | 115
200444 | 41189 | 61837 | SPS | TX | Sub - Martin - Pantex N 115 kV Terminal Upgrades | Pantex South - Highland Tap 115 kV Terminal Upgrades | Economic | 2018-03-15 | 2017-01-01 | 2017-02-22 | 2017 ITP10 | 324392 | 2017 | 332501.8 | 0 |  | Re-evaluation | 523945 | Pantex South Sub 115 kV | 523931 | Highland Park Tap 115 kV | Upgrade any necessary terminal equipment at Pantex South and/or Highland Tap to increase the rating of the 115 kV line between the two substations. | 115
200455 | 41198 | 61852 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 101104.975 | 98639 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
200455 | 41198 | 61853 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | 2018-12-31 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 111140.75 | 108430 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
210536 | 41199 | 71960 | SPS | TX | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | 2021-10-21 | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1338161 |  | Delay - Mitigation | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
| 51239 | 71933 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2020-10-01 |  |  | GI STUDIES |  |  |  | 4700000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
| 51239 | 71934 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2020-11-01 |  |  | GI STUDIES |  |  |  | 5900000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
200479 | 51249 | 71954 | KPP | KS | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | 2020-12-31 | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | Complete |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
200466 | 51249 | 71955 | EKC | KS | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | 2021-04-12 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 | 5156585 | Complete |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 12692888 | 2018 | 14010573.3857 | 20297796 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 5717372.1624 | 5468352 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
200477 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 11271233 | 2018 | 12441332.2716 | 15279402 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. | 115 | 2.6
200477 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 1273506 | 2018 | 1405712.3383 | 1605462 |  | Delay - Mitigation |  |  |  |  | Build new 1 mile, 115 kV line from Sheldon to Monolith. | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2023-06-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 3703266 | 2018 | 4087712.7459 | 5656017 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 51261 | 71982 | NPPD | NE | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Belvidere – Fairbury 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  | GI STUDIES |  |  |  | 1700000 |  | Re-evaluation |  |  | 640169 | Fairbury | NPPD Belvidere – Fairbury 115kV circuit #1: uprate Belvidere – Fairbury to at least 107 MVA | 115/115
| 51261 | 71983 | NPPD | NE | Multi - Belvidere 115kV Substation GEN-2015-087 Addition | Beatrice – Harbine 115kV circuit #1 | Generation Interconnection | 2019-11-01 |  |  | GI STUDIES |  |  |  | 900000 |  | Re-evaluation | 640076 | Beatrice | 640208 | Harbine | NPPD Beatrice – Harbine 115kV circuit #1: uprate Beatrice – Harbine to at least 102 MVA | 115/115
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2023-01-31 | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 99343.1601 | 90000 |  | On Schedule < 4 | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
200482 | 51280 | 72011 | WFEC | OK | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | 2023-09-01 | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 500000 |  | Delay - Mitigation | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
200482 | 51281 | 72012 | WFEC | OK | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | 2023-08-01 | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1103812.89 | 1000000 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
210483 | 51282 | 72013 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2000000 | 2000000 |  | Re-evaluation |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
210483 | 51282 | 72014 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2019-07-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | Delay - Mitigation | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
210483 | 51282 | 72015 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-05-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8561280.429 | 7950000 |  | Delay - Mitigation | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
210483 | 51282 | 72016 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-08-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 6750000 | 2018 | 7269011.685 | 7520000 |  | Delay - Mitigation | 521016 | OKEENE | 521090 | WATONGA SW | Convert 13.5 mile 69 kV line from Okeene - Watonga SW to 138 kV. | 138 |  | 13.5 | 13.5
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-08-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9272028.276 | 8400000 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-09-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1379766.1125 | 1250000 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-12-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5022348.6495 | 4550000 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2022-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6236542.8285 | 5650000 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-06-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 3500000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-05-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 11750000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
210483 | 51282 | 72025 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-05-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 11755607.2785 | 1162000 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
210483 | 51282 | 72026 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2020-12-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1103156.25 | 5000000 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-01-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5519064.45 | 5300000 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
210483 | 51282 | 72029 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2018-06-15 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4500000 | 2018 | 4500000 | 6141513 | 5762250.69 | Complete |  |  |  |  | Construct new 9.0 mile 138 kV line from Kingfisher SW - Park Community. | 138 | 9
210483 | 51282 | 72030 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | 2022-06-01 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4415251.56 | 4000000 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2022-11-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4691204.7825 | 4250000 |  | Delay - Mitigation Window | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 51283 | 72032 | EKC | KS | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  |  | 591193 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51283 | 72033 | EKC | KS | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  |  | 13383989 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
| 51283 | 72034 | OGE | OK | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  |  | 20000 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
210496 | 51316 | 72095 | SPS | TX | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | 2022-03-11 | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 232952 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-03-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11038128.9 | 10000000 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 7616308.941 | 6900000 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
210489 | 51327 | 82113 | WFEC | OK | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-08-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8184368.712 | 7600000 |  | Delay - Mitigation |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
210489 | 51327 | 82114 | WFEC | OK | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-04-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 323067.186 | 300000 |  | Delay - Mitigation | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-02-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 6954021.207 | 6300000 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 51332 | 82126 | OGE | OK | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | 2022-10-14 |  |  | GI STUDIES |  |  |  | 1099958 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51332 | 82127 | OGE | OK | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | 2022-10-14 |  |  | GI STUDIES |  |  |  | 1025042 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
| 51333 | 82128 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2022-10-15 |  |  | GI STUDIES |  |  |  | 1099958 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51333 | 82129 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2022-10-15 |  |  | GI STUDIES |  |  |  | 9213042 |  | On Schedule < 4 |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210496 | 61346 | 92151 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | 2022-04-16 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 13967362.375 | 20859497 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
210496 | 61346 | 92152 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | 2022-04-16 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 6694970.975 | 81052 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
210507 | 61347 | 92153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36646140 |  | In Service |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
210507 | 61347 | 92154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32405135 |  | In Service |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
210507 | 61347 | 102153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5718715 |  | In Service |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 5962651 |  | In Service |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102157 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6341420 |  | In Service |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
210507 | 61347 | 102158 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | 2020-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15137218 |  | In Service |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
210548 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2023-05-31 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 3927927.3066 | 3647471 |  | Delay - Mitigation | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
210505 | 71352 | 102172 | WFEC | OK | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | 2020-12-01 | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 735139.225 | 717209 |  | Delay - Mitigation |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
210511 | 81423 | 112253 | WFEC | OK | GEN-2016-020 Interconnection Costs | GEN-2016-020 Interconnection Costs (WFEC) | Generation Interconnection | 2019-11-01 |  | 2019-04-03 | DISIS-2016-001 | 10000 | 2019 | 10000 | 10000 |  | Delay - Mitigation |  |  |  |  | GEN-2016-020 Interconnection Costs
210611 | 81474 | 112307 | AEP | OK | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2023-05-15 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 9689511.55 | 12400000 |  | On Schedule < 4 |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation.
210565 | 81481 | 122622 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection | 2025-12-31 |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 146903.6406 | 136893 |  | In Service |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
| 81481 | 122623 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES | 10000 | 2020 | 10506.25 | 10000 |  | In Service |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
| 81483 | 112331 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 1175646 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating |  | 0.04
| 81483 | 112332 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 9959548.73 |  | On Schedule < 4 |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. |  | 1.32
| 81488 | 112339 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-05-31 |  |  | GI STUDIES |  |  |  | 250000 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81488 | 112340 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2023-05-31 |  |  | GI STUDIES |  |  |  | 8805000 |  | On Schedule < 4 |  |  |  |  | Construct one (1) new 230 kV switchyard on the Oahe - Fort Thompson North 230 kV transmission that will consist of a three (3) breaker ring bus, three (3) 230 kV power circuit breakers, nine (9) 230 kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, three (3) line take-off structures, conductor, overhead optical ground wire, communication equipment, and a control building.
| 81489 | 112333 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 1388819 |  | On Schedule < 4 |  |  |  |  | : Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81489 | 112334 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 17798882 |  | On Schedule < 4 |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. |  | 0.32
210564 | 81489 | 122600 | OGE | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection | 2021-12-31 | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | Delay - Mitigation |  |  |  |  | Relay settings upgrades
210630 | 81490 | 122601 | OGE | OK | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection | 2023-12-31 | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  |  | 10000 |  | NTC - Commitment Window |  |  |  |  | Change relay settings to accommodate the construction of the GEN-2016-095 wind farm.
| 81491 | 112337 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 918474 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.04
| 81491 | 112338 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 7400346 |  | On Schedule < 4 |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81495 | 112353 | SPS | TX | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES | [5 empty] | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV.
210577 | 81497 | 112500 | EREC | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (EREC) | Regional Reliability | 2021-11-01 | 2022-12-01 | 2020-11-17 | 2020 ITP | 4270000 | 2021 | 4270000 | 4319598 |  | Complete | 660000 | ABERDEEN JCT |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA | 115 | 13.4
210577 | 81497 | 122511 | EREC | SD | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 115/69 kV Transformer | Regional Reliability | 2021-11-01 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1102500 | 2021 | 1102500 | 1068027 |  | Complete |  |  |  |  | Install new 115/69 kV transformer at Richmond to achieve a summer emergency rating of 63 MVA
210577 | 81497 | 122512 | EREC | SD | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 69 kV Capacitor Bank | Regional Reliability | 2021-11-01 | 2022-12-01 | 2020-11-17 | 2020 ITP | 230000 | 2021 | 230000 | 219100 |  | Complete |  |  |  |  | Install a new 8 MVAR capacitor bank at Richmond 69 kV | 69
210584 | 81497 | 132893 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 | 989393 | Complete |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA
210577 | 81497 | 132894 | EREC | SD | Multi - Aberdeen Junction - Richmond 115 kV | Richmond 69 kV Substation | Regional Reliability | 2021-11-01 | 2022-12-01 | 2020-11-17 | 2020 ITP | 5738500 | 2021 | 5738500 | 5658500 |  | Complete |  |  |  |  | Expand the existing 69 kV substation to accommodate a new 115/69 kV transformer | 115/69
210584 | 81497 | 143181 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability |  | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3359437.5 | 3277500 |  | On Schedule < 4 |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
210540 | 81498 | 112358 | OGE | OK | Sub - Westmoore 138 kV | Westmoore 138 kV Breakers | Regional Reliability | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 271289 | 2020 | 278071.225 | 271289 |  | Complete | 514887 | WESTMOORE 138 |  |  | Replace 2 breakers at Westmoore 138 kV with 40 kA breakers | 138
210623 | 81500 | 112360 | AEP | OK | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 43180687.5 | 46270466 |  | On Schedule < 4 | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56
210544 | 81501 | 112361 | AEP | OK | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | 2023-12-15 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4645175.5906 | 4194065 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138
210541 | 81503 | 112363 | SPS | TX | Sub - Hale Cty Interchange 115 kV | Hale County Interchange 115 kV Breakers | Regional Reliability | 2021-05-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1658004 | 2019 | 1741940.4525 | 257408 |  | In Service | 525454 | Hale Co Interchange 115 kV |  |  | Replace 3 breakers at Hale County Interchange 115 kV with 40 kA breakers | 115
210538 | 81505 | 112366 | NPPD | NE | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | 2020-02-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 | 2555908 | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115
210538 | 81506 | 112367 | NPPD | NE | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | 2021-01-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 | 434289 | Complete | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115
210538 | 81507 | 112368 | NPPD | NE | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | 2022-07-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 679553 |  | Delay - Mitigation | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
210539 | 81508 | 112369 | EM | KS | Sub - Craig 161 kV | Craig 161 kV Breaker | Regional Reliability | 2021-06-30 | 2021-06-01 | 2019-11-18 | 2019 ITP | 311400 | 2019 | 327164.625 | 259864 |  | In Service | 542978 | CRAIG 161 KV |  |  | Replace 1 breaker at Craig 161 kV with 63 kA breakers | 161
210539 | 81509 | 112370 | EM | MO | Sub - Leeds 161 kV | Leeds 161 kV Breakers | Regional Reliability | 2020-09-24 | 2021-06-01 | 2019-11-18 | 2019 ITP | 468500 | 2019 | 480212.5 | 400871 | 400871 | Complete | 542997 | LEEDS 161 KV |  |  | Replace 2 breakers at Leeds 161 kV with 40 kA breakers | 161
210539 | 81511 | 112372 | EM | MO | Sub - Southtown 161 kV | Southtown 161 kV Breakers | Regional Reliability | 2021-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 898600 | 2019 | 944091.625 | 1348442 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 4 breakers at Southtown 161 kV with 40 kA breakers | 161
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2027-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 870294.6744 | 838500 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
210545 | 81514 | 112378 | WFEC | OK | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 53710 | 52400 |  | Delay - Mitigation | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
210545 | 81515 | 112379 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | 2022-05-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 2160000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
210545 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 134795.1875 | 204000 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
210542 | 81516 | 112381 | EKC | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Baileyville - South Seneca 115kV Ckt 1 | Regional Reliability | 2022-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3067168.2 | 2020 | 3222443.5901 | 3393918 |  | Delay - Mitigation | 533322 | BAILEYVILLE N.M. STATION 115 KV (NEMAHA MARSHALL R | 533337 | SOUTH SENECA 115 KV | Rebuild 4 miles of 115 kV line from Baileyville to South Seneca and upgrade any necessary terminal equipment at Baileyville and/or South Seneca to increase the summer emergency rating to 239 MVA | 115 | 4
210605 | 81516 | 112383 | EKC | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability | 2022-06-01 | 2021-04-01 | 2021-03-02 | 2019 ITP | 2528867.81 | 2020 | 2656891.7429 | 10675598 |  | Delay - Mitigation | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Tear down 7.99 miles of 115 kV line from Baileyville to Smittyville, 2.17 miles of 115 kV line from Marshall County to Smittyville, and the Smittyville substation, rebuild 10.16 miles of 115 kV line from Baileyville to Marshall County and upgrade any necessary terminal equipment at Marshall County and/or Baileyville to increase the summer emergency rating to 239 MVA | 115 | 2.2
210544 | 81520 | 112389 | AEP | OK | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-05-27 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 |  | Delay - Mitigation | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2
210544 | 81523 | 112393 | AEP | OK | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 2201381 |  | In Service | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5
210545 | 81525 | 112395 | WFEC | OK | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2021-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 410000 | 400000 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
210642 | 81529 | 112399 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 238289 |  | NTC - Commitment Window | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230/230
210642 | 81529 | 112401 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability | 2022-06-01 | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 397668.28 |  | NTC - Commitment Window | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230/230
210540 | 81532 | 112402 | OGE | OK | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | On Schedule < 4 | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69/69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 639725.5625 | 608900 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115/115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3782250 | 2991100 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115/115
210592 | 81547 | 112509 | EKC | KS | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-12-31 | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 11908479.725 | 12217322 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wolf Creek to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
210626 | 81547 | 122598 | NEET | KS/MO | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-01-01 | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 87298161.45 | 85168938 |  | On Schedule < 4 |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2021-01-01 | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1025000 | 1000000 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138/138
210586 | 81553 | 112443 | WFEC | OK | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-12-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 10524075.5803 | 10267390.81 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138/138
210543 | 81557 | 112451 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 485388.75 | 726694 |  | On Schedule < 4 | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115/115
210543 | 81557 | 112452 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1716195.9375 | 437574 |  | On Schedule < 4 | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115/115
210543 | 81557 | 112453 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1635297.8125 | 467574 |  | On Schedule < 4 | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115/115
210570 | 81559 | 112456 | EDE | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | 2023-01-01 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 69054450 | 69054450 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
210569 | 81559 | 112457 | EKC | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EKC) | Transmission Service | 2023-06-01 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 4008402 | 2020 | 4211327.3513 | 5608820 |  | On Schedule < 4 | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 2.44 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 | 2.7
210593 | 81561 | 112458 | TSOK | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic |  | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 102028138.4569 | 97111851 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345/345
210544 | 81561 | 112460 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 770654.45 | 733520 |  | On Schedule < 4 | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138/138
210544 | 81561 | 112502 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2026-01-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3409095.4055 | 5383105 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06
210540 | 81561 | 112504 | OGE | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic |  | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4349183.0094 | 4139615 |  | On Schedule > 4 |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
210544 | 81571 | 112488 | AEP | OK | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 |  | Delay - Mitigation | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115
210515 | 81581 | 112510 | SPS | NM | Multi-Hobbs Interchange-Millen 115kV | Hobbs Interchange to Millen Rebuild 115 kV Ckt1 | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3165684 | 2019 | 3409095.4055 | 0 |  | On Schedule < 4 | 527891 | Hobbs Interchange 115 kV | 528435 | Millen Sub 115 kV | Rebuild 10.5 miles of Hobbs Interchange to Millen 115kV Line |  | 3.5
210515 | 81581 | 122510 | SPS | TX | Multi-Hobbs Interchange-Millen 115kV | Johnson Draw 115 kV Capacitor Bank | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-06-07 | DPA-2018-Mar-854 | 3749224 | 2019 | 4037504.1579 | 0 |  | On Schedule < 4 | 527362 | Johnson Draw 115 kV |  |  | New 28.8 MVAR capacitor bank addition at Johnson Draw 115kV | 115
210609 | 81591 | 122537 | OGE | OK | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2024-04-20 | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4095900 | 3996000 |  | Delay - Mitigation |  |  |  |  | Install + 275 MVAR Capacitor Bank(s) at Border 345 kV.
| 81594 | 122540 | SPS | NM | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  |  | 7365886 |  | On Schedule < 4 |  |  |  |  | Install + 100 MVAR Capacitor Bank(s) at Crossroads 345 kV. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81599 | 122547 | SPS | TX | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2022-12-15 |  |  | GI STUDIES |  |  |  | 210533 |  | On Schedule < 4 |  |  |  |  | Replace two 345 kV structures, wave traps (3X), and jumpers to achieve minimum emergency rating of 956 MVA. Network Upgrade Shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81600 | 122546 | SPS | TX | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-01 |  |  | GI STUDIES |  |  |  | 184651 |  | On Schedule < 4 |  |  |  |  | Replace approximately four structures on the Crossroads - Tolk 345 kV line to achieve a minimum rating of 956 MVA. Network Upgrade shared among four requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81606 | 122554 | SPS | NM | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 483969 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
| 81607 | 122556 | SPS | NM | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 413496 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81608 | 122558 | SPS | NM | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 413496 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81609 | 122560 | SPS | NM | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 413496 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81613 | 122568 | SPS | TX | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  |  | 14055360 |  | On Schedule < 4 |  |  |  |  | Build new 345/230 kV Transformer Ckt 2 at Tolk to achieve a minimum emergency rating of 921 MVA on the Crossroads - Tolk 345 kV Ckt 1 line. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  | 0.5
210560 | 81614 | 122570 | BEPC | ND | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 33155575 | 2020 | 34834075.9844 | 32751932 |  | Delay - Mitigation | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
210559 | 81614 | 122571 | MWE | ND | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | 2021-09-05 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2020 | 19716372.125 | 19235485 |  | Delay - Mitigation |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
210560 | 81614 | 122572 | BEPC | ND | Multi - Neset - New Town 230 kV | North Shore 230/115 kV Transformer | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3176320 | 2020 | 3337121.2 | 3848527 |  | Delay - Mitigation |  |  |  |  | Build new 230/115 kV Transformer at North Shore substation | 230/115
210560 | 81614 | 122575 | BEPC | ND | Multi - Neset - New Town 230 kV | North Shore 230 kV Substation | Regional Reliability | 2022-12-31 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 20938350 | 2020 | 21998353.9688 | 15681907 |  | Delay - Mitigation |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch
210522 | 81616 | 122599 | NWE | SD | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | 2019-06-01 | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 | 555000 | Complete |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115
210586 | 81617 | 122577 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138kV Ckt 1 Rebuild | Economic | 2023-01-01 | 2023-01-01 | 2020-11-17 | 2020 ITP | 2850000 | 2020 | 2994281.25 | 5750000 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Rebuild 5.09-mile 138 kV line from Anadarko to Gracemont as a double circuit and install/upgrade any necessary terminal equipment to increase the summer emergency rating to 353 MVA for each circuit | 138
210586 | 81617 | 122753 | WFEC | OK | Line - Anadarko - Gracemont 138kV | Anadarko - Gracemont 138 kV Ckt 2 Rebuild | Economic | 2023-01-01 | 2023-01-01 | 2020-11-17 | 2020 ITP | 1750000 | 2021 | 1793750 | 3330000 |  | On Schedule > 4 | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Rebuild 5.09-mile 138kV line from Anadarko to Gracemont as double circuit and add/upgrade any necessary equipment to increase the achieve a summer emergency rating of 353 MVA for each circuit
210589 | 81617 | 122755 | OGE | OK | Line - Anadarko - Gracemont 138kV | Gracemont 138 kV Ckt 2 Terminal Equipment | Economic | 2023-01-01 | 2023-01-01 | 2020-11-17 | 2020 ITP | 6075003 | 2021 | 6226878.075 | 1124593 |  | On Schedule < 4 | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Install terminal equipment at Gracemont 138 kV to support a second 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 353 MVA
210562 | 81628 | 122602 | WAPA | ND | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2021-12-31 |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1547750 | 1510000 |  | Delay - Mitigation |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
| 81636 | 122635 | OGE | OK | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-14 |  |  | GI STUDIES |  |  |  | 1099871 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
210606 | 81636 | 122637 | EKC | KS | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  | 2025-03-15 | 2021-03-04 | GI STUDIES | 16624 | 2021 | 17039.6 | 16624.73 |  | On Schedule < 4 |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
| 81639 | 122640 | SPS | NM | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-17 |  |  | GI STUDIES |  |  |  | 4578401 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum system emergency rating of 430 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81640 | 122641 | SPS | NM | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  |  | 697513 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum emergency rating of 456 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81641 | 122642 | SPS | NM | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES | [5 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81642 | 122643 | SPS | NM | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES | [5 empty] | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81644 | 122646 | SPS | NM | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-15 |  |  | GI STUDIES |  |  |  | 968567 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 478 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81645 | 122645 | SPS | NM | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-15 |  |  | GI STUDIES |  |  |  | 4852215 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 90/90 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  |  | 13
| 81646 | 122647 | SPS | TX | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  |  | 5943138 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Tuco 230 kV Substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81647 | 122648 | SPS | TX | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2021-10-28 |  |  | GI STUDIES |  |  |  | 3318135 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Deaf Smith 115 kV substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
210551 | 81648 | 122650 | EKC | KS | Sub - Neosho 345 kV | Caney River - Neosho 345 kV Terminal Upgrades | Sponsored Upgrade | 2020-06-25 | 2020-10-01 | 2019-12-31 | SUS-013 | 419116 | 2020 | 419116 | 286283.4 | 286283.4 | Complete | 532793 | NEOSHO 345 KV | 532780 | Caney River | Upgrade terminal equipment, disconnect switches, and line switch to increase the summer normal and emergency ratings to at least 1159 MVA.
210557 | 81652 | 122657 | CBPC | IA | Sub-Flint Hills 69 kV Switching Station | Sub - Donald Feldman 69kV Switching Station | Regional Reliability | 2020-06-01 | 2020-06-01 | 2020-04-08 | DPA-2019-March-1011 | 1100000 | 2020 | 1100000 | 1227000 |  | Complete |  |  |  |  | Construct a new switching station at Flint Hills connecting the MEC Clarksville line and Corn Belt's Parkersburg and Plainfield line
210552 | 81654 | 122661 | NPPD | NE | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability | 2020-06-01 | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 | 3704140 | Complete | 640330 | Riverdale | 640331 | Riverdale | Install a new 230/115 kV 187 MVA transformer located at Riverdale substation | 230/115
| 81655 | 122662 | OGE | OK | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 15000 |  | On Schedule < 4 |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
210563 | 81656 | 122664 | NPPD | NE | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | 2022-12-01 | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 6000000 |  | On Schedule < 4 | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each.
| 81657 | 122665 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 1388819 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81657 | 122666 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 10361130 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81658 | 122669 | BEPC | ND | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2025-06-30 |  |  | GI STUDIES |  |  |  | 2776827 |  | In Service |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
| 81660 | 122673 | EKC | KS | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 20000 |  | On Schedule < 4 |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
210612 | 81660 | 122674 | OGE | OK | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15375 | 15000 |  | On Schedule < 4 |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
| 81661 | 122676 | EKC | KS | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 810255 |  | On Schedule < 4 |  |  |  |  | Construct one (1) new 345 kV circuit breaker and two (2) new 345 kV disconnect switches.
| 81661 | 143150 | EKC | KS | Benton 345kV GEN-2016-162 and 163 Interconnection Costs | Benton 345kV GEN-2016-162 and 163 Interconnection (TOIF) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 1198282 |  | On Schedule < 4 |  |  |  |  | Construct one (1) new 345 kV dead-end, one (1) new 345 kV disconnect switch, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel.
| 81662 | 122677 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES | [5 empty] | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
| 81662 | 122678 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES | [5 empty] | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
| 81665 | 122684 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  |  | 1636796 |  | In Service |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81665 | 122687 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  |  | 2155837 |  | In Service |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81666 | 122688 | WAPA | SD | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2023-06-30 |  |  | GI STUDIES |  |  |  | 644488 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
| 81670 | 122791 | OGE | OK | Viola 345/138 kV Transformer CKT 2 | GEN-2016-119 Tap - Arcadia 345kV (DISIS-2016-002-3) | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES |  |  |  | 68725000 |  | On Schedule < 4 |  |  |  |  | Build new terminal at new substation on Sooner to Spring Creek line being built for Gen-2016-119. Expand Arcadia Substation and re-route four transmission lines to allow for room for new transmission line to be brought in. Build approximately 47 miles of new 345kV line from new substation to Arcadia.
| 81670 | 122792 | EKC | KS | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection |  |  |  | GI STUDIES |  |  |  | 9204586 |  | On Schedule < 4 |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
210558 | 81673 | 122713 | AEP | OK | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-01 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 3160967 |  | On Schedule < 4 | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49
210578 | 81675 | 122717 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 383760 | 374400 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 0/0
210578 | 81675 | 122718 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | Delay - Mitigation | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
210578 | 81675 | 122801 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | Delay - Mitigation | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA
210578 | 81675 | 122802 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | Delay - Mitigation | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 345/161
210586 | 81679 | 122722 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-12-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 932750 | 910000 |  | Delay - Mitigation | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
210586 | 81679 | 122865 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 207562.5 | 202500 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
210586 | 81679 | 122866 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | 2022-04-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 415125 | 405000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
210574 | 81682 | 122725 | SPS | TX | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3035101.875 | 2961075 |  | On Schedule < 4 | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
210574 | 81684 | 122727 | SPS | TX | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7534565.9 | 7350796 |  | On Schedule < 4 | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
210575 | 81687 | 122730 | AEP | LA | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2024-06-01 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 24213141.425 | 23622577 |  | On Schedule < 4 | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2
210650 | 81691 | 122733 | BEPC | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock 230 kV Terminal Upgrades | Economic | 2023-10-01 | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 614000 |  | NTC - Commitment Window |  |  |  |  | Increase line clearances and/or upgrade any necessary terminal equipment at Whitlock 230 kV
210648 | 81691 | 122734 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 893000 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line.
210639 | 81691 | 122735 | EREC | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 614000 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Sully Buttes for Oahe - Sully Buttes - Whitlock 230 kV line
210648 | 81691 | 143613 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 2068000 |  | NTC - Commitment Window |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
210648 | 81691 | 143614 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 5789000 |  | NTC - Commitment Window |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
210645 | 81694 | 122739 | NPPD | NE | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 4600000 |  | NTC - Commitment Window | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
210627 | 81717 | 122796 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2023-04-30 | 2022-01-01 | 2021-11-05 | 2020 ITP | [5 empty] | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA |  | 0.2
210628 | 81717 | 122823 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2023-04-01 | 2022-01-01 | 2021-11-05 | 2020 ITP | 11500000 | 2021 | 11787500 | 11500000 |  | Delay - Mitigation |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
210627 | 81717 | 143182 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2023-04-30 | 2022-01-01 | 2021-11-05 | 2020 ITP | 1259660 | 2021 | 1291151.5 | 5264319 |  | On Schedule < 4 |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 0.84 | 1
210582 | 81719 | 122803 | SEPC | KS | Device - Russell 115 kV | Russell 115 kV Capacitor Bank | Regional Reliability | 2024-01-01 | 2022-06-01 | 2020-11-23 | 2020 ITP | 5306633 | 2021 | 5439298.825 | 5306633 |  | NTC - Commitment Window | 539701 | Russell 115 KV |  |  | Add new 24 MVAR capacitor bank at Russell 115 kV
210583 | 81720 | 122804 | EM | KS | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-12-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 909665.975 | 887481 |  | Delay - Mitigation |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
210583 | 81722 | 122806 | EM | KS | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 300000 |  | On Schedule < 4 | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker
210583 | 81723 | 122807 | EM | KS | Sub - Shawnee Mission 161 kV | Shawnee Mission 161 kV Breaker | Regional Reliability | 2023-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 335416 | 2020 | 352396.435 | 355416 |  | Delay - Mitigation | 543031 | SHAWNEE MISSION 161 KV |  |  | Replace 1 breaker at the Shawnee Mission 161 kV station with a 40 kA breaker
210583 | 81724 | 122808 | EM | KS | Sub - Southtown 161 kV #2 | Southtown 161 kV Breaker | Regional Reliability | 2021-12-22 | 2022-06-01 | 2020-11-17 | 2020 ITP | 244265 | 2021 | 244265 | 389812 |  | In Service | 542993 | SOUTHTOWN 161 KV |  |  | Replace 1 breaker at the Southtown 161 kV station with a 40 kA breaker
210580 | 81728 | 122812 | EKC | KS | Line - Circleville - Goff 115 kV | Circleville - Goff 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-07-02 | 2025-06-01 | 2020-11-17 | 2020 ITP | 13028143 | 2021 | 13028143 | 14232227 | 14232227 | Complete | 533152 | CIRCLEVILLE 115 KV | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | Rebuild 14.56 miles of 115 kV line from Circleville to Goff and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  |  | 14.5
210580 | 81730 | 122814 | EKC | KS | Line - Kelly - Goff 115 kV | Goff - Kelly 115 kV Ckt 1 Rebuild | Regional Reliability | 2021-06-18 | 2025-06-01 | 2020-11-17 | 2020 ITP | 5602343 | 2021 | 5602343 | 5483173 | 5483173 | Complete | 533331 | KING HILL N.M. COOP 115 KV (NEMAHA MARSHALL R.E.C. | 533217 | KELLY 115 KV | Rebuild 10.0 miles of 115 kV line from Goff to Kelly and upgrade any necessary terminal equipment to achieve a summer emergency rating 239 MVA |  |  | 10
210589 | 81733 | 122818 | OGE | OK | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4388178.75 | 4281150 |  | On Schedule < 4 | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 4.71
210589 | 81733 | 122819 | OGE | OK | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1108690.225 | 1081649 |  | On Schedule < 4 | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA |  |  | 1.19
210616 | 81741 | 122848 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1889822.225 | 1843729 |  | On Schedule > 4 | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345/138
210616 | 81741 | 122849 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 31475649.775 | 30707951 |  | On Schedule > 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345/138
210616 | 81741 | 122850 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5128925.75 | 5003830 |  | On Schedule > 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122851 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5007790.225 | 4885649 |  | On Schedule > 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122858 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2604730 | 2541200 |  | On Schedule > 4 | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
210656 | 81741 | 122863 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 65000 |  | NTC - Commitment Window | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
| 81741 | 133085 | TBD | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 57512100 |  | RFP Issued |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating. | 345 | 34.8
| 81741 | 133106 | TBD | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 23400139 |  | RFP Issued |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA | 345 | 13.2
210616 | 81741 | 143176 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6646646.325 | 6484533 |  | On Schedule > 4 |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
210586 | 81751 | 122864 | WFEC | OK | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 871250 | 850000 |  | On Schedule > 4 | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
210574 | 81755 | 122869 | SPS | TX | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 571184 |  | Delay - Mitigation | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA. |  | 33
210574 | 81756 | 122870 | SPS | TX | Sub - Newhart - Potter 230 kV | Newhart - Potter 230 kV Terminal Upgrades | Regional Reliability | 2022-04-01 | 2022-04-01 | 2020-11-17 | 2020 ITP | 735013 | 2021 | 753388.325 | 0 |  | On Schedule < 4 | 525461 | Newhart Interchange 230 kV | 523959 | Potter County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Newhart and/or Potter 230 kV to achieve a summer emergency rating of 540 MVA. |  | 67
210574 | 81757 | 122871 | SPS | TX | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 11900197.725 | 11609949 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
210574 | 81758 | 122872 | SPS | TX | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | On Schedule < 4 | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
210574 | 81760 | 122876 | SPS | TX | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7130500.65 | 6956586 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
210574 | 81763 | 122883 | SPS | TX | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 835432 |  | On Schedule < 4 | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
210581 | 81768 | 122745 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3474482.475 | 3910285 |  | Delay - Mitigation |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
210581 | 81768 | 122746 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 177367.025 | 173041 |  | Delay - Mitigation |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
210645 | 81769 | 122741 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 6910000 |  | NTC - Commitment Window | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill. |  | 9
210645 | 81769 | 143599 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 1010000 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
210645 | 81769 | 143600 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 950000 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
210576 | 91875 | 143156 | AEP | OK | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | 2022-10-28 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1184404 |  | On Schedule < 4 |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV
210579 | 91876 | 143157 | WAPA | ND | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-04-01 | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2196797.425 | 2143217 |  | Delay - Mitigation |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
210585 | 91878 | 143159 | MRES | MN | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | 2023-09-17 | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 |  |  | 4358300 |  | Delay - Mitigation |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
210591 | 91881 | 143162 | CPEC | ND | Device - Agate 115 kV | Agate 115 kV Reactor | Regional Reliability | 2022-07-01 | 2022-04-01 | 2020-11-23 | 2020 ITP | 1310400 | 2021 | 1343160 | 1310400 |  | Delay - Mitigation |  |  |  |  | Install 2x6 MVAR reactors at Agate to control voltage on the 115 kV transmission system
210574 | 91884 | 143167 | SPS | TX | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1717624.275 | 1675731 |  | Delay - Mitigation |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210600 | 91885 | 143177 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S1260 - S1362 161 kV Ckt 1 Rebuild | Regional Reliability | 2022-08-01 | 2023-04-01 | 2021-02-16 | DPA-2018-October-949 | 858928 | 2021 | 880401.2 | 858928 |  | On Schedule < 4 | 646260 |  |  |  | Rebuild 0.9 miles of 161 kV line from S1260 to S1362 line to achieve 243 MVA summer emergency rating. | 161
210600 | 91885 | 143178 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-08-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 102500 | 100000 |  | On Schedule < 4 | 645456 | Sub 3456 | 645458 | Sub 3458 (Neb Cty) | The upgrade disconnect switch and associated jumpers on S3456 to S3458 345 kV line to achieve at least a 981 MVA summer emergency rating. | 345
210600 | 91885 | 143179 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability | 2024-04-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 615000 | 600000 |  | On Schedule < 4 | 645455 | Sub 3455 | 645740 | Sub 3740 | Replace structures to increase clearance on S3455 to S3740 345 kV CKT1 (approximately 6-7 structures) to achieve a 1112 MVA summer emergency rating. | 345
210574 | 91888 | 143168 | SPS | TX | Line - Cargill - Deaf Smith #24 115 kV | Cargill - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 5378526 | 2021 | 5512989.15 | 5378526 |  | Delay - Mitigation |  |  |  |  | Rebuild 7.74 miles of 115 kV line from Cargill to Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210574 | 91889 | 143169 | SPS | TX | Line - Parmer - Deaf Smith #24 115 kV | Parmer - Deaf Smith #24 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 999423 | 2021 | 1024408.575 | 999423 |  | Delay - Mitigation |  |  |  |  | Rebuild 1.16 miles of 115 kV line from Parmer - Deaf Smith #24 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210574 | 91890 | 143170 | SPS | TX | Line - Parmer - Deaf Smith #20 115 kV | Parmer - Deaf Smith #20 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 5293163 | 2021 | 5425492.075 | 5293163 |  | Delay - Mitigation |  |  |  |  | Rebuild 7.6 miles of 115 kV line from Parmer - Deaf Smith #20 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210590 | 91891 | 143183 | EMW | KS | Sub - Greenwood 161 kV Terminal Upgrades | Greenwood 161 kV Terminal Upgrades | Transmission Service | 2022-05-31 | 2021-12-31 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 600168 | 2021 | 615172.2 | 600168 |  | Delay - Mitigation | 541218 | Greenwood Energy Center 161 KV | 541233 | Lees Summit East 161 KV | Replace 2 breakers, relays at Greenwood 161 kV substation | 161
210590 | 91892 | 143184 | EMW | KS | Sub - Pleasant Hill 161 kV and Lake Winnebago 161 kV Terminal Upgrades | Pleasant Hill 161kV and Lake Winnebago 161 kV Terminal Upgrades | Transmission Service | 2021-04-23 | 2021-06-01 | 2020-11-24 | SPP-2020-AG1-AFS-3 | 337005 | 2021 | 337005 | 483586 | 483586 | Complete | 541225 | Pleasant Hill 161 KV | 541243 | Lake Winnebago 161 KV | Replace 2 breakers at Pleasant Hill 161 kV substation and replace 1 switch at Lake Winnebago 161 kV substation in order to increase the limit on the Pleasant Hill - Lake Winnebago 161 kV line. | 161
210617 | 91939 | 143253 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2025-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 |  |  |  | 7865000 |  | Delay - Mitigation Window | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69
210617 | 91939 | 143254 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 |  |  |  | 5340500 |  | Delay - Mitigation Window | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69
210617 | 91939 | 143255 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 |  |  |  | 450000 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV
210617 | 91939 | 143256 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 |  |  |  | 500000 |  | Delay - Mitigation Window |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV
210655 | 92112 | 143587 | EMW | KS | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 51502 |  | NTC - Commitment Window |  |  |  |  | Upgrade the switch at Platte City 161 kV for the Platte City - Weston 161 kV line.
210652 | 92113 | 143588 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 72919000 |  | NTC-C Project Estimate Window |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up
210652 | 92113 | 143589 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 342000 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
210652 | 92113 | 143590 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 342000 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
210633 | 92114 | 143591 | AEP | OK | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 9020000 |  | NTC - Commitment Window |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69
210646 | 92123 | 143660 | OPPD | NE | Line - S3454 - S3740 345 kV | S3454 - S3740 345 kV New Line | Regional Reliability |  | 2024-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 38380095 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 29 mile 345 kV line from S3454 to S3740 Ckt 1. | 345 | 23.3
210646 | 92123 | 143661 | OPPD | NE | Line - S3454 - S3740 345 kV | S3454 345 kV Terminal Upgrades | Regional Reliability |  | 2024-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 1624037 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at S3454 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210646 | 92123 | 143662 | OPPD | NE | Line - S3454 - S3740 345 kV | S3740 345 kV Terminal Upgrades | Regional Reliability |  | 2024-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 1680146 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at S3740 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210637 | 92140 | 143663 | EKC | KS | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 267179 |  | NTC - Commitment Window |  |  |  |  | Replace breaker 115-483 at the Jarbalo Junction substation | 115
210647 | 92141 | 143666 | EM | KS | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 319002 |  | NTC - Commitment Window |  |  |  |  | Upgrade the R5-33 breaker at the Craig 161 kV substation | 161
210640 | 92142 | 143667 | MRES | MN | Sub - Moorehead 230 kV Substation Reconfiguration | Moorehead 230 kV Substation Reconfiguration | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 7935000 |  | NTC - Commitment Window |  |  |  |  | Reconfigure the Moorehead 230 kV substation with a ring bus | 230
210654 | 92143 | 143668 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th - Stateline 161 kV Rebuild | Regional Reliability | 2022-01-31 | 2026-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 4948819 |  | NTC - Commitment Window |  |  |  |  | Rebuild approximately 5.5 miles of the existing 161 kV line from Joplin West 7th to Stateline. | 161 |  | 5.5
210654 | 92143 | 143669 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Joplin West 7th 161 kV Terminal Upgrades | Regional Reliability | 2022-01-31 | 2026-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 468900 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Joplin West 7th 161 kV substation. | 161
210654 | 92143 | 143670 | EDE | MO | Multi - Joplin West 7th - Stateline 161 kV | Stateline 161 kV Terminal Upgrades | Regional Reliability | 2022-01-31 | 2026-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 468900 |  | NTC - Commitment Window |  |  |  |  | : Upgrade any necessary terminal equipment at Stateline 161 kV substation. | 161
210647 | 92144 | 143664 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 255075 |  | NTC - Commitment Window |  |  |  |  | Upgrade the R3-7 breaker at the Shawnee Mission 161 kV substation | 161
210647 | 92144 | 143665 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  | 2023-06-01 | 2022-03-10 | 2021 ITP |  |  |  | 255075 |  | NTC - Commitment Window |  |  |  |  | Upgrade the R7-12 breaker at the Shawnee Mission 161 kV substation | 161
210652 | 92168 | 143714 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 72000000 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande.
210653 | 92168 | 144226 | MWE | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 3834545 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 5 mile 115 kV line from Finstad to Vanhook
210652 | 92168 | 144227 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Terminal Equipment #2 | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 374583 |  | NTC-C Project Estimate Window |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
210652 | 92168 | 144230 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 22000000 |  | NTC-C Project Estimate Window |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
210652 | 92168 | 144231 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 1500000 |  | NTC-C Project Estimate Window |  |  |  |  | Install a switched shunt at Finstad.
210652 | 92168 | 144233 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 5000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
210652 | 92168 | 144235 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt1 Transformer (115 kV) | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 5000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install a 345/115 kV Ckt 1 transformer at Finstad and upgrade any necessary 115 kV terminal equipment. | 345/115
210652 | 92168 | 144236 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 184000000 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad.
210652 | 92168 | 144237 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Terminal Equipment | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 2500000 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at Leland Olds substation to support a new 345 kV line from Finstad.
210652 | 92168 | 144238 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 2500000 |  | NTC-C Project Estimate Window |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
210653 | 92168 | 144239 | MWE | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 2334441 |  | NTC-C Project Estimate Window |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad
210653 | 92178 | 144148 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 22000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install a 150 MVAR statcom at the 115 kV E Newtown bus
210653 | 92178 | 144202 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2024-07-01 | 2031-12-01 | 2022-03-11 | 2021 ITP |  |  |  | 1500000 |  | NTC-C Project Estimate Window |  |  |  |  | Expand existing E New Town substation to accommodate the statcom interconnection
210619 | 92180 | 143705 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2022-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 |  |  |  | 11250834 |  | NTC - Commitment Window | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA
210619 | 92180 | 144283 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 |  |  |  | 374583 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
210619 | 92180 | 144284 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability |  | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 |  |  |  | 374583 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub.
210656 | 92184 | 143786 | OGE | OK | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 168228 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at the Cleo Corner 69 kV substation | 69/69
210656 | 92190 | 143806 | OGE | OK | Multi - Rocky Point - Marietta 2 - Marietta 4 138 kV Rebuild | Marietta 2 - Marietta 4 138 kV Ckt 1 New Line (OGE) | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 1575000 |  | NTC - Commitment Window |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta 2 to Marietta 4. | 138/138
210656 | 92190 | 143815 | OGE | OK | Multi - Rocky Point - Marietta 2 - Marietta 4 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 5000000 |  | NTC - Commitment Window |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69/69
210656 | 92190 | 143816 | OGE | OK | Multi - Rocky Point - Marietta 2 - Marietta 4 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 8806000 |  | NTC - Commitment Window |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69/69
210656 | 92190 | 143817 | OGE | OK | Multi - Rocky Point - Marietta 2 - Marietta 4 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 250000 |  | NTC - Commitment Window |  |  |  |  | Replace the existing relays at Rocky Point | 69/69
210657 | 92190 | 144173 | WFEC | OK | Multi - Rocky Point - Marietta 2 - Marietta 4 138 kV Rebuild | Marietta 4 138 kV Ckt 1 Terminal Equipment | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 736000 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Marietta 2 to support a new 138 kV line from Marietta 4 with a 286/286/286/286 (SN/SE/WN/WE) MVA rating
210653 | 92211 | 144163 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 500000 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub with a 239/239/239/239 (SN/SE/WN/WE) MVA rating
210652 | 92211 | 144171 | BEPC | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | Judson - Tande 345 kV Tap Line | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 22500000 |  | NTC-C Project Estimate Window |  |  |  |  | Tap the 345 kV line from Judson to Tande approximately 18 miles from Judson and build the 345 kV portion of the Eastfork substation.
210653 | 92211 | 144177 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 3800000 |  | NTC-C Project Estimate Window |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag to achieve a 239/239/239/239 (SN/SE/WN/WE) MVA rating
210653 | 92211 | 144178 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 500000 |  | NTC-C Project Estimate Window |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub with a 239/239/239/239 (SN/SE/WN/WE) MVA rating
210652 | 92211 | 144198 | BEPC | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | XFR 345/115 kV Eastfork (115 kV) | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 5000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install a 345/115 kV transformer at Eastfork and upgrade any necessary terminal equipment.
210653 | 92211 | 144199 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - Eastfork - Tande 345 kV | Eastfork 345/115 kV (345 kV) | Regional Reliability |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 2334441 |  | NTC-C Project Estimate Window |  |  |  |  | Install a 345 kV terminal equipment at Eastfork to accommodate a 345/115 kV transformer with a 332/415/332/415 (SN/SE/WN/WE) MVA rating
210641 | 92213 | 143980 | NIPCO | IA | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability | 2023-10-31 | 2023-06-01 | 2022-03-11 | 2021 ITP |  |  |  | 168228 |  | NTC - Commitment Window |  |  |  |  | Upgrade the terminal equipment at Hinton (K412) substation.
210645 | 92220 | 144143 | NPPD | NE | Line - Ogallala - Ogallala 115 kV Ckt 1 | Ogallala - Ogallala (NPPD) 115 kV Ckt 1 | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 280000 |  | NTC - Commitment Window |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
210644 | 92220 | 144220 | TSGT | NE | Line - Ogallala - Ogallala 115 kV Ckt 1 | Ogallala - Ogallala 115 kV Ckt 1 (TSGT) | Economic |  | 2023-01-01 | 2022-03-11 | 2021 ITP |  |  |  | 280000 |  | NTC - Commitment Window |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD to achieve a 398/398/398/398 (SN/SE/WN/WE) MVA rating. | 115
210620 | 92237 | 144206 | SPS | TX | Line - Twist - Wilco 115 kV | Wilco 115 kV Substation | Regional Reliability |  | 2022-06-01 | 2021-12-07 | DPA-2021-Feb-1279-1280 |  |  |  | 9225928 |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Exum to Hillmar Cheese Plant 115 kV line 4 miles west of the RB-Exum substation and build the new Wilco Substation
210620 | 92237 | 144207 | SPS | TX | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability |  | 2022-06-01 | 2021-12-07 | DPA-2021-Feb-1279-1280 |  |  |  | 8909901 |  | NTC - Commitment Window |  |  |  |  | Tap the RB-Kemp to Moore 115 kV line 1 mile east of the RB-Kemp substation and build the new Twist Substation
210620 | 92237 | 144208 | SPS | TX | Line - Twist - Wilco 115 kV | Twist - Wilco 115 kV Ckt 1 | Regional Reliability |  | 2022-06-01 | 2021-12-07 | DPA-2021-Feb-1279-1280 |  |  |  | 2678226 |  | NTC - Commitment Window |  |  |  |  | Build a new 115 kV line between the new Twist Substation and the Wilco Substation