| # Activity |  | # Proposed Interval |
| --- | --- | --- |
| Completion of data collection, analyses and special studies that are shown in Appendix A to be incomplete, followed by distribution to all parties of data and all completed studies along with any related workpapers. |  | Not more than 90 days following the date of this response. |
| Technical conference of experts regarding data, explanation and clarifications (via telephone, conference call or through exchange of e-mail). |  | Approximately 10 days following distribution of data and completed studies. |
| Aquila, Inc. prepares and distributes to the parties its proposed Class Cost of Service (CCOS) study and underlying data with workpapers. |  | Approximately 60 days after the issuance of the Commission’s Report and Order in Case No. ER-2004-0034 so that revenue data from that case may be used in the CCOS studies. The operation of law date for Case No. ER-2004-0034 is June 2, 2004. |
| Other parties prepare and distribute to each other their proposed Class Cost of Service studies and (to the extent necessary) underlying data and workpapers. |  | About 45 days following receipt of Aquila, Inc.’s proposed Class Cost of Service study. |
| Technical conference to be informally convened among the active parties to discuss differences in CCOS studies, resolve non-methodological differences (via telephone and physical participation at PSC offices if desired). |  | Roughly 15 days following informal circulation of all CCOS studies. |
| All parties simultaneously file their CCOS studies and supporting testimony with the Commission, and provide their workpapers to the other parties. |  | Roughly 60 days following Technical Conference. |
| All parties simultaneously file their rate design proposals and supporting testimony with the Commission, and provide their workpapers to the other parties. |  | Roughly 2 weeks following the filing of the CCOS studies. |
| All parties simultaneously file their rebuttal testimony to the CCOS studies. |  | Roughly 4 weeks following the filing of the CCOS studies with the Commission. |
| All parties simultaneously file their rate design rebuttal testimony. | Roughly 4 weeks following the filing of the rate design direct testimony with the Commission. |  |
| Statement of Contested Issues filed. | Approximately 2 weeks following the filing of rate design rebuttal testimony. |  |
| Cross-rebuttal and surrebuttal testimony on all issues filed. | About one week following the filing of the Statement of Contested Issues. |  |
| Prehearing conference (possibly by telephone). | About two weeks following the filing of surrebuttal testimony. |  |
| Statements of Position on Issues filed; Order of Witnesses, Order of Cross-examination filed. | About 2-3 days following the prehearing conference. |  |
| Evidentiary Hearing. | Roughly 1-2 weeks following Statements of Position as permitted by Commission's calendar and to permit pre-hearing briefing for Commissioners. At this time it is not possible to estimate accurate the amount of hearing time that would be needed, but it is sensed that at least 1 week would be needed. |  |