Exhibit No.

Issue:	Energy Center Costs, Fuel and Purchased Power Expenses, IEC

Witness:  Brad Beecher

Type of Exhibit:  Surrebuttal Testimony

Sponsoring Party:  Empire District

Case No. ER-2004-0570

Date Testimony Prepared: November 22, 2004

Before the Public Service Commission

of the State of Missouri

Surrebuttal Testimony

Of

Bradley P. Beecher

November 22, 2004

TABLE OF CONTENTS

OF

BRADLEY P. BEECHER

THE EMPIRE DISTRICT ELECTRIC COMPANY

BEFORE THE

MISSOURI PUBLIC SERVICE COMMISSION

SUBJECT								        PAGE

INTRODUCTION						     		1

ENERGY CENTER UNITS 3 AND 4						1

NATURAL GAS PRICE AND OVERALL TREATMENT

OF FUEL AND PURCHASE POWER EXPENSES				4

SURREBUTTAL TESTIMONY

OF

BRADLEY P. BEECHER

ON BEHALF OF

THE EMPIRE DISTRICT ELECTRIC COMPANY

BEFORE THE

MISSOURI PUBLIC SERVICE COMMISSION

CASE NO. ER-2004-0570

# Introduction

Q.	PLEASE STATE YOUR NAME AND BUSINESS ADDRESS.

A.	Bradley P. Beecher.  My business address is 602 Joplin Street, Joplin, Missouri.

Q.	BY WHOM ARE YOU EMPLOYED AND IN WHAT CAPACITY?

A.	The Empire District Electric Company (“Empire” or “Company”), I am Vice President of Energy Supply.

Q.	ARE YOU THE SAME BRAD P. BEECHER WHO PREVIOUSLY FILED DIRECT AND REBUTTAL TESTIMONY IN THIS CASE BEFORE THE MISSOURI PUBLIC SERVICE COMMISSION (“COMMISSION”) ON BEHALF OF THE COMPANY?

A.	Yes.

Q.	WHAT IS THE PURPOSE OF THIS TESTIMONY?

A.	The purpose of this surrebuttal testimony is to respond to the positions taken in the rebuttal testimony of Office of Public Counsel (“OPC”) witness Ted Robertson concerning the proposed disallowance of a portion of the project costs related to the construction of the Energy Center Units 3 & 4.  I will also address Empire’s position on the proposed price for natural gas and overall treatment of fuel and purchased power expenses in response to the rebuttal testimony of OPC witness James A. Busch.

I.	ENERGY CENTER UNITS 3 AND 4

Q.	PLEASE BRIEFLY DESCRIBE OPC’S TED ROBERTSON’S POSITION IN REBUTTAL TESTIMONY AS YOU CURRENTLY UNDERSTAND IT.

A.	OPC witness Ted Robertson alleges that Empire was “obviously wasteful” in completing Energy Center Units 3 and 4 as it relates to the scope of work surrounding Patch Construction.

Q.	DID YOU ADDRESS THE PATCH ISSUE IN REBUTTAL TESTIMONY?

A.	Yes.  Please refer to my rebuttal testimony as I rebutted the direct testimony of Staff witness David Elliott and Roberta McKiddy concerning the same issue.

Q.	WHAT FACTORS DID EMPIRE CONSIDER WHEN DETERMINING WHETHER TO PROCEED WITH PATCH OR MOVING ON TO ANOTHER VENDOR?

A.	There were several issues Empire was dealing with around the time it was deemed that Patch could not obtain a performance bond.

1.	Empire needed at least one of the new units on line to meet the 12% minimum Southwest Power Pool (“SPP”) capacity margin requirement before June 1, 2003.

2.	Given that Patch could not obtain a performance bond, what was the most cost effective way to complete the project for our customers?

3.	Given the Staff position in Case No. ER-2001-299, what was the most effective way to minimize risk to our shareholders?

To further expand on item 1, SPP requires every load serving entity to maintain installed capacity equal to 12% in excess of its seasonal peak. Without the addition of Energy Center 3 Empire would have been 47 MW short of the 12% capacity margin requirement in 2003. There is no monetary penalty for not maintaining the contractually agreed upon capacity margin.  Empire, however, takes its power pool obligations seriously.  It is each member of the SPP’s responsibility to maintain electric reliability for our customers.  Mismanagement by any one member of SPP can jeopardize the entire system, resulting in unfortunate events like the blackout in August of 2003.  A change in contractors at this late date was sure to delay the schedule and probably not allow us to meet SPP’s requirements.

Item 2 required us to assess the potential costs to complete the project without Patch.  We knew that if we replaced Patch, the next bidder was a higher cost.  We also knew that if we replaced Patch there would be additional expense for re-work and transition.  On the other hand, we believed that if we managed Patch’s financial involvement in the job, there was an opportunity to complete Patch’s scope at the contract value and finish the project on schedule.

As for item 3, Staff’s recent position on rate treatment of Empire’s State Line Combined Cycle (“SLCC”) Unit in 2001 (Case No. ER-2001-299) weighed in our decision process.  In the SLCC case, Empire had deemed a contractor, Fru-Con, was in default of the contract and replaced them with another contractor at a higher cost.  The replacement of Fru-Con with another contractor at a higher cost was the major basis cited by the Staff in their plant disallowance position in the previous case.  If we replaced Patch with another bidder, we would have not only jeopardized meeting our SPP requirement, but we would have been repeating that which Staff judged as non-prudent in the SLCC case.  By this point, we also knew that the Patch entities were not financially strong.  If Empire continued with Patch we had to limit their financial involvement.

No one has challenged the prudence of the initial selection of Patch. Based on what Empire knew at the time, including a balance of all of the concerns outlined, led us to believe that executing Amendment 01 with Patch provided for the best balance of all concerned.

Q.	DOES OPC WITNESS ROBERTSON CONSIDER ALL OF THE OTHER ISSUES?

A.	No, he doesn’t consider the other important and significant issues that Empire was facing at the time. He only considers the Patch Performance Bond issue.

Q.	PLEASE EXPLAIN.

A.	He picks a line item out of the budget and deems that Empire was wasteful on that one item.  OPC witness Robertson says in his Rebuttal Testimony, page 6, lines 9-11, “It is the Public Counsel’s belief that Company’s failure to enforce the original contract requirement for Patch to post a performance bond caused it to be “on the hook” for the financial responsibility to complete the project.”  As pointed out on page 21 of my rebuttal testimony, Empire bettered its budget in several areas and was given no credit by OPC as to those line items.  Also, it should be remembered that Patch was unable to secure a performance bond, so it was impossible for Empire to enforce that contact provision.

Q.	DOES OPC WITNESS TED ROBERTSON EVER MENTION EMPIRE’S “DEFINITIVE ESTIMATE” IN HIS REBUTTAL TESTIMONY WHEN SPEAKING OF PROPOSED DISSALLOWANCE?

A.	No.  Just like Staff witnesses David Elliott and Roberta McKiddy, OPC witness Ted Robertson takes a line item that was over budget and does not give Empire credit for line items under budget. In other words, he ignores Empire’s definitive estimate.

Q.	DOES EMPIRE BELIEVE IT MADE PRUDENT DECISIONS DURING ITS CONSTRUCTION OF THE ENERGY CENTER UNITS 3 AND 4?

A.	Yes.  Empire believes that after looking at all of the issues, the Commission will agree that Empire made prudent decisions during the construction of Energy Center Units 3 and 4.

Q.	DOES EMPIRE HAVE ANY OTHER COMMENTS REGARDING THIS ISSUE?

A.	We completed the project at only **$           ** over our Board approved $55 million definitive estimate.  We completed the project on schedule which allowed us to maintain the capacity margin requirements required by SPP.  OPC is trying to enforce some type of “perfect construction” standard applied to over budget line items but ignoring under budget line items.  This standard is virtually unattainable when applied on an after-the-fact basis.  We ask that the Commission consider all of the relevant factors, put itself in Empire’s position, and find that Empire made prudent decisions based on all factors we considered at the time.

II.	NATURAL GAS PRICE AND OVERALL TREATMENT OF FUEL AND PURCHASE POWER EXPENSES

Q.	DOES EMPIRE AGREE WITH THE UPDATE THAT OPC WITNESS JAMES A. BUSCH MADE TO HIS NATURAL GAS PRICE?

A.	Empire agrees with the correction OPC witness Busch made due to an error in his formula of his original recommendation.  The correction makes the OPC natural gas price 4.68 $/MMBtu.  However, Mr. Busch is still utilizing NYMEX futures prices for 2005 and 2006 as of September 16, 2004.  As I stated in my rebuttal testimony, the natural gas market has changed dramatically since the time direct testimony was filed.  Using NYMEX future prices as of November 17, 2004, Empire calculates that Mr. Busch’s method would yield a natural gas price of about 5.37 $/MMBtu.

Q.	DO YOU AGREE WITH THE OPC POSITON THAT FUEL AND PURCHASED POWER EXPENSE SHOULD BE TREATED IN THE TRADITIONAL MANNER OF USING ONLY ONE NATURAL GAS PRICE AND NOT USING AN INTERM ENERGY CHARGE (“IEC”) MECHANISM?

A.	The traditional method should only be used to the extent that the Commission would allow Empire the opportunity to collect the Company’s actual prudently incurred fuel and purchased power expenses.  In other words, if the traditional method is used, costs included in rates should reflect reality.

Q.	TO WHAT LEVEL OF TOTAL COMPANY ON-SYSTEM FUEL AND PURCHASED POWER EXPENSE ARE YOU REFERRING?

A.	Based on NYMEX natural gas prices as of November 17, 2004, the total Company on-system fuel and purchased power expense of $137,548,710 for 5,092,000 MWh’s or 27.01 $/MWh is appropriate for setting rates in this case.  The run summary is attached as Surrebuttal Schedule BPB-8.

Q.	IS THIS THE SAME VALUE RECOMMENDED IN YOUR REBUTTAL TESTIMONY?

A.	No.  The change is due to the volatile nature of natural gas prices.  In my rebuttal testimony I supported $140,840,180 for 5,092,000 MWh’s or 27.66 $/MWh for setting rates.  This level was based on spot natural gas at the average NYMEX futures prices for 2005 and 2006 as of October 27, 2004.  This price was 7.50 $/MMBtu.  This resulted in a total natural gas price (i.e. combined with the 2005 hedged position) of 6.02 $/MMBtu.

As of November 17, 2004, the NYMEX futures prices for this same period is now about 6.79 $/MMBtu.  In the new model run 6.79 $/MMBtu was used for the spot natural gas price as opposed to 7.50 $/MMBtu in rebuttal, resulting in a total natural gas price of 5.69 $/MMBtu compared to Mr. Busch’s value of 4.68 $/MMBtu. When the difference of 1.01 $/MMBtu is applied to an expected burn range of 8,000,000 to 10,000,000 MMBtu a before tax expense shortfall of $8 – 10 million dollars will occur. OPC’s proposal is clearly too low to allow Empire to recover it’s prudently incurred fuel and purchased power expenses.

Q.	DOES EMPIRE SUPPORT AN ALTERNATE METHOD OF COST RECOVERY IF THE COMMISSION BELIEVES THAT A LEVEL OF $137,548,710 WITH A NATURAL GAS PRICE OF 5.69 $/MMBTU IS NOT APPROPRIATE AT THIS TIME TO USE FOR SETTING RATES IN THIS CASE?

A.	Yes.  Empire supports a properly crafted IEC as an alternate method as I stated in my rebuttal testimony.  The Company continues to support an IEC in the $20 million range with a term of 5 years as indicated in Empire’s direct case and tariffs.  Although the Company continues to support an IEC with a term of 5 years, Empire would be willing to accept an IEC with a 3 year term. However, anything shorter than a 3 year term would not be acceptable.  Empire believes that anything under 3 years would affect stability for our customers as well as our stockholders and the rating agencies.  If the IEC is constructed with a 1 year term, Empire would have to file another rate case immediately.  Likewise, if a 2 year IEC results, Empire would need to file another case in only 13 months.

Q.	WHAT FLOOR AND CEILING DOES THE COMPANY SUPPORT FOR AN IEC?

A.	The Company supports a $20 million IEC in the range of $120 million to $140 million for 5,092,000 MWh’s.  This represents natural gas prices in the range of roughly 4.00 to 6.00 $/MMBtu.  The $140 million ceiling for 5,092,000 MWh with 6.00 $/MMBtu natural gas is consistent with where natural gas futures and our hedged position were as of October 27, 2004, the time I prepared my rebuttal testimony.

Q.	HOW DOES THIS COMPARE TO STAFF’S FILED POSITION?

A.	In direct testimony Staff supported an IEC with a 2-year term in the range $107,436,748 to 130,888,272 for 5,092,000 MWh’s which represented natural gas prices in the range 3.20 to 5.62 $/MMBtu.  Staff failed to update the natural gas prices in their rebuttal testimony.  However, as I pointed out in my rebuttal testimony, Staff’s direct testimony did not include $2.4 million for firm natural gas transportation and roughly $1.3 million for transportation losses and commodity charges.  Empire believes that Staff has agreed to include these expenses.  This would make Staff’s range roughly $111 million to $135 million for 5,092,000 MWh’s.  This compares to the Company’s position of $120 million to $140 million for 5,092,000 MWh’s.

Q.	DO YOU HAVE ANY COMMENTS REGARDING MR. BUSCH’S STATEMENTS CONCERNING THE LAWFULNESS OF THE IEC?

A.	OPC’s position appears to be that an IEC is lawful only if OPC agrees to it.  However, I fail to understand how the agreement of OPC in a stipulation affects the law.  If the Commission determines that an IEC is lawful under Missouri law, it may utilize an IEC in this case as it has in a previous Empire case (Case No. ER-2001-299) and a recent Aquila Inc. case (Case No. ER-2004-0034), regardless of OPC’s opinion.  In the event that the Commission determines an IEC is unlawful or would lead to unnecessary and possibly time-consuming controversy in the courts, the Commission should allow total Company on-system fuel and purchased power expense based on $137,548,710 for 5,092,000 MWh’s as a basis for Empire’s rates.

Q.	DOES THIS CONCLUDE YOUR SURREBUTTAL TESTIMONY?

A.	Yes it does.