## AMO
| TV-F1-2024 |  |  |  |  | Ameren MO Transmission Lines - 2024
Scheduled Work Listed By Miles Unless Otherwise Noted
[7 empty] | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line # | Line Name | ROW Name | Volt | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.34 | AU |  | Adair-Appanoose-2 |  | 161 | RB | [20 empty] | 1
25 | FD |  | Apache Flats-Mariosa Delta |  | 161 | SG | [20 empty] | 2
14.9 | DN |  | Apache Flats-Sub Tap-1 (Barnett-California - 1 to Apache Flats) |  | 161 | SG | [20 empty] | 2
0.42 | DK |  | Ashley-Sub Tap - 2 (Cahokia-Venice-2 to Ashley) |  | 138 | SCA
12.29 | AC |  | Atchinson-Outlaw |  | 345 | RB | [20 empty] | 2 | 1
0.73 | EH |  | Baumgartner Sub Tap (Meramec-Watson - 2 to Baumgartner) |  | 138 | SCA | [21 empty] | 1
43.24 | WA |  | Belleau-Montgomery-6 |  | 345 | SG |  |  | 1 | [20 empty] | 4
55.2 | FF |  | Belleau-Pike-1 |  | 161 | RB | [10 empty] | 55 | [9 empty] | 18 | 1 | 1 | 2
11.18 | EO |  | Rockwood-Big River |  | 138 | SCA | [23 empty] | 1
13.5 | DS |  | Big River-Tyson 3 & 4 |  | 138 | SCA | [21 empty] | 1 |  | 1
1.09 | EU |  | Blanchette-Sub Tap |  | 138 | SCA
44.2 | BF |  | Bland-Franks-3 |  | 345 | SG | [20 empty] | 3
28.7 | QQ |  | Buck Knob-Rivermines-2 |  | 138 | RT | [20 empty] | 4 | 1 | 1
9 | O |  | Cahokia-Central 1 & 2 |  | 138 | SCA
0.48 | AD |  | Cahokia-Meramec |  | 138 | SCA | [23 empty] | 1
2.47 | CL |  | Cahokia-Popplar-5 |  | 138 | SCA | [23 empty] | 1
31.6 | CD |  | Callaway-Bland-1 (Paralleled Circuits) |  | 345 | SG | [9 empty] | 32 | [10 empty] | 2 | 3 | 2
16.6 | FH |  | Callaway-Loose Creek |  | 345 | SG
17 | CO |  | Calumet-Sub Tap (Pike-Dundee-Calumet) |  | 161 | RB
3.23 | DO |  | Camden-Sub Tap - 2 (Camdenton - 2 - Lakeview to Camden) |  | 161 | SG
2.8 | Q |  | Campbell-Euclid - 4 (Partially Paralleled Circuits) |  | 138 | SCA | [22 empty] | 1 | 1
3.2 | BX |  | Campbell-Maline-1 & 2 |  | 138 | SCA | [10 empty] | 3 | [12 empty] | 1
1.6 | BZ |  | Campbell-Sub Tap-4 (Cahokia-Roxford - 4 to Campbell) |  | 345 | SCA
6.36 | UU |  | Cape-Joppa-1 - (MO side) |  | 161 | RT | [10 empty] | 7
6.1 | CS |  | Cape-Kelso - 2 East Line |  | 161 | RT | [10 empty] | 6 | [9 empty] | 1
7.1 | CW |  | Cape-Kelso -3 (West line) |  | 161 | RT | [10 empty] | 7
4.5 | AF |  | Cape-Viaduct Tap |  | 138 | RT
19.2 | DL |  | Cape-Wedekind-2 |  | 161 | RT |  |  | 19 | [17 empty] | 1 | 2
8.5 | BP |  | Carbide-Sub Tap - 2 (Palmyra-Viele-2) |  | 161 | RB | [10 empty] | 8 | [9 empty] | 1 | 1
5.9 | AJ |  | Central-Watson-1 |  | 138 | SCA | [21 empty] | 1 |  | 1
24.1 | DT |  | Clark-Cominco-2 |  | 161 | RT | [17 empty] | 24 | [5 empty] | 2
95.4 | AE |  | Clark-Osage-2 |  | 138 | RT | [10 empty] | 95 | [9 empty] | 2 | 2 | 3 | 2
17.7 | PP |  | Clark-Pea Ridge 3 & 4 |  | 138 | RT | [10 empty] | 18 | [10 empty] | 1
27.8 | EB |  | Clark-Pilot Knob-1 |  | 161 | RT | [20 empty] | 7 |  | 1
46 | E |  | Conway-Tyson 3 & 4 |  | 138 | SCA | [20 empty] | 1 | 1 |  | 1
2.74 | CH |  | Dillon-Alfermann | ITC | 138 | RT | [22 empty] | 2 | 3
3.5 | D |  | Dorsette-Sub Tap 4 |  | 138 | SCA | [21 empty] | 1
2 | AG |  | Dorsette-Sub Tap 8 |  | 138 | SCA
2.2 | ET |  | Dupo Ferry-Selma |  | 138 | RT | [10 empty] | 2 | [10 empty] | 1
13.5 | DU |  | Fletcher-Cominco - 1 |  | 161 | RT | [20 empty] | 2 |  |  | 2
30.5 | EA |  | Fletcher-Pilot Knob - 2 |  | 161 | RT | [21 empty] | 2 | 2 | 1
9.4 | DZ |  | Fletcher-Sweetwater - 3 |  | 161 | RT | [20 empty] | 1 | 1
0.9 | AH |  | Ft. Zumwalt-Sub Tap |  | 138 | SCA | [22 empty] | 1
56.6 | AI |  | Gasco-Osage-2 |  | 138 | SG |  |  | 1 | [17 empty] | 3 | 3 | 3
12.13 | CG |  | General Motors-Sub Tap |  | 161 | SG
6.1 | R |  | Gray Summit-Franklin 1 & 2 |  | 138 | RT | [21 empty] | 1
21.84 | EF |  | Gray Summit-Rockwood 3 & 4 |  | 138 | SCA | [10 empty] | 11 | [9 empty] | 1 | 1 |  | 2
14.2 | CP |  | Guthrie-Moreau-1 |  | 161 | SG |  |  | 14 | [17 empty] | 1 |  |  | 3
30.7 | CC |  | Guthrie-Overton-3 |  | 161 | SG | [20 empty] | 3 |  | 3
1.7 | DJ |  | Hall Street-Ashley 1 |  | 138 | SCA | [23 empty] | 1
8.28 | FA | 4549 | Herlman-Maywood(Missouri) | ITC | 345 | RB | [9 empty] | 0 | 8
16.5 | FE |  | Hughes-High Prairie Wind |  | 345 | RB | [20 empty] | 1 | 1
5.2 | BL |  | Hunter-Sub Tap 1 & 2 (Page-Mason 1 & 2 to Hunter) |  | 138 | SCA | [20 empty] | 1
18.86 | HA |  | Joachim-St. Francis 1&2 |  | 138 | RT | [21 empty] | 3 | 1
5.14 | ES |  | Joppa-Kelso (MO side) |  | 345 | RT | [20 empty] | 2
17.7 | EX |  | Kelso-Lutesville-1 |  | 345 | RT | [20 empty] | 1
19.1 | CT |  | Kelso-Miner-2 |  | 161 | RT | [20 empty] | 3 | 1
29.41 | CX |  | Kelso-Stoddard-3 |  | 161 | RT | [20 empty] | 1
40.2 | BE |  | Labadie-Bland-3 |  | 345 | RT | [20 empty] | 3 |  | 2
6 | AP |  | Labadie-Gray Summit-3 |  | 138 | SCA
50 | AS |  | Labadie-Montgomery-4 |  | 345 | RT | [20 empty] | 3 | 1
60 | AV |  | Labadie-Tyson 1 & 2 |  | 345 | SCA | [10 empty] | 30 | [11 empty] | 1 | 1
0.25 | DP |  | Lathrop-Sub Tap (NW Electric Co-op to Lathrop) |  | 161 | RB
5 | J |  | Lemay-Sub Tap 1 & 2 (Cahokia-Meramec 1 & 2 to Lemay) |  | 138 | SCA | [23 empty] | 1
37.29 | FI |  | Loose Creek-Franks-2 |  | 345 | SG | [21 empty] | 1 | 1
12 | FM |  | Loose Creek-Mariosa Delta |  | 345 | SG | [23 empty] | 2
13 | AK |  | Lutesville-Heritage |  | 345 | RT
63 | AQ |  | Lutesville-St. Francois-1 |  | 345 | RT | [20 empty] | 4 | 2 | 4 | 1
9.6 | DD |  | Marion Tap-2 (Pike-Palymyra - 2 to Marion Sub) |  | 161 | RB | [20 empty] | 1 | 2 | 2
8.3 | BV |  | Marshall-Lakeshire-4 |  | 138 | SCA | [23 empty] | 1
8.2 | ED |  | Marshall-Sub Tap-1 (Central-Watson - 1 to Marshall) |  | 138 | SCA | [21 empty] | 1 | 1 | 1
14.6 | AW |  | Marshall-Tyson 1 & 2 |  | 138 | SCA | [21 empty] | 1 |  | 1
11.16 | DH |  | Mason-Carrollton-8 |  | 138 | SCA | [20 empty] | 1 | 1
26.3 | LL |  | Mason-Gray Summit 1 & 2 |  | 138 | SCA
50 | AR |  | Mason-Labadie 3 & 4 |  | 345 | SCA | [20 empty] | 1 | 1 | 3 | 2
12.04 | ER |  | Mason-McClay -9 |  | 138 | SCA | [20 empty] | 1 | 0 |  | 1
47 | C |  | Mason-Meramec 1 & 2 |  | 138 | SCA | [20 empty] | 1 |  | 1
26.9 | BQ |  | Mason-Sioux-7 |  | 345 | SCA | [23 empty] | 1
3 | DQ |  | Maurer Lake Sub Supply (MO City-Carrollton to M. Lake) |  | 161 | RB | [20 empty] | 1 | 1
121.75 | I |  | Maywood-Hills |  | 345 | RB | [20 empty] | 3 | 1 | 1 | 4
65.22 | FB |  | Maywood-Zachary | ITC | 345 | RB | [20 empty] | 3 | 1
5.3 | DC |  | McClay-Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to McClay) |  | 138 | SCA | [23 empty] | 1
4.69 | F |  | Meramec-Baumgartner - 1 |  | 138 | SCA | [20 empty] | 1 |  | 2
16.27 | H |  | Meramec-Joachim 1 & 2 |  | 138 | SCA | [20 empty] | 3 | 1 | 1 | 1
13.9 | G |  | Meramec-Watson - 2 |  | 138 | SCA | [20 empty] | 1 | 3 | 1 | 1
18.6 | CR |  | Miller-Zion-1 |  | 138 | SG | [20 empty] | 2 |  | 2
10 | CV |  | Miner-Charleston-1 |  | 161 | RT | [10 empty] | 10
10 | CU |  | Miner-Sikeston-1 |  | 161 | RT | [10 empty] | 10
1.41 | AL |  | Mississippi-Sub Tap-1 & 2 MO |  | 138 | SCA
46.44 | CB |  | Montgomery-Callaway 7 & 8 |  | 345 | SG | [20 empty] | 1
38 | AT |  | Montgomery-Guthrie-3 |  | 161 | SG |  |  |  | 38 | [14 empty] | 25 |  |  | 2 |  | 15
64.7 | II |  | Montgomery-Maywood |  | 345 | SG | [20 empty] | 1
64 | ZZ |  | Montgomery-Overton-5 |  | 345 | SG |  |  | 64 | [17 empty] | 1 |  |  | 3
5 | EL |  | Moreau-Mariosa Delta |  | 161 | SG | [20 empty] | 1
1 | CF |  | O'Fallon Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to O'Fallon) |  | 138 | SCA
52.26 | VV |  | Osage-Overton |  | 138 | SG | [9 empty] | 52 | [10 empty] | 4
35.9 | BS |  | Overton-Moberly-1 |  | 161 | RB | [20 empty] | 1 | 1
10.1 | BT |  | Overton-Sedalia-1 |  | 161 | SG | [20 empty] | 1
2.5 | P |  | Page-Euclid-1 (Paralleled Circuits) |  | 138 | SCA | [22 empty] | 1 | 1
19.6 | A |  | Page-Mason 1 & 2 |  | 138 | SCA | [21 empty] | 1 |  | 1
21.6 | U |  | Page-Sioux-4 |  | 138 | SCA | [20 empty] | 1 | 1 | 1 | 3
11.6 | B |  | Page-Warson 5 & 6 |  | 138 | SCA | [23 empty] | 2
2.5 | BM |  | Palmyra Sub Supply - 1 (Montgomery Sub T-1 to Palmyra) |  | 345 | RB
6.2 | BN |  | Palmyra-North Marblehead-1 |  | 161 | RB | [10 empty] | 6 | [11 empty] | 2
70 | BH |  | Palmyra-Viele-2 |  | 161 | RB | [10 empty] | 70 | [9 empty] | 2 | 1 |  | 4
| CN |  | Pike-Dundee 3 & 4 |  | 161 | RB | [21 empty] | 1
40 | GG |  | Pike-Palmyra-2 |  | 161 | RB | [10 empty] | 40 | [9 empty] | 11
72.89 | CI |  | Rivermines-Alfermann | ITC | 138 | RT | [22 empty] | 4 | 4
71 | TT |  | Rivermines-Cape-1 |  | 138 | RT | [20 empty] | 4 | 3 | 3 | 1
24.9 | NN |  | Rivermines-Clark-2 |  | 138 | RT | [20 empty] | 5 | 1 |  | 1
29.8 | SS |  | Rivermines-Taum Sauk 1 & 2 |  | 138 | RT | [20 empty] | 2 | 2
1.7 | EK |  | Rush Island-Holcim-1 (Distribution) |  | 345 | RT
17 | BO |  | Rush Island-St. Francois-1 |  | 345 | RT | [20 empty] | 1 |  | 2
66.2 | BI |  | Rush Island-Tyson 1 & 2 |  | 345 | SCA | [10 empty] | 33 | [10 empty] | 1
11.9 | JJ |  | Salisbury-Moberly - 10 |  | 161 | RB | [20 empty] | 1 | 1 | 1
23.34 | W |  | Sioux-Belleau-6 |  | 345 | SCA | [10 empty] | 1 | [9 empty] | 1 |  |  | 2
32 | AB |  | Sioux-Maline 3 & 4 |  | 138 | SCA | [23 empty] | 1
4.82 | AO |  | Sioux-Meppen MO |  | 138 | SCA
28.6 | AA |  | Sioux-Roxford 5 MO |  | 345 | SCA
24.46 | EP |  | St. Francois-New Bourbon |  | 138 | RT | [21 empty] | 3 |  | 1
10 | BC |  | St. Francois-Rivermines 1 |  | 138 | RT | [20 empty] | 1 | 1
10 | BC |  | St. Francois-Rivermines 2 |  | 138 | RT | [18 empty] | 10 |  | 2 | 2
10 | BC |  | St. Francois-Rivermines 3 |  | 138 | RT | [18 empty] | 10 |  | 1 | 1
1.04 | BD |  | St. Francois-Sub Tap-2 |  | 138 | RT | [20 empty] | 1 | 1
12.4 | CZ |  | Stoddard-Berntie - 1 (Includes Stoddard to Richland) |  | 161 | RT | [22 empty] | 1
6.25 | CQ |  | Tegeler-Explorer-1 |  | 138 | SG | [20 empty] | 1
44.1 | AM |  | Thomas Hill-Adair-1 |  | 161 | RB | [20 empty] | 1 | 2 | 2 | 1
|  |  | Trail of Tears-Charmin |  | 161 | RT
0 | EW |  | Troy sub Tap (C.E.P.C. owned) |  | 161 | SG
11.96 | AX |  | Tyson-Meramec-4 |  | 138 | SCA | [23 empty] | 1
3.15 |  |  | Venice-Campbell 1 |  | 138 | SCA
3.91 | BW |  | Venice-Campbell-1 & 2 MO |  | 138 | SCA | [23 empty] | 1
12.81 | AN | 7407 | Wedekind-Charmin |  | 161 | RT | [21 empty] | 1 | 1
4.56 | YY |  | Wedekind-Sub Tap-1 |  | 161 | RT |  |  | 5 | [7 empty] | 5 | [9 empty] | 1 | 1 |  | 1
31.03 | FC | 5944 | Zachary-Ottumwa | ITC | 345 | RB | [20 empty] | 2 | 2
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [5 empty] | Totals | 0 | 0 | 104 | 38 | 0 | 0 | 0 | 0 | 0 | 84 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 45 | 0 | 144 | 77 | 61 | 92
[29 empty] | 1Q | 144
[29 empty] | 2Q | 185
Radial Taps | [28 empty] | 3Q | 635
[29 empty] | 4Q | 130
1094
Note on AB5: Breece, Rachel: work pushed from Q3 2023 due to crew availability
Note on D8: Strauss, Anthony D: includes Cahokia - Ashley 2 (MO Side) and Ashley - Venice 2 (MO Side)
Note on AB9: Breece, Rachel: some work pushed to Q2 2024 due to crew availability
Note on AC9: Breece, Rachel: completed remaining work from Q1 due to crew availability
Note on D10: Strauss, Anthony D: Meramec Watson from str 40 to Baumgartner
Note on AC10: Campos Alfaro, Salvador P1 IDENTIFIED ON 2024 PATROL
Note on J11: Henderson, Michelle: hazard tree
Note on AE11: Graham, Sharon K: work Identified in 2024 4th qtr patrol
Note on AB12: Breece, Rachel: some work pushed to Q2 due to crew availability
Note on AC12: Breece, Rachel: completed remaining work from Q1 due to crew availability
Note on AD12: Breece, Rachel: work identified on 2nd qurter patrol
Note on AE12: Breece, Rachel: work identified on 2nd qurter patrol 2024
Note on AE13: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on AC14: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AE14: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D15: Strauss, Anthony D: Includes Mason-McClay from str 53 to Blanchette
Note on AB17: Thurman, Ralph E: work identified on 2023 4th Q patrol
Note on AC17: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AD17: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AE19: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D20: Strauss, Anthony D: Includes Cahokia Russell 2 & 4 (MO side). Includes Cahokia Gratiot str 6 to Gratiot sub. Includes Cahokia - Central Str 9-1010-1011-Gratiot
Note on AE20: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AB21: Graham, Sharon work done due to crew availability
Note on AD21: Graham, Sharon K: Work identified from 2nd quarter patrol
Note on D23: Henderson, Michelle: New for 2024: Combining Pike-Dundee and Dundee-Calumet into Calumet Sub Tap
Note on AE25: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on AE26: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D27: Strauss, Anthony D: Includes Cahokia Roxford from str 1150 to Campbell sub
Note on J32: Thurman, Ralph E: Work completed due to Helicopter availability
Note on AC32: Thurman, Ralph E: Work identified on 2024 2nd Qtr. OHT patrol
Note on AC33: Breece, Rachel: remaining work from Q1 completed
Note on AC34: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AE34: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on Y35: Thurman, Ralph E: Trimmed due to Jaraff availability
Note on AE35: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AB36: Thurman, Ralph E: work identified on 2023 3rd Q patrol
Note on AD36: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AE36: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AB38: Thurman, Ralph E: Mowed no spray in National Forest
Note on AD38: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on D39: Porcelli, Jennifer L: Includes portion of Marshall-Tyson
Note on AB39: Campos Alfaro, Salvador:work done early due to crew availability.
Note on AE39: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on AD40: Thurman, Ralph E: Reclamation project
Note on AE40: Thurman, Ralph E: Reclamation project
Note on D41: Strauss, Anthony D: Includes Warson - Mason from str 57 to Dorsette sub. Includes Mason - Carrolton from Dorsette sub to str 129
Note on AC43: Thurman, Ralph E: Work identified on 2024 2nd Qtr. OHT patrol
Note on AB44: Thurman, Ralph E: hazard tree found on 2024 patrol
Note on AE44: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AD45: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AE45: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AD47: Campos Alfaro, Salvador: Work found in 2024 Patrol
Note on J48: Henderson, Michelle: hazard tree
Note on AB48: Graham, Sharon K: work done due to crew availability
Note on AD48: Graham, Sharon K: work idnetified from 2nd quarter patrol
Note on D49: Graham, Sharon K: includes Belleau-GM-3 and GM-Point Prairie-3
Note on AC51: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AE51: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on J52: Henderson, Michelle: trimming added due to additional funding and crew availability
Note on AE52: Graham, Sharon K: work found in the 2024 second qtr patrol
Note on AD53: Graham, Sharon K: work identified from 2nd quarter patrol
Note on AE54: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on Q55: Breece, Rachel: pushed to 3rd Quarter due to crew availability
Note on AB56: Breece, Rachel: Work identified on 4th period 2023 patrol
Note on AC56: Breece, Rachel: Work identified on 4th period 2023 patrol
Note on D57: Strauss, Anthony D: Includes Page-Mason from Str 22 to Hunter sub. Includes Central - Watson str 55-2056-1079. Includes Marshall Lakeshire from structure 1079 to Hunter sub
Note on AD58: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AB60: Thurman, Ralph E: work identified on 2024 1st Q patrol
Note on AC61: Thurman, Ralph E: Tree disbursement
Note on AB62: Thurman, Ralph E: work identified on 2022 4th Q patrol unable to complete due to weather and crops. Completed on 1/4/24
Note on AD63: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AC65: Thurman, Ralph E: Work identified on 2024 1st Qtr. patrol
Note on AE66: Campos Alfaro, Salvador: P1 identified on 2nd patrol
Note on D68: Strauss, Anthony D: Includes Meramec-Watson from Mackenzie Switch to str 86
Note on AE68: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on AD69: Graham, Sharon K: work identified from 2nd quarter patrol
Note on AE70: Graham, Sharon K: work found in 2024 3rd qtr patrol
Note on AC72: Thurman, Ralph E: Work identified on 2024 1st Qtr. patrol
Note on AD72: Thurman, Ralph E: Work identified on 2024 1st Qtr. patrol
Note on AE72: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on AB73: Breece, Rachel: some work completed ahead of schedule due to crew availability work originally pushed from Q2 2023 due to crew availability
Note on AC73: Breece, Rachel: some work pushed from Q2 2023 due to crew availability
Note on AD73: Breece, Rachel: some work pushed from Q2 2023 due to crew availability
Note on D74: Strauss, Anthony D: Str 37A to Lakeshire sub
Note on AE74: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D75: Strauss, Anthony D: Includes Central - Watson and Marshall - Lakeshire from Marshall to str 1079
Note on AE75: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on AC76: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AE76: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D77: Strauss, Anthony D: Includes Mason - Carrolton and Carrollton Sioux from str 52 to carrolton sub
Note on AB77: Campos Alfaro, Salvador: work was complerted in 1st quarter due to crew availability
Note on AC77: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol Also Good Dry Access
Note on D78: Strauss, Anthony D: only includes isolated section of Mason Gray Summit from str 98 to 327
Note on D79: Strauss, Anthony D: Includes Mason-Wildwood and Wildwood - Gray Summit from wildwood sub to Str 98
Note on AB79: Campos Alfaro, Salvador: work done due to crew availability
Note on AC79: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AD79: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AE79: Campos Alfaro, Salvador: work identified on 2024 1st and 2nd quarter patrol
Note on AB80: Campos Alfaro, Salvador: work was complerted in 1st quarter
Note on AC80: Campos Alfaro, Salvador: work was complerted in 1st quarter due to dry access
Note on AE80: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on AB81: Campos Alfaro, Salvador: the rest of work was done in 4th quarter 2023
Note on AD81: Campos Alfaro, Salvador: P1 Found while driving by uptooting tree
Note on D82: Strauss, Anthony D: Includes Mason Carrolton from Mason Sub to str 52. Includes Carrolton - Sioux from Sioux to str 52.
Note on AE82: Campos Alfaro, Salvador: work identified on 2024 1st and 2nd quarter patrol
Note on AB83: Breece, Rachel: work completd ahead of schedule due to crew availability
Note on AB84: Breece, Rachel: Work identfied on 2023 OHT patrol in 4h patrol period
Note on AC84: Breece, Rachel: work identified on Q1 ground patrol
Note on AD84: Breece, Rachel: work identified on 2nd quarter patrol
Note on AE84: Breece, Rachel: work identified on 1st quarter patrol 2024
Note on AB85: Breece, Rachel: some work completd ahead of schedule due to crew availability work originally pushewd from Q3 2023 due to crew availability
Note on AC85: Breece, Rachel: work originally pushed from Q3 2023 due to crew availability
Note on AE86: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D87: Strauss, Anthony D: Includes Baumgartner Watson from Baumgartner to str 54
Note on D88: Porcelli, Jennifer L: Includes Meramec-Sandy Creek and Sandy Creek - Joachim
Note on AD88: Campos Alfaro, Salvador: P1 Found on 2024 patrol
Note on AE88: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on D89: Strauss, Anthony D: Includes Baumgartner Watson from str 54 to Watson
Note on AE89: Campos Alfaro, Salvador: work identified on 2024 4th quarter patrol
Note on AD90: Graham, Sharon K: work identified fro previous patrol
Note on D93: Strauss, Anthony D: Includes Sioux - Roxford 1 & 2 from str 51 to 57
Note on K95: Henderson, Michelle: trimming added due to additional funding and crew availability
Note on Z95: Graham, Sharon K: reclamation
Note on AE95: Graham, Sharon K: reclamation
Note on D96: Graham, Sharon K: include Montgomery-Spencer Creek, Spencer Creek-Maywood
Note on J97: Henderson, Michelle: trimming added due to additional funding and crew availability
Note on AE97: Graham, Sharon K: work found in the 2024 second qtr patrol
Note on D100: Graham, Sharon K: includes: Osage Plant-Osage Sub (4 circuits), Osage-Eldon, Eldon-Barnett, Barnett-California, California-Overton
Note on AB101: Breece, Rachel: work identified from 2023 aerial trimming
Note on AC101: Breece, Rachel: work identified from 2023 aerial trimming
Note on AD103: Campos Alfaro, Salvador: Some work identified on 2024 Patrol
Note on AE103: Campos Alfaro, Salvador: work identified on 2024 4th quarter patrol
Note on D104: Strauss, Anthony D: Includes Warson - Mason
Note on AC104: Campos Alfaro, Salvador: work done due to crew availability
Note on AE104: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on D105: Strauss, Anthony D: Runs from Page to str 50 on Mason - Sioux.Includes Page - Berkeley and Berkeley - Sioux
Note on AB105: Campos Alfaro, Salvador: work done due to crew availability
Note on AC105: Campos Alfaro, Salvador: work done due to crew availability
Note on AD105: Campos Alfaro, Salvador: Reclamation
Note on AE105: Campos Alfaro, Salvador:took care of priorities while doing Reclamation
Note on AE106: Campos Alfaro, Salvador: work identified on 2024 3rd quarter patrol
Note on AD108: Breece, Rachel: work identified on 2nd quarter patrol
Note on AB109: Breece, Rachel: Work identified on 3rd period 2023 patrol
Note on AC109: Breece, Rachel: Work identified on 3rd period 2023 patrol and 2024 OHT
Note on AE109: Breece, Rachel: work identified on 3rd quarter patrol 2024
Note on D110: Henderson, Michelle: will be removing for 2024. Pike-Dundee is now part of the Calumet Sub tap
Note on AC110: Breece, Rachel: work idetified 2nd period patrol 2023
Note on AD112: Thurman, Ralph E: Reclamation project
Note on AE112: Thurman, Ralph E: Reclamation project
Note on AC113: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AD113: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AE113: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AB114: Thurman, Ralph E: Mowed no spray in National Forest
Note on AE114: Thurman, Ralph E: Constrution for Clark sub rebuild. (Clemens)
Note on AC115: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AD117: Thurman, Ralph E: Work identified on 2024 3rd Qtr. patrol
Note on D118: Porcelli, Jennifer L: Includes portion of Rush Island Subtap
Note on AC118: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on AB119: Breece, Rachel: some wok pushed to Q2 due to crew availability
Note on AC119: Breece, Rachel: completed remaining work from Q1 due to crew availability
Note on AD119: Breece, Rachel: work identified on 2024 OHT patrol
Note on R120: Campos Alfaro, Salvador:only applied on 4 spans near creek aquatic herbicide
Note on AB120: Campos Alfaro, Salvador: work done due to dry access
Note on AE120: Campos Alfaro, Salvador: work identified on 2024 1st and 2nd quarter patrol
Note on AE121: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D122: Strauss, Anthony D: Includes Sioux - Meppen North 4 From str 176E to Str 146. Includes Out of Service lines from 146 to 122
Note on D123: Strauss, Anthony D: Runs from Sioux to str 77. Includes Sioux - Roxford 1 & 2
Note on AE124: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AB125: Thurman, Ralph E: hazard tree found on 2024 patrol
Note on AC125: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on Z126: Thurman, Ralph E: Work completed due to Jaraff availability
Note on AC126: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on Z127: Thurman, Ralph E: Work completed due to Jaraff availability
Note on AB127: Thurman, Ralph E: work identified on 2023 2nd Q patrol
Note on AB128: Thurman, Ralph E: work identified on 2023 2nd Q patrol
Note on AD129: Thurman, Ralph E: Construction project
Note on AB131: Breece, Rachel: work idetified from 2023 aerial trimming
Note on AC131: Breece, Rachel: work idetified from 2023 aerial trimming
Note on AD131: Breece, Rachel: work identified on 3rd qurter patrol
Note on AE131: Breece, Rachel: work identified on 3rd quarter 2024 patrol
Note on D132: Henderson, Michelle: For 2024: combined with Wedekind-Trail of Tears into one line: Wedekind-Charmin
Note on D134: Porcelli, Jennifer L: Includes Tyson-Arnold and Arnold-Meramec
Note on AE134: Campos Alfaro, Salvador: work identified on 2024 2nd quarter patrol
Note on D136: Strauss, Anthony D: Include Venice - Campbell from st 2020 to Campbell. Includes Venice Hall st from str 2020 to 1020
Note on AE136: Campos Alfaro, Salvador: work identified on 2024 1st quarter patrol
Note on D137: Henderson, Michelle: New for 2024: Combine Wedekind-Trail of Tears and Trail 0f Tears-Charmin into one line: Wedekind-Charmin-7407
Note on AC137: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on AD137: Thurman, Ralph E: Work identified on 2024 2nd Qtr. patrol
Note on J138: Thurman, Ralph E: Work completed due to Helicopter availability
Note on AC138: Thurman, Ralph E: Work identified on 2024 2nd Qtr. OHT patrol
Note on AE138: Thurman, Ralph E: Work identified on 2024 4th Qtr. patrol
Note on AB139: Breece, Rachel: some work completed ahead of schedule due to crew availability work originally pushed from Q3 2023 due to crew availability
Note on AC139: Breece, Rachel: work originially pushed from Q3 2023 due to crew availability

## MO
MO - 2024 - Scheduled vs. Completed Work
Quarter | Scheduled Miles | Completed Miles | Percentage Completed
1 | 144 |  | 0%
2 | 185 |  | 0%
3 | 635 |  | 0%
4 | 130 |  | 0%
Totals | 1094 | 0 | 0%

## AIC
| TV-F1-2024 |  |  | AMEREN IL TRANSMISSION LINES - 2024
Scheduled Work Listed By Miles Unless Otherwise Noted
[7 empty] | Aerial Side Trimming Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line # | Line Name | ROW Name | Volt | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.95 | NJ | 1590 | ADM Faries Parkway-Hans |  | 138 | JC | [20 empty] | 1
1.27 | TE | 1651 | ADM North-ADM Faries Parkway |  | 138 | JC | [20 empty] | 1
8.23 | TG | 1616 | ADM North-Mount Zion Route 121 |  | 138 | JC | [10 empty] | 8 | [9 empty] | 1
17.25 | BI |  | Albion South-Gibson, P.S. Indiana |  | 345 | JP | [20 empty] | 1
39.87 | AL |  | Albion South-Norris City North |  | 345 | JP | [20 empty] | 1
2.63 | AE | 1452B | American Steel-Sub Tap |  | 138 | TS | [20 empty] | 1 | 1
34.1 | SM | 1536 | Ashley-Jordan |  | 138 | JP | [21 empty] | 1 | 1 | 1
12.17 | SE | 1486 | Ashley-Mount Vernon West |  | 138 | JP | [9 empty] | 0 | 12 | [9 empty] | 1 |  | 1
9.73 | T | 1619 | Auburn North-Austin |  | 138 | JWM | [21 empty] | 1 | 1
36.5 | U | 1306 | Auburn North-Jacksonville Ind. Park |  | 138 | JWM | [21 empty] | 1
5.35 | ZD | 4522 | Austin-Kincaid |  | 345 | TS
76.5 | JD | 4527 | Austin-Meredosia | ITC | 345 | TS | [9 empty] | 76 | [10 empty] | 2 | 3
6.13 | BC |  | Avena-Sub Tap |  | 138 | JC | [20 empty] | 1 |  | 1
10.56 | BQ | 1482A | Aviston-Sub Tap |  | 138 | TS
12.92 | TV | 4538/4531 | Baldwin-Prairie State-4538 |  | 345 | TS
13.81 | TX | 4548 | Baldwin-Prairie State-4548 |  | 345 | TS | [23 empty] | 1
2 | BR | 1526A | Baldwin-Sub Tap |  | 138 | TS | [20 empty] | 1
20.78 | TM | 4521 | Baldwin-Turkey Hill |  | 345 | TS | [20 empty] | 1
0.99 | BS | 1586A | Belleville 17TH. ST. Spur |  | 138 | TS | [20 empty] | 1 | 1
3.37 | BT | 1586B | Belleville 65TH ST Spur |  | 138 | TS | [20 empty] | 1 | 1 | 1 | 1
43.57 | SD | 1482 | Belleville Turkey Hill-Ashley |  | 138 | TS | [20 empty] | 1 | 1 | 1
2.29 | SL | 1532 | Belleville Turkey Hill-South Belleville |  | 138 | TS | [20 empty] | 1
13.16 | FF |  | Benton Northwest-Ina |  | 138 | JP | [9 empty] | 0 | 13 | [10 empty] | 1 | 1 | 1
9.08 | EE | 1517 | Benton NW - Jordan - 1517 |  | 138 | JP | [9 empty] | 0 | 9 | [11 empty] | 1 | 2
5.72 | CH | 1462 | Blue Mound-Sub Tap |  | 138 | JC
6.53 | ZH | 1638 | Bondville-SW Campus |  | 138 | JC
28.54 | SX | 1582 | Brokaw-Gibson City |  | 138 | JC
34.66 | RK | 1376 | Brokaw-Mahomet |  | 138 | JC
9.1 | SW | 1578 | Brokaw-Normal East |  | 138 | JWM
5.63 | CB | 4555 | Brokaw-S Bloomington |  | 345 | JWM
9.28 | SV | 1576 | Bunsonville-Tilton Energy Center |  | 138 | JC
13.75 | KA |  | Cahoka-Dupo Ferry - 1 (Paralleled Circuits) |  | 138 | TS
36.23 | TL | 4511 | Cahokia-Baldwin |  | 345 | TS | [20 empty] | 1 |  | 1
5.93 | TY | 1492A | Cahokia-Centerville |  | 138 | TS
1 | VA |  | Cahokia-Central |  | 138 | TS | [21 empty] | 3
1 | CX |  | Cahokia-Gratiot - 3 & Cahokia - Russell - 2 |  | 138 | TS | [9 empty] | 0 | 1
18.2 | IB |  | Cahokia-Meramec 1 & 2 |  | 138 | TS | [9 empty] | 0 | 18
36.4 | LA | 4574 | Cahokia-Prairie State |  | 345 | TS | [22 empty] | 1
3.2 | ML |  | Cahokia-Ridge 1& 2 |  | 138 | TS | [20 empty] | 1 | 1
17.6 | AC |  | Cahokia-Roxford - 4 (Paralleled Circuits) |  | 345 | TS | [9 empty] | 0 | 17
0.63 | CY |  | Cahokia-Russell - 4 & Cahokia-Poplar - 5 |  | 138 | TS | [9 empty] | 0 | 1
18.89 | SF | 4597 | Cahokia-Turkey Hill |  | 345 | TS | [20 empty] | 1 | 1
4.5 | NA |  | Cahokia-Venice 1 & 2 |  | 138 | TS
40.3 | UU |  | Cape-Joppa-1 |  | 161 | JP | [22 empty] | 2 | 3
18.65 | K | 1515 | Carbondale Northeast - Jordan-1515 |  | 138 | JP | [6 empty] | 19 | [16 empty] | 2
21.16 | BF | 4525 | Casey West-Kansas West |  | 345 | JC
21.13 | AZ | 4587 | Casey West-Neoga South |  | 345 | JC | [10 empty] | 21 | [10 empty] | 3
26.54 | BE |  | Casey West-Newton |  | 345 | JC | [10 empty] | 27 | [10 empty] | 1
27.8 | BA |  | Casey West-Sullivan |  | 345 | JC | [10 empty] | 27 | [10 empty] | 2
11.63 | AG | 1540 | Castro-Canton South |  | 138 | JWM | [21 empty] | 1 | 1
28.51 | MK | 1394 | Caterpillar Mapleton-Sub Tap |  | 138 | JWM | [10 empty] | 29 | [11 empty] | 1 | 2
20.06 | RB | 1313 | Clinton Rt. 54-N. Decatur |  | 138 | JC | [22 empty] | 2
22.41 | TP | 4535 | Clinton-Brokaw |  | 345 | JC | [22 empty] | 1
43.16 | TR | 4545 | Clinton-Goose Creek |  | 345 | JC |  | 29 | [8 empty] | 43 |  |  | 29
5.3 | ZI | 4571 | Clinton-Oreana |  | 345 | JC |  | 5 | [8 empty] | 5 | [5 empty] | 1
8.46 | NC | 1372B | Clinton-Sub Tap |  | 138 | JC
22.34 | AX | 4557 | Coffeen North-Ramsey East |  | 345 | JC | [10 empty] | 22 | [11 empty] | 2
0.28 | I | 4595 | Coffeen-Coffeen North |  | 345 | JC
4.74 | TH | 1626 | Coffeen-Midway |  | 138 | TS | [9 empty] | 0 | 5 | [11 empty] | 2 | 2
30.4 | AW | 4516 | Coffeen-Pana North |  | 345 | TS | [20 empty] | 2 |  | 1 | 2
50.07 | TS | 4551 | Coffeen-Roxford |  | 345 | TS | [20 empty] | 1 |  | 1 | 1
15.88 | LB | 4513 | Commodore - Aster |  | 345 | JP | [9 empty] | 0 | 16 | [11 empty] | 1 | 1
0.28 | DK |  | Commodore - Pinckneyville-1597 |  | 138 | JP
0.28 | DL |  | Commodore - Pinckneyville-1715 |  | 138 | JP
6.39 | AI |  | Crab Orchard-Marion North |  | 138 | JP | [20 empty] | 1 | 1 | 1
19.11 | VV |  | Crab Orchard-Muddy |  | 138 | JP | [20 empty] | 1 | 2 |  | 1
2.32 | RH | 1364A | Diamond Star-Sub Tap |  | 138 | JWM
0.83 | RC | 1326A | Diamond Star-Sub Tap |  | 138 | JWM
8.84 | DS | 1477 | Docket - Greenback |  | 138 | JWM
21.07 | BH | 4573 | Duck Creek-Ipava South |  | 345 | JWM | [21 empty] | 1 |  | 1
34.72 | ND | 4563 | Duck Creek-Tazewell |  | 345 | JWM | [20 empty] | 1 | 1 | 2 | 2
23.52 | CE |  | Dupo Ferry-Buck Knob - 1 (Paralleled Circuits) |  | 138 | TS
6.48 | AR |  | E. Quincy-Quincy South |  | 138 | JWM | [20 empty] | 0 | 1 | 1
4.92 | SB | 1472 | East Belleville-Turkey Hill |  | 138 | TS | [20 empty] | 1 | 1 | 1 | 1
5.87 | RT | 1432 | East Collinsville-O'Fallon Porter Road |  | 138 | TS | [20 empty] | 1 | 2 | 2 | 1
2.44 | RQ | 1416 | East Main Street-Route 51 Decatur |  | 138 | JC | [10 empty] | 2 | [10 empty] | 1
30.5 | HB |  | East Quincy-Hamilton - 4 |  | 138 | JWM | [20 empty] | 0 | 1 | 5 | 2
14.63 | MN | 1422 | East Springfield-Sub Tap |  | 138 | JWM | [22 empty] | 2
4.7 | MP | 1374 | Edwards-Caterpillar 1 |  | 138 | JWM |  | 5 | [18 empty] | 1 |  | 1
5.81 | MD | 1345 | Edwards-Caterpillar Mapleton |  | 138 | JWM | [20 empty] | 1
23.51 | MJ | 1358 shared | Edwards-Fargo 2 |  | 138 | JWM | [20 empty] | 1 | 1
14.62 | MX | 1397 | Edwards-Keystone |  | 138 | JWM | [10 empty] | 15 | [9 empty] | 0 |  |  | 1
21.94 | PP |  | Effingham-Newton |  | 138 | JC | [22 empty] | 1
2.68 | MO | 1382A | El Paso-Sub Tap |  | 138 | JWM
7.46 | JB | 1385 | Faraday-Mount Zion PPG 1385 & 1637 |  | 138 | JC
33 | JA | 4507 | Faraday-Pana | ITC | 345 | JC
12 | MR | 1377 | Fargo-Moss Cat |  | 138 | JWM | [23 empty] | 1
5.54 | MF | 1347/1326 | Fargo-Pioneer |  | 138 | JWM | [20 empty] | 1 | 1 | 2 | 1
4.09 | MQ | 1526D | Fayetteville Bee Hollow-Sub Tap |  | 138 | TS | [20 empty] | 1 |  |  | 1
14.28 | MU | 1526E | Fayetteville Bee Hollow-Sub Tap |  | 138 | TS | [20 empty] | 1
5.36 | ME | 1672 | Fogarty-Kickapoo |  | 138 | JWM | [20 empty] | 2
8 | DT | 1563 | Fogarty-Limit |  | 138 | JWM
2.84 | BK |  | Gibson City S-Gibson City PP |  | 138 | JC
5.75 | NK | 1436A | Gillespie Macoupin St-Sub Tap |  | 138 | TS | [21 empty] | 2 | 3
15.23 | ZJ | 1388 | Gilman-Watseka |  | 138 | JC
14.71 | NL | 4575 | Goose Creek-Rising |  | 345 | JC | [10 empty] | 15 | [11 empty] | 1
16.66 | J |  | Grand Tower-Carbondale Northwest |  | 138 | JP | 17 | [19 empty] | 3 | 4 | 2
30.54 | TT |  | Grand Tower-Marion South |  | 138 | JP | 31 | [19 empty] | 2 | 3 | 3 | 3
0.26 | BO |  | Grand Tower-Perryville |  | 138 | JP
2.07 | DU | 1537 | Greenback - Illiopolis |  | 138 | JWM
1.99 | NM | 1674 | Hans-ADM North |  | 138 | JC
53.9 | RG | 1362 | Havana-Galesburg Monmouth Blvd |  | 138 | JWM | [10 empty] | 54 | [9 empty] | 0 | 0 | 0
46.48 | RF | 1352 | Havana-Huff |  | 138 | JWM
14.91 | ZA | 1356 | Havana-Ipava South |  | 138 | JWM | [20 empty] | 1 | 1
20.2 | RP | 1406 | Havana-Mason City West |  | 138 | JWM | [20 empty] | 1
48.17 | MY | 1422 | Havana-Shockey |  | 138 | JWM
0.65 | TI | 6101 | Hennepin-ComEd |  | 138 | JWM
31.39 | SP | 1552 | Hennepin-East Kewanee |  | 138 | JWM | [20 empty] | 1 | 1 |  | 1
13.38 | SQ | 1556 | Hennepin-Oglesby |  | 138 | JWM
14.51 | SI | 1516 | Hennepin-Oglesby |  | 138 | JWM
26.27 | MZ | 1512 | Hennepin-Spring Bay |  | 138 | JWM
5.5 | ZC | 4549 | Herleman-Maywood(Illinois) | ITC | 345 | JWM
20.8 | MI | 1357 | Hines-Caterpillar Sub. 2 |  | 138 | JWM | [20 empty] | 1 | 1 | 1
20.88 | LL |  | Hoopeston-Paxton East |  | 138 | JC | [20 empty] | 1
22.08 | KK | 1305 | Hoopeston-Vermilion |  | 138 | JC | [10 empty] | 22 | [10 empty] | 1 |  | 2
20.35 | DH |  | Huff-W. Washington |  | 138 | JWM
7 | EA |  | Hull-Sub Tap-1 (Sioux S.Quincy to River) |  | 138 | TS
12.51 | XX | 1311 | Hutsonville-Heath (Marathon Oil) |  | 138 | JC
33.66 | W | 1448 | Hutsonville-Kansas West |  | 138 | JC | [10 empty] | 34 | [9 empty] | 1
45.44 | O |  | Hutsonville-Neoga South |  | 138 | JC | [21 empty] | 1
11.04 | GG |  | Ina-Mt. Vernon 42nd St. (note Ip tap at structure 763) Same Circuit as HH) |  | 138 | JP | [9 empty] | 0 | 11 | [10 empty] | 1
21.18 | AF | 1348 | Ipava South-Canton South |  | 138 | JWM | [22 empty] | 3 | 3
21.41 | NN |  | Ipava South-Macomb West |  | 138 | JWM | [20 empty] | 0 | 1
0.67 | CZ | 1401 | Ipava-Ipava South |  | 138 | JWM
0.71 | NO | 1512A | J&L-Sub Tap |  | 138 | JWM
1.71 | NP | 1552A | J&L-Sub Tap |  | 138 | JWM
19.81 | V | 1612 | Jacksonville Industrial Park-Meredosia East |  | 138 | JWM
0.37 | DB | 1533 | Jarvis-Canteen |  | 138 | TS
2.38 | DC | 1316 | Jarvis-Kren |  | 138 | TS
0.21 | DV | 1728 | Jasper - Olney North |  | 138 | JC
41.7 | H |  | Jerseyville Northeast-Virden |  | 138 | TS |  | 42 | [18 empty] | 3 | 10
0 | BL |  | Joppa,E.E.I -Joppa |  | 161 | JP
32.6 | ES |  | Joppa-Kelso |  | 345 | JP | [9 empty] | 0 | 33 | [9 empty] | 1 | 3 | 1 | 1
23.42 | AV |  | Joppa-Mound City West |  | 161 | JP | [20 empty] | 1 |  |  | 1
28.5 | ET | 4586 | Jordan - Commodore-4586 |  | 345 | JP | [21 empty] | 1 | 1 | 1
47.52 | A | 4523 | Jordan - Massac-4523 |  | 345 | JP | [6 empty] | 48 | [13 empty] | 1 | 2 | 2 | 1
1.15 | DN | 1707 | Jordan - W. Frankfort - 1707 |  | 138 | JP | [9 empty] | 0 | 1
1.23 | DO | 1713 | Jordan - W. Frankfort - 1713 |  | 138 | JP | [6 empty] | 1
10.8 | ZK |  | Kansas West-Charleston NE |  | 138 | JC
18.98 | XA |  | Kansas West-Murdock |  | 138 | JC | [16 empty] | 1
15.02 | Y |  | Kansas West-Paris South |  | 138 | JC | [20 empty] | 1
62 | ZL | 4559 | Kansas-Faraday | ITC | 345 | JC | [23 empty] | 1
3.25 | NQ | 1366A | Kewanee South St-Sub Tap |  | 138 | JWM | [22 empty] | 1 | 1
1.57 | MA | 1325 | Kickapoo-Mcgrath |  | 138 | JWM | [20 empty] | 2 |  | 1
27.6 | BM |  | Kinmundy-Louisville South |  | 138 | JC | [22 empty] | 1
31.06 | II |  | Kinmundy-Mt Vernon West |  | 138 | JP | [9 empty] | 0 | 31 | [9 empty] | 1 | 1 | 1
29.5 | BN |  | Kinmundy-Ramsey East |  | 138 | JC | [20 empty] | 1 |  | 1
1 | WA | 1436/1456 | Laclede Steel Supply - 1 & 2 |  | 138 | TS
| DW | 1314 | Lanesville Sub Tap |  | 138 | JWM
23.85 | NF | 1646 | LaSalle N.-Fox River |  | 138 | JWM
24.82 | ZM | 4515 | Latham-Oreana |  | 345 | JC
22.8 | AB | 1677 | Lawrenceville South-Jasper |  | 138 | JC
21.63 | ZZ |  | Lawrenceville South-Robinson |  | 138 | JC | [20 empty] | 1 |  | 2 | 2
9.89 | AD |  | Lawrenceville South-Vincennes |  | 138 | JC
7.2 | DJ | 1446A | Litchfield-Sub Tap |  | 138 | TS | [21 empty] | 2 | 2 | 1
41.37 | C |  | Macomb Northeast-Niota |  | 138 | JWM
2.82 | OO |  | Macomb West-Macomb Northeast |  | 138 | JWM
41 | DA |  | Macomb-Sub Tap |  | 138 | JWM | [23 empty] | 1
6.82 | TZ | 1452A | Madison Industrial-Stallings |  | 138 | TS | [20 empty] | 1 | 1
0.19 | AE | 1452 T | Madison State St-Sub Tap |  | 138 | TS | [20 empty] | 1
1.55 | BV | 1592A | Mahomet-Sub Tap |  | 138 | JC
15.71 | CA | 4505 | Mapleridge-Fargo |  | 345 | JWM | [10 empty] | 16 | [9 empty] | 1 | 1 |  | 1
6.8 | DE |  | Marion North-Herrin East |  | 138 | JP | [9 empty] | 0 | 7 | [5 empty] | 1
9.1 | UA |  | Marion South-Crab Orchard |  | 138 | JP | [21 empty] | 1 | 1
6.6 | TJ | 6102 | Marseilles-ComEd |  | 138 | JWM
35.3 | RE | 1346 | Mason City West-Latham |  | 138 | JWM
31.33 | AU | 7163 | Massac - Marion S - 7163 |  | 161 | JP | [20 empty] | 1 | 1 | 1 | 1
1.94 | DP | 7174 | Massac - Joppa-7174 |  | 161 | JP
| DQ | 7296 | Massac - Joppa-7296 |  | 161 | JP
15.4 | G |  | Mattoon West-Charleston NE |  | 138 | JC | [20 empty] | 1 |  |  | 4
14.2 | RR |  | Mattoon West-Neoga |  | 138 | JC
1.55 | MB | 1325 | McGrath-Limit |  | 138 | JWM
53.05 | RL | 1382 | McLean-Oglesby |  | 138 | JWM | [16 empty] | 0 | 1 |  |  |  | 1
41.31 | MM |  | Meredosia East-Ipava South |  | 138 | JWM | [21 empty] | 1
31 | D |  | Meredosia East-Roodhouse West |  | 138 | TS | [9 empty] | 0 | 31 | [9 empty] | 2 | 1 |  | 2
45.55 | DD |  | Meredosia-East Quincy (North Line No. 1) |  | 138 | JWM
45.43 | AJ |  | Meredosia-East Quincy (South Line No. 2) |  | 138 | JWM | [10 empty] | 46 | [9 empty] | 0
45.8 | NH | 4503 | Meredosia-Herleman | ITC | 345 | JWM | [10 empty] | 46
46.9 | NG | 4539 | Meredosia-Ipava | ITC | 345 | JWM | [21 empty] | 1 |  | 1 | 182-180A, 176-175, 170-169, 167A-166, 165B-165, 164A-164, 159B-159A, 158B-158A
0.65 | F |  | Meredosia-Meredosia East Lines 1,2,3,4 |  | 138 | JWM
28.23 | SN | 1542 | Midway-South Centralia |  | 138 | JP | [20 empty] | 1 | 3
0.66 | RM | 1386B | Mira-Sub Tap |  | 138 | JC
0.9 | DM |  | Mississippi Sub 3rd Supply (Laclede - 1 (1436) to Mississippi) |  | 138 | TS
1 | BX |  | Mississippi Sub Supply 1 & 2 (Sioux-Roxford 1 & 2 to Mississippi) |  | 138 | TS
0.14 | RD | 1342A | Monsanto-Sub Tap |  | 138 | JWM
5.23 | MV | 1395 | Moss-Cat-Hallock |  | 138 | JWM
39 | BG | 4591 | Mount Vernon West-Xenia |  | 345 | JP | [9 empty] | 0 | 39 | [9 empty] | 1 |  | 1 | 2
4.43 | BY | 1462A | Mount Zion PPG-Sub Tap |  | 138 | JC | [20 empty] | 1 | 1
2.36 | BZ | 1574 | Mount Zion Route 121-Mount Zion PPG |  | 138 | JC | [10 empty] | 2 | [9 empty] | 2 | 1
3.37 | AN |  | Moweaqua North-Sub Tap |  | 138 | JC | [21 empty] | 1
12.55 | CD | 1462B | Mt. Auburn-Sub Tap |  | 138 | JC | [20 empty] | 1
3.14 | HH |  | Mt. Vernon 42nd St.-Mt. Vernon West (Structure 763 to MT Vernon IP sub) |  | 138 | JP | [9 empty] | 0 | 3
40.8 | SS |  | Murdock-Mattoon |  | 138 | JC | [10 empty] | 41 | [12 empty] | 2
15.46 | Z |  | Murdock-Sidney |  | 138 | JC
4.35 | AT |  | N. Marblehead-Quincy, 3rd & Jefferson |  | 138 | JWM | [10 empty] | 5
13.36 | QQ |  | Neoga-Effingham |  | 138 | JC | [22 empty] | 1
12 | MS | 1318 | New Holland-Kickapoo |  | 138 | JWM | [10 empty] | 12 | [9 empty] | 1
34.32 | YY |  | Newton-Robinson |  | 138 | JC | [23 empty] | 3
20.79 | CV | 4583 | Newton-Tanner-4583 |  | 345 | JC | [20 empty] | 1 | 3 | 1
23.14 | AM |  | Norris City North-Muddy |  | 138 | JP | [20 empty] | 1 | 1 | 1
1.93 | TC | 1604 | North 27th Street Decatur-ADM North |  | 138 | JC | [20 empty] | 1 | 1
2.54 | CF | 1522A | North 27th Street Decatur-Sub Tap |  | 138 | JC | [20 empty] | 1 | 1
16.55 | RM | 1386 | North Champaign-Sidney |  | 138 | JC | [20 empty] | 1 | 1 | 2
17.5 | SC | 1476 | North Coulterville-Steeleville |  | 138 | JP | [9 empty] | 0 | 17 | [9 empty] | 1 | 2
0.47 | EU | 2303 | North Coulterville-Sub Tap |  | 345 | TS
24.12 | RD | 1342 | North Decatur - Docket |  | 138 | JWM | [22 empty] | 1
2.67 | SJ | 1522 | North Decatur-East Main Street |  | 138 | JC | [10 empty] | 3 | [9 empty] | 1
16.9 | CG | 1350 | North Decatur-Latham - 1350 |  | 138 | JWM | [20 empty] | 1
14.99 | ST | 1566 | North Decatur-Latham - 1566 |  | 138 | JWM | [10 empty] | 15 | [10 empty] | 1
2.18 | TB | 1602 | North Decatur-North 27th Street Decatur |  | 138 | JC | [10 empty] | 2 | [5 empty] | 1
10.51 | DI | 1556A | North LaSalle-Sub Tap |  | 138 | JWM | [23 empty] | 1
22.93 | RW | 1446 | North Staunton-Midway |  | 138 | TS | [20 empty] | 1 |  |  | 1
3.89 | SG | 1496 | Oglesby-LaSalle |  | 138 | JWM | [23 empty] | 1
16.4 | CI | 1516B | Oglesby-Ottawa |  | 138 | JWM
28.01 | AK |  | Olney North-Albion South |  | 138 | JP | [9 empty] | 0 | 28 | [9 empty] | 2
3.24 | TD | 1606 | Oreana-ADM North - 1606 |  | 138 | JC | [20 empty] | 1 | 1
3.93 | TF | 1610 | Oreana-ADM North - 1610 |  | 138 | JC | [20 empty] | 1 | 1
8.49 | ZN | 4571A /4545A | Oreana-Sub Tap |  | 345 | JC
9.1 | NE | 1652 | Ottawa-Fox River |  | 138 | JWM
1.89 | B |  | Palmyra-N. Marblehead |  | 161 | JWM
18.43 | JJ | 1408 | Pana North-Ramsey East |  | 138 | JC | [22 empty] | 1 | 2
33.6 | JC | 4553 | Pana-Austin | ITC | 345 | TS
31.8 | SA | 1466 | Pana-Midway |  | 138 | TS | [20 empty] | 1 | 3 | 1
34.2 | P |  | Pana-Neoga South |  | 138 | JC
1.34 | ZE | 1390 | Pana-Pana North - 1390 |  | 138 | JC
33.49 | RZ | 1462 | Pana-Route 51 Decatur |  | 138 | JC | [21 empty] | 1
11.7 | Q | 1549 | Pana-Taylorville South |  | 138 | TS | [20 empty] | 1
1.27 | ZF | 1423 | Pawnee West-Austin |  | 138 | TS | [20 empty] | 1
18 | S |  | Pawnee West-Taylorville South |  | 138 | TS | [9 empty] | 0 | 18 | [9 empty] | 1
16.79 | CC |  | Paxton East-Gibson City South |  | 138 | JC | [23 empty] | 1
22.13 | AP |  | Paxton East-Gilman |  | 138 | JC | [22 empty] | 2
| DR |  | Pinckneyville - Pinckneyville-2 |  | 138 | JP
3.75 | DF |  | Pioneer-Hines |  | 138 | JWM | [20 empty] | 2 | 1 | 2
4.38 | RU | 1434 | Porter Rd-E Belleville |  | 138 | TS | [20 empty] | 1
7.22 | LC | 4552 | Prairie State-Aster |  | 345 | JP | [9 empty] | 0 | 7
39.43 | TQ | 4541 | Prairie State-Mount Vernon West-4541 |  | 345 | JP | [20 empty] | 0 | 1 |  | 1
46.29 | TO | 4531 | Prairie State-Stallings |  | 345 | TS | [20 empty] | 1 | 1 |  | 1
16.46 | CJ | 1552B | Princeton-Sub Tap |  | 138 | JWM | [23 empty] | 2
4.6 | AS |  | Quincy South-N. Marblehead |  | 138 | JWM
30.45 | AY | 4509 | Ramsey East-Neoga South |  | 345 | JC | [22 empty] | 2
16.5 | BB |  | Rantoul-Rising |  | 138 | JC
6.9 | ZO |  | Rantoul-Sub Tap |  | 138 | JC | [21 empty] | 1 |  | 1
0 | ZP | 1642 | Rising-Bondville |  | 138 | JC
9.02 | SZ | 1592 | Rising-N. Champaign |  | 138 | JC
0 | ZR |  | Robinson Marathon North-Sub Tap |  | 138 | JC
0.25 | ZQ |  | Robinson Marathon-Robinson Marathon North |  | 138 | JC
28.24 | E |  | Roodhouse West-Jerseyville Northwest |  | 138 | TS | [9 empty] | 0 | 28 | [11 empty] | 3
1 | ZX |  | Roxford-Wood River Refinery-2 (SOUTH LINE TO CONOCO) |  | 138 | TS
29.67 | ZY | 4585 | Rush Island-Baldwin |  | 345 | TS | [9 empty] | 0 | 29 | [9 empty] | 1
8.34 | SY | 1586 | S. Belleville-Centerville |  | 138 | TS | [21 empty] | 1 | 1 | 1
4.93 | SR | 1562 | S. Bloomington-Brokaw |  | 138 | JWM
5.63 | TA | 1596 | S. Bloomington-Brokaw 1596 |  | 138 | JWM | [10 empty] | 6
23.01 | RJ | 1372 | S. Bloomington-Clinton Rt. 54 |  | 138 | JC | [20 empty] | 1 |  | 2
7.28 | RC | 1544 | S. Bloomington-McLean |  | 138 | JWM | [23 empty] | 1
5.58 | RH | 1334 | S. Bloomington-W. Washington |  | 138 | JWM | [23 empty] | 3
0.2 | RI | 1614 | Sandburg-E Galesburg |  | 138 | JWM
32.13 | RI | 1366 | Sandburg-East Kewanee |  | 138 | JWM | [10 empty] | 33
44.13 | ZB | 4547 | Sandburg-Fargo | ITC | 345 | JWM
8.63 | RN | 1392 | Sandburg-Galesburg Monmouth Blvd |  | 138 | JWM | [22 empty] | 1
5.75 | CK | 1380 | Schram City-Sub Tap |  | 138 | TS | [22 empty] | 1
7.6 | AO |  | Shawnee-Joppa-1 |  | 345 | JP | [20 empty] | 1 | 4
51.96 | BD | 4565 | Shawnee-West Frankfort East |  | 345 | JP | [20 empty] | 1 | 3 | 4 | 2
6.64 | CM | 1704 | Shockey-Gillett |  | 138 | JWM
31.3 | TK | 4501 | Sidney-Eugene |  | 345 | JC | [20 empty] | 1 |  |  | 1
35.19 | TN | 4525 | Sidney-Kansas |  | 345 | JC | [20 empty] | 1 | 1
31.4 | AA | 1524 | Sidney-Paxton East |  | 138 | JC | [23 empty] | 1
24.25 | NI | 4567 | Sidney-Rising | ITC | 345 | JC
14.64 | RA | 1312 | Sidney-SW Campus |  | 138 | JC | [21 empty] | 1
0.5 | CL |  | Sioux-Roxford 1 & 2 - IL |  | 345 | TS | [9 empty] | 0 | 1
87.43 | X |  | Sioux-South Quincy - 4 |  | 138 | TS | [9 empty] | 87 | [10 empty] | 1 |  | 1 | 1
36.77 | SK | 1526 | South Belleville-Tilden |  | 138 | TS | [20 empty] | 1 |  | 1 | 1
15.8 | SO | 1546 | South Centralia-Mount Vernon West |  | 138 | JP | [20 empty] | 1 | 1 | 1
6.48 | CN |  | South Quincy-East Quincy - 4 |  | 138 | JWM | [10 empty] | 7
2.34 | CO | 1476C | Sparta-Sub Tap |  | 138 | JP | [9 empty] | 0 | 2
8.6 | RS | 1426 | Stallings-East Collinsville |  | 138 | TS | [20 empty] | 1 | 1 | 1 | 1
8.54 | TW | 4581 | Stallings-Roxford |  | 345 | TS | [9 empty] | 0 | 8
27.93 | WW | 1636 | Steeleville-Grand Tower |  | 138 | JP | [9 empty] | 28 | [10 empty] | 2 | 2 | 2 | 1
34 | ZS | 4512 | Sugar Creek-Kansas | ITC | 345 | JC
22.5 | BU | 1615 | Tanner - Jasper |  | 138 | JC | [10 empty] | 22 | [9 empty] | 1 |  | 1
0.08 | DX | 1599 | Tanner - Louisville S. |  | 138 | JC
20.49 | N | 1553 | Tanner - Newton -1553 |  | 138 | JC | [16 empty] | 1
4.44 | DY | 4526 | Tanner - Xenia |  | 345 | JP
8.45 | R |  | Taylorville South-Taylorville Northeast |  | 138 | TS |  | 8 | [18 empty] | 2 | 5 | 1
12 | MG | 1353 | Tazewell-E Peoria |  | 138 | JWM | [21 empty] | 1 | 2
61.75 | MT | 1367 | Tazewell-E. Springfield |  | 138 | JWM | [16 empty] | 1 |  | 1 |  | 1 |  | 2 | 1
9.88 | MH | 1354 | Tazewell-Eastern |  | 138 | JWM | [20 empty] | 1
0.64 | NB | 4521 | Tazewell-Powerton (C.E.) |  | 345 | JWM
8.58 | CP | 1342C | Turris Coal-Sub Tap-1342A |  | 138 | JWM
10 | ZU | 1302A | Valmeyer-Sub Tap |  | 138 | TS | [20 empty] | 1
1 | CQ |  | Venice-Campbell - 1 (Partially Paralleled Circuits) |  | 138 | TS
1 | BW |  | Venice-Campbell - 2 |  | 138 | TS
3.37 | DG | 1359 | Venice-Madison Industrial |  | 138 | TS | [21 empty] | 1
5 | CR |  | Venice-Ridge - 4 |  | 138 | TS
0.27 |  |  | Venice-Venice Peaker #3 & #4 |  | 138 | TS
0.33 |  |  | Venice-Venice Peaker North |  | 138 | TS | [20 empty] | 1
26.8 | RO | 1396 | Vermilion-N. Champaign |  | 138 | JC | [10 empty] | 27 | [10 empty] | 2
11.44 | SU | 1572 | Vermilion-Tilton Energy Center |  | 138 | JC | [16 empty] | 1 |  |  |  |  | 2 |  | 1
12.8 | HA |  | Virden-Austin |  | 138 | TS
36.25 | TU | 4561 | W Frankfort East-Mt. Vernon West |  | 345 | JP | [20 empty] | 1 | 1 | 1 | 1
11.29 | AH |  | W. Frankfort East-Herrin East |  | 138 | JP | [9 empty] | 0 | 11 | [9 empty] | 1 | 1 | 1
20.2 | M |  | W. Frankfort East-Muddy |  | 138 | JP | [22 empty] | 1
33.1 | BJ |  | W. Frankfort East-Norris City North |  | 345 | JP | [20 empty] | 3 |  | 1 | 2
|  |  | W. Frankfort-Joppa |  |  | JP
5.25 | L |  | W. Frankfort-W. Frankfort East |  | 138 | JP | [21 empty] | 0 | 1 | 1
1.28 | BP | 1356 | Wallace-E. Peoria |  | 138 | JWM
3.27 | MW | 1396 | Wallace-Keystone |  | 138 | JWM
11.5 | MC | 1344 | Wallace-Spring Bay |  | 138 | JWM | [10 empty] | 12 | [9 empty] | 1 |  | 1 | 1
3.72 | CS | 1322A | Waltonville Sub Tap |  | 138 | JP | [21 empty] | 1 | 2
14.55 | AQ |  | Watseka-Goodland |  | 138 | JC | [16 empty] | 1 | [5 empty] | 1 | 1
0.25 | CT | 1312A | Windsor Road Sub Tap |  | 138 | JC
14.13 | RX | 1452 | Wood River-Madison Industrial |  | 138 | TS | [21 empty] | 1 | 2 | 3
25.46 | RV | 1436 | Wood River-North Staunton |  | 138 | TS | [20 empty] | 1 | 5 | 1 | 1
4.07 | SH | 1506 | Wood River-Roxford |  | 138 | TS
6.36 | CU | 1502 | Wood River-Roxford (NORTH LINE TO CONOCO) |  | 138 | TS
17.84 | RY | 1456 | Wood River-Stallings |  | 138 | TS | [20 empty] | 1 | 2 |  | 1
10.82 | CW | 1570 | Woodhall-Hallock |  | 138 | JWM
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [5 empty] | Totals | 48 | 89 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 191 | 1016 | 0 | 0 | 29 | 0 | 0 | 8 | 1 | 1 | 0 | 120 | 141 | 121 | 103 | 0 | 0 | 0
[29 empty] | 1Q | 176
[29 empty] | 2Q | 451
Radial Tap | [28 empty] | 3Q | 1206
[29 empty] | 4Q | 103
1936
5018.61 | [6 empty] | 48 | 89 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 191 | 1016 | 0 | 0 | 29 | 0 | 0 | 8 | 1 | 1 | 0 | 120 | 141 | 121
[31 empty] | 0 | 0 | 0
Note on AB5: Cox, Jeremy J: work identifeied on 3q patrol
Note on AB6: Cox, Jeremy J: work identified on 3q patrol
Note on AB7: Cox, Jeremy J: work identified on 3q patrol
Note on AB8: Part, Jesse: Work identified on 2023 patrol.
Note on D9: Henderson, Michelle: Upgraded voltage for 2024 to 345kv from 138kv
Note on AB9: Part, Jesse: Work identified on 2023 patrol.
Note on AC10: Strauss, Anthony D: Non priority work left over from 2023 patrol
Note on D11: Henderson, Michelle: For 2024: Ashley-WFRK will now stop at Jordan and be ASHL-JORD-1536
Note on AC11: Part, Jesse: Work identified on 2023 patrol.
Note on AD11: Part, Jesse: Work identified on 2024 patrol.
Note on AE11: Part, Jesse: Work identified on 2024 patrol.
Note on Q12: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AD12: Part, Jesse: Work identified on 2024 patrol.
Note on AC13: Mohr, Jeremy W: priority work
Note on AD13: Mohr, Jeremy W: work identified on 2024 patrol
Note on AC14: Mohr, Jeremy W: priority work
Note on AB16: Strauss, Anthony D: work identified on 2023 patrol
Note on AC16: Strauss, Anthony D: Priority work found on 2024 patrol
Note on AB17: Cox, Jeremy J: work identified on 3q patrol
Note on AD17: Cox, Jeremy J: work identified on 2024 patrols
Note on AE20: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AC23: Strauss, Anthony D: priority work found on 2024 patrol
Note on AC24: Strauss, Anthony D: Priority work found on 2024 patrol
Note on AD24: Strauss, Anthony D: work identified on 2024 patrol
Note on AE24: Strauss, Anthony D: work identified on 2024 patrol
Note on AB25: Strauss, Anthony D: Capital Project at turkey hill sub
Note on AC25: Strauss, Anthony D: non priority work left over from 2023 patrol and Capital project
Note on AD25: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AB26: Strauss, Anthony D: Work completed due to proximity of crew.
Note on Q27: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AC27: Part, Jesse: Work identified on 2023 patrol.
Note on AD27: Part, Jesse: Work identified on 2024 patrol.
Note on AE27: Part, Jesse: Work identified on 2024 patrol.
Note on D28: Henderson, Michelle: For 2024: Benton-WFRK will be divided into Benton-Jordan and Jordan-WFRK
Note on Q28: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AD28: Part, Jesse: Work identified on 2024 patrol.
Note on AE28: Part, Jesse: Work identified on 2024 patrol.
Note on AB37: Strauss, Anthony D: work identified on 2023 patrol
Note on AD37: Strauss, Anthony D: work identified on 2024 patrol
Note on AC39: Strauss, Anthony D: non priority work left over form 2023 patrol
Note on R40: Strauss, Anthony D: q2 work moved to q3 due to crew avialability
Note on R41: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AD42: Strauss, Anthony D: work identified on 2024 patrol
Note on AB43: Strauss, Anthony D: work identified on 2023 patrol
Note on AC43: Strauss, Anthony D: non priority work left over from 2023 patrol
Note on R44: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on R45: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AC46: Strauss, Anthony D: non priority work left over from 2023 patrol
Note on AD48: Part, Jesse: Work identified on 2024 patrol.
Note on AE48: Part, Jesse: Work identified on 2024 patrol.
Note on D49: Henderson, Michelle: Carbondale - WFRK is being divided into CDNE-JORD & JORD-WFRK-1713
Note on AE49: Part, Jesse: Work ISO construction project.
Note on AC51: Cox, Jeremy J: work identified on 2023 patrol
Note on AC52: Cox, Jeremy J: work identified on 2023 patrol
Note on D53: Henderson, Michelle: Changed name in 2024 from Casey-Breed to Casey-Sullivan
Note on AC53: Cox, Jeremy J: work identified on 2023 patrol
Note on AC54: Mohr, Jeremy W: work identified in 2024
Note on AD54: Mohr, Jeremy W: work identified on 2024 patrol
Note on AD55: Mohr, Jeremy W: work identified on 2024 patrol
Note on AE55: Mohr, Jeremy W: work identified on 2024 patrol
Note on AD56: Cox, Jeremy J: work identified on 2023 patrols
Note on AD57: Cox, Jeremy J: work identified on 2024 patrols
Note on U58: Cox, Jeremy J: helicopter cleanup
Note on X59: Cox, Jeremy J: Construction Clearing
Note on AD61: Cox, Jeremy J: work identified on 2024 patrols
Note on R63: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AD63: Strauss, Anthony D: work identified on 2024 patrol
Note on AE63: Strauss, Anthony D: work identified on 2024 patrol
Note on AB64: Strauss, Anthony D: Work identified on 2023 patrol
Note on AD64: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE64: Strauss, Anthony D: work identified on 2024 patrol
Note on AB65: Strauss, Anthony D: Diaz capital project
Note on AD65: Strauss, Anthony D: work identified on 2024 patrol, and Diaz sub construction clearing
Note on AE65: Strauss, Anthony D: Diaz construction project
Note on Q66: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AD66: Part, Jesse: Work identified on 2024 patrol.
Note on AE66: Part, Jesse: Work identified on 2024 patrol.
Note on D67: Henderson, Michelle: Line segment that goes from Pinckneyville sub to the new Commodore sub. Was part of PNKY-WFRK patrol. Updated for 2024
Note on D68: Henderson, Michelle: new line segment with 2 spans that goes from CMDR-PNKY. Added for 2024
Note on AB69: Part, Jesse: Work identified on 2023 patrol.
Note on AC69: Part, Jesse: Work identified on 2023 patrol.
Note on AD69: Part, Jesse: Work identified on 2024 patrol.
Note on AC70: Part, Jesse: Work identified on 2023 patrol.
Note on AE70: Part, Jesse: Mow work on the Harco Sub Tap (part of CRO-MUDY)
Note on D73: Henderson, Michelle: previously part of N. Decatur - Illiopolis
Note on AC74: Mohr, Jeremy W: hazard tree mitigation
Note on AE74: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB75: Mohr, Jeremy W: customer request
Note on AC75: Mohr, Jeremy W: hazard tree mitigation
Note on AD75: Mohr, Jeremy W: crop locked structure brush/LRTP access clearing
Note on AE75: Mohr, Jeremy W: LRTP access clearing
Note on AC77: Mohr, Jeremy W: moved to later in year to overlap construction
Note on AD77: Mohr, Jeremy W: City request to mow fee owned
Note on AC78: Strauss, Anthony D: priority work from 2023 patrol
Note on AD78: Strauss, Anthony D: priority work on 2024 patrol
Note on AE78: Strauss, Anthony D: work identified on 2024 patrol
Note on AC79: Strauss, Anthony D: non priority work from 2023 patrol
Note on AD79: Strauss, Anthony D: work identified on 2024 patrol
Note on AE79: Strauss, Anthony D: work identified on 2024 patrol
Note on AC80: Cox, Jeremy J: work identified on 2023 patrol
Note on AC81: Mohr, Jeremy W: moved to later in year to overlap constructio
Note on AD81: Mohr, Jeremy W: Construction access clearing
Note on AE81: Mohr, Jeremy W: Construction access
Note on AD82: Mohr, Jeremy W: work identified on 2024 patrol
Note on AD83: Mohr, Jeremy W: Fee owned clearing in Leeve District- Kevin B
Note on AB85: Mohr, Jeremy W: customer request
Note on AC85: Mohr, Jeremy W: structures cleared given access options
Note on AB86: Mohr, Jeremy W: Trees were removed by landowner
Note on AE86: Mohr, Jeremy W: Shotgun deer season work
Note on AD87: Cox, Jeremy J: work identified on 2023 patrols
Note on AE91: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB92: Mohr, Jeremy W: construction work
Note on AC92: Mohr, Jeremy W: work under city permit to along bike trail
Note on AD92: Mohr, Jeremy W: work identified on 2024 patroll
Note on AE92: Mohr, Jeremy W: PCRP easement clearing
Note on AE93: Strauss, Anthony D: work identified on 2024 patrol
Note on AB95: Mohr, Jeremy W: construction work
Note on D96: Henderson, Michelle: new line Dec 2023
Note on AC98: Strauss, Anthony D: priority work from 2024 patrol
Note on AD98: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AD100: Cox, Jeremy J: work identified on 2024 patrols
Note on AB101: Part, Jesse: Work identified on 2023 patrol and work ISO construction project.
Note on AC101: Part, Jesse: Work identified on 2023 patrol, and work completed ISO construction project.
Note on AD101: Part, Jesse: Work completed ISO construction project.
Note on AB102: Part, Jesse: Work identified on 2023 patrol with some additional helicopter clean up work.
Note on AC102: Part, Jesse: Work identified on 2023 patrol.
Note on AD102: Part, Jesse: Work identified on 2024 patrol.
Note on AE102: Part, Jesse: Work identified on 2024 patrol.
Note on D104: Henderson, Michelle: previously part of N. Decatur - Illiopolis
Note on AB106: Mohr, Jeremy W: crew availability
Note on AC106: Mohr, Jeremy W: moved to 3rd QRT after progressive treats brush
Note on AD106: Mohr, Jeremy W: priority brush was control by Progressive
Note on AB108: Mohr, Jeremy W: Remainder scheduled for completion in April
Note on AB109: Mohr, Jeremy W: Work identified on patrol
Note on AB112: Mohr, Jeremy W: Construction work
Note on AC112: Mohr, Jeremy W: construction clearing per new design
Note on AE112: Mohr, Jeremy W: work identified on 2024 patrols
Note on AC117: Mohr, Jeremy W: work identified in 2024
Note on AD117: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB118: Cox, Jeremy J: work identified on 3q patrol
Note on AC119: Cox, Jeremy J: work identified on 2023 patrol
Note on AE119: Cox, Jeremy J: work identified on 2024 patrol
Note on D122: Henderson, Michelle: changing name from Huts-Robinson to Huts-Heath in 2024
Note on AB123: Cox, Jeremy J: work identified on 3q patrol
Note on AC124: Cox, Jeremy J: work identified on 2023 patrol
Note on Q125: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AC125: Part, Jesse: Work identified on 2023 patrol.
Note on AD126: Mohr, Jeremy W: work identified on 2024 patrol
Note on AE126: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB127: Mohr, Jeremy W: Crew availability
Note on D134: Henderson, Michelle: added as new line for 2024 - 2 lines run together (1706 & 1728) but will be patrolled as 1728
Note on AB135: Strauss, Anthony D: work identified on 2023 patrol
Note on AC135: Strauss, Anthony D: cleanup from helicopter trim
Note on Q137: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB137: Part, Jesse: Work identified on 2023 patrol.
Note on AC137: Part, Jesse: Work identified on 2023 patrol.
Note on AD137: Part, Jesse: Work identified on 2023 patrol.
Note on AE137: Part, Jesse: Work identified on 2023 patrol.
Note on AB138: Part, Jesse: Work identified on 2023 patrol.
Note on AE138: Part, Jesse: Work identified on 2024 patrol.
Note on D139: Henderson, Michelle: PNKY-WFRK will be renamed for 2024 and will now be Jordan-Commodore-4586 and is upgraded to 345kv from 230kv
Note on AC139: Part, Jesse: Work identified on 2023 patrol.
Note on AD139: Part, Jesse: Work identified on 2023 patrol.
Note on AE139: Part, Jesse: Work identified on 2024 patrol.
Note on D140: Henderson, Michelle: new for 2024: JORD-MASS was partly PNKY-WFRK and mostly WFRK-JOPA, now renamed to reflect the rebuild and upgrade to 345kv
Note on AC140: Part, Jesse: Work identified on 2023 patrol.
Note on AD140: Part, Jesse: Work identified on 2023 patrol and ISO construction project.
Note on AE140: Part, Jesse: Work identified on 2024 patrol.
Note on D141: Henderson, Michelle: Used to be part of Benton NW -WFRK
Note on Q141: Part, Jesse: Pushed to Q3 due to crew availability.
Note on D142: Henderson, Michelle: Used to be part of Carbondale - W. Frankfort
Note on X144: Cox, Jeremy J: Construction Clearing
Note on AB145: Cox, Jeremy J: work identified on 3q patrol
Note on AE146: Cox, Jeremy J: work identified on 2024 patrol
Note on AD147: Mohr, Jeremy W: work identified on 2024 patrol
Note on AE147: Mohr, Jeremy W: work identified on 2024 patrol, crop locked brush
Note on AB148: Mohr, Jeremy W: construction work
Note on AD148: Mohr, Jeremy W: Construction access clearing
Note on AD149: Cox, Jeremy J: work identified on 2024 patrols
Note on Q150: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB150: Part, Jesse: Work identified on 2023 patrol.
Note on AC150: Part, Jesse: Work identified on 2023 patrol.
Note on AD150: Part, Jesse: Work identified on 2024 patrol.
Note on AB151: Cox, Jeremy J: work identified on 3q patrol
Note on AD151: Cox, Jeremy J: work identified on 2023 patrols
Note on D153: Henderson, Michelle: new line purchased from CWLP - goes from Lanesville Sub to str 140 on Greenback- W. Illiopolis. Added for 2024
Note on D156: Henderson, Michelle: Changed name in 2024 from Lawrenceville - Olney to Lawrenceville-Jasper-1677
Note on AB157: Cox, Jeremy J: wowrk identified on 3q patrol
Note on AD157: Cox, Jeremy J: work identified on 2024 patrols
Note on AE157: Cox, Jeremy J: work identified on 2024 patrol
Note on AC159: Strauss, Anthony D: priority work from 2024 patrol
Note on AD159: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE159: Strauss, Anthony D: work identified on 2024 patrol
Note on AE162: Mohr, Jeremy W: work identified on 2024 patrol
Note on AC163: Strauss, Anthony D: non priority work from 2023 patrol
Note on AB166: Mohr, Jeremy W: customer request
Note on AC166: Mohr, Jeremy W: used jarraff to trim crop locked backyard trees
Note on AE166: Mohr, Jeremy W: Deer season work for Intren, worked on a customer call in
Note on Q167: Part, Jesse: Pushed to Q3 due to crew availability.
Note on X167: Part, Jesse: Continued reclamation
Note on AC168: Part, Jesse: Work identified on 2023 patrol.
Note on AD168: Part, Jesse: Work identified on 2024 patrol.
Note on D171: Henderson, Michelle: Divided Joppa-Marion into Marion-Massac-7163 and Massac-Joppa-7174
Note on AB171: Part, Jesse: Work identified on 2023 patrol.
Note on AC171: Part, Jesse: Work identified on 2023 patrol.
Note on AD171: Part, Jesse: Work identified on 2024 patrol.
Note on AE171: Part, Jesse: Work identified on 2024 patrol.
Note on D172: Henderson, Michelle: new for 2024. Previously part of the Marion - Joppa line
Note on D173: Henderson, Michelle: new 161 kv line for 2024. Runs in the old corridor for JOPA-WFRK 230kv
Note on AB174: Cox, Jeremy J: work identified on 3q patrol
Note on AE174: Cox, Jeremy J: work identified on 2024 patrol
Note on X177: Mohr, Jeremy W: Customer cleared priority trees, REC moved to 2nd QRT
Note on AC177: Mohr, Jeremy W: priority trees trimmed after customer did not sign REC easement
Note on AC178: Mohr, Jeremy W: hazard tree mitigation
Note on R179: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AB179: Strauss, Anthony D: work completed due to proximity of crew.
Note on AC179: Strauss, Anthony D: helicopter clean up
Note on AE179: Strauss, Anthony D: work identified on 2024 patrol
Note on AB181: Mohr, Jeremy W: work completed in 2023
Note on AC183: Mohr, Jeremy W: hazard tree mitigation
Note on AE183: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB185: Part, Jesse: Work identified on 2023 patrol.
Note on AC185: Part, Jesse: Work identified on 2023 patrol.
Note on Q191: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB191: Part, Jesse: Work identified on 2023 patrol.
Note on AD191: Part, Jesse: Work identified on 2023 patrol.
Note on AE191: Part, Jesse: Mowing for construction project.
Note on AB192: Cox, Jeremy J: work identified on 3q patrol
Note on AC192: Cox, Jeremy J: work identified on 2023 patrol
Note on AC193: Cox, Jeremy J: work identified on 2023 patrol
Note on AC194: Cox, Jeremy J: work identified on 2023 patrol
Note on AB195: Cox, Jeremy J: work identified on 3q patrol
Note on Q196: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AE197: Cox, Jeremy J: work identified on 2024 patrol
Note on AD200: Cox, Jeremy J: work identified on 2023 patrols
Note on AB201: Mohr, Jeremy W: work identified on patrol
Note on AE202: Cox, Jeremy J: work identified on 2024 patrol
Note on D203: Henderson, Michelle: Newton-Xenia 345kv is being split into 2 lines in 2024: Newton-Tanner-4583 and Tanner-Xenia-4526
Note on AB203: Cox, Jeremy J: work identified on 3q patrol
Note on AC203: Cox, Jeremy J: work identified on 2023 patrol
Note on AD203: Cox, Jeremy J: work identified on 2023 patrols
Note on AB204: Part, Jesse: Work identified on 2023 patrol.
Note on AC204: Part, Jesse: Work identified on 2023 patrol.
Note on AD204: Part, Jesse: Work identified on 2024 patrol.
Note on AC205: Cox, Jeremy J: work identified on 2023 patrol
Note on AC206: Cox, Jeremy J: work identified on 2023 patrol
Note on AB207: Cox, Jeremy J: work identified on 3q patrol
Note on AC207: Cox, Jeremy J: work identified on 2023 patrol
Note on AD207: Cox, Jeremy J: work identified on 2023 patrols
Note on Q208: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB208: Part, Jesse: Work identified on 2023 patrol.
Note on AC208: Part, Jesse: Work identified on 2023 patrol.
Note on D210: Henderson, Michelle: N. Decatur - Illiopolis is now split into 3 segments for 2024: N. Decatur - Docket (NDEC- Latham-1342 & Latham-Docket 1409), Docket-Greenback, and Greenback - W. Illiopolis
Note on AD210: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB211: Cox, Jeremy J: work identified on 3q patrol
Note on AB212: Mohr, Jeremy W: work identifed on patrol
Note on AC213: Mohr, Jeremy W: priority work
Note on X214: Cox, Jeremy J: Construction Clearing
Note on AE215: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB216: Strauss, Anthony D: Work identified on 2023 patrol
Note on AE216: Strauss, Anthony D: work identified on 2024 patrol
Note on AE217: Mohr, Jeremy W: work identified on 2024 patrol
Note on Q219: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB219: Part, Jesse: Work identified on 2023 patrol.
Note on AC220: Cox, Jeremy J: work identified on 2023 patrol
Note on AC221: Cox, Jeremy J: work identified on 2023 patrol
Note on AD225: Cox, Jeremy J: work identified on 2024 patrols
Note on AE225: Cox, Jeremy J: work identified on 2024 patrol
Note on AB227: Strauss, Anthony D: Work identified on 2023 patrol
Note on AC227: Strauss, Anthony D: priority work from 2024 patrol
Note on AD227: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AC230: Cox, Jeremy J: work identified on 2023 patrol
Note on AB231: Strauss, Anthony D: work identified on 2023 patrol
Note on AB232: Strauss, Anthony D: Work identified on 2023 patrol
Note on R233: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AB233: Strauss, Anthony D: work identified on 2023 patrol
Note on AE234: Cox, Jeremy J: work identified on 2024 patrol
Note on AD235: Cox, Jeremy J: work identified on 2024 patrols
Note on D236: Henderson, Michelle: new for 2024: short line segment from PNKY sub to PNKY CTG sub.
Note on AB237: Mohr, Jeremy W: worked with City to complete work on their property
Note on AC237: Mohr, Jeremy W: Pioneer sub exspansioin clearing
Note on AD237: Mohr, Jeremy W: Mowing along bike trail
Note on Q239: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB240: Part, Jesse: Pushed work to Q2 because this is a newly-acquired line and my ground patrol was scheduled for late Q1.
Note on AE240: Part, Jesse: Work identified on 2024 patrol.
Note on AB241: Strauss, Anthony D: Work identified on 2023 patrol
Note on AC241: Strauss, Anthony D: non priority work from 2023 patrol
Note on AE241: Strauss, Anthony D: work identified on 2024 patrol
Note on AE242: Mohr, Jeremy W: work identified on 2024 patrol
Note on AD244: Cox, Jeremy J: work identified on 2024 patrols
Note on AC246: Cox, Jeremy J: work identified on 2023 patrol
Note on AE246: Cox, Jeremy J: work identified on 2024 patrol
Note on D247: Henderson, Michelle: Runs entirely in a corridor with Sidney-Rising 345kv and does not get patrolled separately
Note on D249: Henderson, Michelle: Will be removed as a patrol for 2024 - it is now part of the Hutsonville - Heath patrol
Note on R251: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AD251: Strauss, Anthony D: priority work identified on 2024 patrol
Note on R253: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on AB253: Strauss, Anthony D: Rush Island Tower Lights Capital project
Note on AC254: Strauss, Anthony D: work from 2023 patrol
Note on AD254: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE254: Strauss, Anthony D: Goalby Construction project
Note on AB257: Cox, Jeremy J: work identified on 3q patrol
Note on AD257: Cox, Jeremy J: work identified on 2023 patrols
Note on AE258: Mohr, Jeremy W: work identified on 2024 patrol
Note on AE259: Mohr, Jeremy W: crop locked brush identified on 2024 patrol
Note on AD263: Mohr, Jeremy W: Construction clearing around substation
Note on AD264: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AB265: Part, Jesse: Work completed ISO a construction project.
Note on AC265: Part, Jesse: Work identified on 2023 patrol and work completed ISO a construction project.
Note on AB266: Part, Jesse: Priority work identified on 2023 patrol.
Note on AC266: Part, Jesse: Work identified on 2023 patrol.
Note on AD266: Part, Jesse: Work identified on 2024 patrol and ISO construction project.
Note on AE266: Part, Jesse: Work identified on 2024 patrol and ISO construction project.
Note on AB268: Cox, Jeremy J: work identified on 4q patrol
Note on AE268: Cox, Jeremy J: work identified on 2024 patrol
Note on AB269: Cox, Jeremy J: work identified on 1q patrol
Note on AC269: Cox, Jeremy J: work identified on 2023 patrol
Note on AE270: Cox, Jeremy J: work identified on 2024 patrol
Note on AC272: Cox, Jeremy J: work identified on 2023 patrol
Note on R273: Strauss, Anthony D: Q2 work moved to Q3 due to crew availability
Note on AB274: Strauss, Anthony D: work left over from last year.
Note on AD274: Strauss, Anthony D: non priority work completed due to availability of equipment
Note on AE274: Strauss, Anthony D: Sioux - Meppen - Hull construction project
Note on AB275: Strauss, Anthony D: work identified on 2023 patrol
Note on AD275: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE275: Strauss, Anthony D: work identified on 2024 patrol
Note on AB276: Part, Jesse: Priority work idenified on 2023 patrol.
Note on AC276: Part, Jesse: Work identified on 2023 patrol.
Note on AD276: Part, Jesse: Work identified on 2024 patrol.
Note on Q278: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AB279: Strauss, Anthony D: Work identified on 2023 patrol
Note on AC279: Strauss, Anthony D: work from 2024 patrol
Note on AD279: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE279: Strauss, Anthony D: work identified on 2024 patrol
Note on R280: Strauss, Anthony D: q2 work moved to q3 due to crew availability
Note on Q281: Part, Jesse: Was ground sprayed in 2022, but the Shawnee National Forest sections were skipped. Would like to ground spray those if allowed now that we have mowed in 2023. UPDATE: Forest Service property was not sprayed because there was not a USFS agreement in place at time of vendor's presence on Ameren property.
Note on AB281: Part, Jesse: Work identified on 2023 patrol.
Note on AC281: Part, Jesse: Work identified on 2023 patrol.
Note on AD281: Part, Jesse: Work identified on 2024 patrol.
Note on AE281: Part, Jesse: Work identified on 2024 patrol.
Note on D283: Henderson, Michelle: Was Louisville - Olney. Will be renamed Tanner -Jasper for 2024 as it now does not go into either Louisville or Olney
Note on AB283: Cox, Jeremy J: work identified on 3q patrol
Note on AD283: Cox, Jeremy J: work identified on 2024 patrols
Note on D284: Henderson, Michelle: new line segment for 2024 that only goes from Tanner Sub - Louisville Sub.
Note on D285: Henderson, Michelle: changed from Louisville-Newton for 2024 - it goes into Tanner now instead of Louisville
Note on X285: Cox, Jeremy J: Construction Clearing
Note on D286: Henderson, Michelle: Was previously part of Newton-Xenia 345. Now split into Newton-Tanner and Tanner-Xenia
Note on AB287: Strauss, Anthony D: work identified on 2023 patrol
Note on AC287: Strauss, Anthony D: helicopter follow up crew
Note on AD287: Strauss, Anthony D: helicopter crew clean up
Note on AC288: Mohr, Jeremy W: east peoria bike trail
Note on AD288: Mohr, Jeremy W: work identified on 2024 patrol
Note on Z289: Mohr, Jeremy W: additional REC work completed
Note on AD289: Mohr, Jeremy W: work identified on 2024 patrol
Note on AE289: Mohr, Jeremy W: work identified on 2024 patrol
Note on AB293: Strauss, Anthony D: Victor Sub construction project.
Note on AC296: Strauss, Anthony D: work from 2023 patrol
Note on B298: Paries, Dieter E: Ameren Property
Note on B299: Paries, Dieter E: Ameren Property
Note on AC300: Cox, Jeremy J: work identified on 2023 patrol
Note on X301: Cox, Jeremy J: Construction clearing
Note on AC301: Cox, Jeremy J: work identified on 2023 patrol
Note on AE301: Cox, Jeremy J: new easements for construction project
Note on AB303: Part, Jesse: Work identified on 2023 patrol.
Note on AC303: Part, Jesse: Work identified on 2023 patrol.
Note on AD303: Part, Jesse: Work identified on 2024 patrol.
Note on AE303: Part, Jesse: Work identified on 2024 patrol.
Note on Q304: Part, Jesse: Pushed to Q3 due to crew availability.
Note on AC304: Part, Jesse: Work identified on 2023 patrol.
Note on AD304: Part, Jesse: Work identified on 2024 patrol.
Note on AD305: Part, Jesse: Work identified on 2024 patrol.
Note on AB306: Part, Jesse: Work identified on 2023 patrol.
Note on AD306: Part, Jesse: Work identified on 2024 patrol.
Note on AE306: Part, Jesse: Work identified on 2023 patrol.
Note on D307: Henderson, Michelle: WFRK-JOPA is being renamed for 2024 to JORD-MASS and the Alpha Code will go with the new name.
Note on AC308: Part, Jesse: Pushed to later in the year due to crew availability.
Note on AD308: Part, Jesse: Work pushed to Q4 due to crew availability.
Note on AE308: Part, Jesse: Worked pushed due to crew availability.
Note on AD311: Mohr, Jeremy W: REOS construction clearing
Note on AE311: Mohr, Jeremy W: Reos Construction clearing
Note on AC312: Part, Jesse: Work identified on 2023 patrol.
Note on AD312: Part, Jesse: Work identified on 2024 patrol.
Note on X313: Cox, Jeremy J: construction clearing
Note on AD313: Cox, Jeremy J: work identified on 2024 patrols
Note on AE313: Cox, Jeremy J: new easements for construction project
Note on AC315: Strauss, Anthony D: non priority work completed due to proximity of crews.
Note on AD315: Strauss, Anthony D: priority work completed on 2024 patrol
Note on AE315: Strauss, Anthony D: work identified on 2024 patrol
Note on AB316: Strauss, Anthony D: Work identified on 2023 patrol
Note on AC316: Strauss, Anthony D: work from 2024 patrol
Note on AD316: Strauss, Anthony D: priority work identified on 2024 patrol
Note on AE316: Strauss, Anthony D: work identified on 2024 patrol
Note on AC319: Strauss, Anthony D: work from 2023 patrol
Note on AE319: Strauss, Anthony D: work identified on 2024 patrl

## IL
IL - 2024 - Scheduled vs. Completed Work
Quarter | Scheduled Miles | Completed Miles | Percentage Completed
1 | 176 |  | 0%
2 | 451 |  | 0%
3 | 1206 |  | 0%
4 | 103 |  | 0%
Totals | 1936 | 0 | 0%