## Cover
Cover Page
Small Utility Rate Case Timeline
MO PSC Case No. WR-2025-0294
Utility Name & Contact Info | The Raytown Water Company
Contact Person | Chiki Thompson
Mailing Address | 10017 E. 63rd Street
Raytown, MO 64133
Phone Contact | (816)356-0333 Ext. 103
E-Mail Address | cthompson@raytownwater.net
Date Case Opened | August 6th, 2025
Local Public Hearing?
Agreement Filing Due Date | January 3rd, 2026
9-Month Deadline | May 6th, 2026
Set out on the following pages is the activities timeline pertaining to the processing of the above-referenced small utility revenue increase request. This timeline assumes that the Staff's investigation of the revenue increase request will result in a conclusion that an increase in the subject utility's operating revenues is needed, that at least the Utility and Staff will reach an agreement regarding the overall resolution of the request without the need for time extensions, and that the request will be resolved without an evidentiary hearing being held. In such instances where an evidentiary hearing will be held, the 9-month deadline will need to be considered in setting the procedural schedule.
The schedule set out in the timeline establishes the Target Due Date for the completion of certain activities needed to process the request in a timely manner. Extensions of the disposition agreement filing deadline, which is 150 days after the date the utility files its request, and certain other deadlines are allowed and if executed will result in changes to the timeline. Agreements for such extensions, which are limited to a maximum of 30 days, will be reduced to writing and filed in the case file, along with an updated timeline.
The entries in the Target Day column represent the number of days from the date the utility filed its request. The entries in the Target Due Date column show the date when the Target Day hits the calendar. To determine the entries for the Calendar Due Date column, Target Due Dates falling on a weekend or a holiday are moved to the next regular working day, except that the effective dates for pending revised tariff sheets cannot be adjusted.

## Days 0-75
Page 1 of 5 Pages
Target | Target | Calendar |  | Responsible
Day | Due Date | Due Date | Case Activity | "Party"
0 | 2025-08-06 | 2025-08-06 | Request Letter Filed and Case Opened (agreement filing due date calculated from this date) | Utility
5 | 2025-08-11 | 2025-08-11 | Compliance with Section (2)(A) of Rule Confirmed (case can be dismissed in case of non-compliance) | Case Manager
7 | 2025-08-13 | 2025-08-13 | Case Activities Timeline Filed in Case File | Case Manager
10 | 2025-08-16 | 2025-08-15 | Draft of Initial Customer Notice Sent to Utility & OPC, copy Consumer Services | Case Manager
20 | 2025-08-26 | 2025-08-26 | Requests for Information Needed for Audit Communicated to Utility by Assigned Staff and filed in EFIS | Assigned Staff
20 | 2025-08-26 | 2025-08-26 | Initial Customer Notice and Notice of Local Public Hearing Mailed to Customers and filed in EFIS | Utility
40 | 2025-09-15 | 2025-09-15 | Responses to Requests for Information Provided to Staff by Utility (staff provides copies of information received to OPC) OR Extension of Agreement Filing Due Date Agreed to by Utility OR Staff May File Motion to Dismiss Case | Utility & Assigned Staff
50 | 2025-09-25 | 2025-09-25 | End of Response Period for Initial Customer Notice | N/A
50 | 2025-09-25 | 2025-09-25 | Local Public Hearing(s) held no later than 60 days after case initiated | All Parties
75 | 2025-10-20 | 2025-10-20 | Deadline for Completion of Construction Projects to be Included in Case OR Agreement Filing Due Date Extended So Projects Can be Included in Case | Utility; Case Manager
These dates are working days that require a filing 'no later than' the date shown
Formulas:
Target = B7+[Target]
Calendar = [Target]
Calendar = [Target]-1

## Days 80-150
Page 2 of 5 Pages
Target | Target | Calendar |  | Responsible
Day | Due Date | Due Date | Case Activity | "Party"
80 | 2025-10-25 | 2025-10-24 | Basic Audit/Investigation Work Completed | Assigned Staff
85 | 2025-10-30 | 2025-10-30 | Initial Audit/Investigation Reports Completed and Provided to Case Manager | Assigned Staff
90 | 2025-11-04 | 2025-11-04 | Staff and OPC's Preliminary Audit/Investigation Results Provided to the Parties, including workpapers | Case Manager & OPC
100 | 2025-11-14 | 2025-11-14 | Utility & OPC Submit Responses Regarding Staff's Preliminary Report to Case Manager (errors/ommissions to be identified and suggested changes to be included) OR Staff Assumes Information Provided is Acceptable (Staff's audit considered "complete" at this time) | Utility & OPC
115 | 2025-11-29 | 2025-11-26 | Any necessary updates to Audit/Investigation Reports finalized and provided to Case Manager | Assigned Staff
120 | 2025-12-04 | 2025-12-04 | Staff's Settlement Proposal Sent to the parties and arrangements made for conference call or meeting to discuss the proposal | Case Manager
125 | 2025-12-09 | 2025-12-09 | Conference Call or Meeting Held with Utility & OPC to Discuss Staff's Settlement Proposal | Parties to the Case
130 | 2025-12-14 | 2025-12-12 | The Parties Notify Staff of Whether They Agree with the Settlement Proposal (if not, the reasons for that and suggested changes to the settlement proposal documents are provided to the Case Manager) | Parties to the Case
|  |  | Utility Must Respond OR Agree to Extension of Agreement Filing Due Date OR Staff May File Motion to Dismiss Case | Utility; Case Manager
140 | 2025-12-24 | 2025-12-24 | Agreed-Upon Changes to Settlement Proposal Documents Completed and Final Disposition Agreement Sent to Company for Signing (copy also sent to other parties, who may or may not sign) | Case Manager
145 | 2025-12-29 | 2025-12-29 | Signed Disposition Agreement Returned to Staff | Utility; OPC (if applicable)
|  |  | Staff Sends Revised Tariff Sheets and Draft Tariff Filing Transmittal Letter to the Utility | Case Manager
150 | 2026-01-03 | 2026-01-02 | Staff Files Executed Disposition Agreement | Case Manager
150 | 2026-01-03 | 2026-01-02 | Utility Files Necessary Tariff Revsions with a 45-day effective date | Utility
These dates are working days that require a filing 'no later than' the date shown
Formulas:
Target = 'Days 0-75'!$B7+[Target]
Calendar = [Target]
Calendar = [Target]-3
Note on D22: Gateley, Curtis: No later than Day 120, so may have to be earlier to comply with the rule.

## Non-Unam Agreement
Page 3 of 5 Pages
This section pertains to the situation where only the Utility and Staff reach an agreement on the overall disposition of the request, but OPC or other intervenors have not requested an evidentiary hearing. The dates shown assume that the Utility will make a 45-day tariff filing on Day 155. If an evidentiary hearing is requested, a procedural schedule will be filed for the case beyond day 150 which will supersede this timeline.
Target | Target | Calendar |  | Responsible
Day | Due Date | Due Date | Case Activity | "Party"
157 | 2026-01-10 | 2026-01-09 | OPC or Other Intervenors File Position Statement(s) | OPC & Other Intervenors
165 | 2026-01-18 | 2026-01-18 | Staff Recommendation Filed if applicable OR ordered by the Commission. (Can include motion for suspension of tariff revisions requesting correction of any deficiencies) | Case Manager
185 | 2026-02-07 | 2026-02-07 | Order Approving Tariff Revisions Issued | Assigned RLJ
195 | 2026-02-17 | 2026-02-16 | Tariff Revisions Effective "On and After" this Date | N/A
210 | 2026-03-04 | 2026-03-04 | Notice Closing Case Issued | Assigned RLJ
These dates are working days that require a filing 'no later than' the date shown
Formulas:
Target = 'Days 0-75'!$B7+[Target]
Calendar = [Target]-1
Calendar = [Target]
Note on C9: Gateley, Curtis: Must be at least 5 business days, so look out for holidays in between day 150 and 157
Note on C18: Gateley, Curtis: This is 45 days, ignore holidays

## Unanimous Agreement
Page 4 of 5 Pages
This section pertains to the situation where all parties reach an agreement on the overall disposition of the request. The dates shown assume that the Utility will make a 30-day tariff filing on Day 155. This timeline assumes the Commission approves the agreement and no evidentiary hearing is necessary.
Target | Target | Calendar |  | Responsible
Day | Due Date | Due Date | Case Activity | "Party"
150 | 2026-01-03 | 2026-01-03 | Unanimous Disposition Agreement is Filed | Staff
157 | 2026-01-10 | 2026-01-09 | Utility Files Necessary Tariff Revisions with a 30-day effective date | Utility
165 | 2026-01-18 | 2026-01-16 | Staff Recommendation Filed if Ordered by the Commission. (Can include motion for suspension of tariff revisions requesting correction of any deficiencies) | Case Manager
175 | 2026-01-28 | 2026-01-28 | Order Approving Tariff Revisions Issued | Assigned RLJ
187 | 2026-02-09 | 2026-02-08 | Tariff Revisions Effective "On and After" this Date | N/A
200 | 2026-02-22 | 2026-02-20 | Notice Closing Case Issued | Assigned RLJ
These dates are working days that require a filing 'no later than' the date shown
Formulas:
Target = 'Days 0-75'!$B7+[Target]
Calendar = [Target]
Calendar = [Target]-1
Note on C19: Gateley, Curtis: 30 days, ignore holidays

## Evidentiary Hearing
Page 5 of 5 Pages
If the parties cannot reach an agreement by day 150 and an evidentiary hearing is necessary, then the parties must file a new procedural schedule in the case. If one of the parties requests and is granted an evidentiary hearing by the Commission prior to day 150, then the remaining dates in this timeline are moot as of the date of that order granting the evidentiary hearing and the parties must file a new procedural schedule.
Target | Target | Calendar |  | Responsible
Day | Due Date | Due Date | Case Activity | "Party"
157 | 2026-01-10 | 2026-01-09 | Utility Files Necessary Tariff Revisions | Utility
165 | 2026-01-18 | 2026-01-16 | Parties File a Procedural Schedule | All Parties
These dates are working days that require a filing 'no later than' the date shown
Formulas:
Target = 'Days 0-75'!$B7+[Target]
Calendar = [Target]-1